## B Sc.7-Nischay
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) |  | Expenditure Till Date (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects |  | REMARKS
1 | Construction of B.Sc Nursing College |  | 42396.16 (2649.76 per unit) | 42396 |  | 4177.2665 |  | 16 | 0 | 7 |  | 9 |  | -
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Darbhanga | B.Sc Nursing College at DMCH, Laheriasarai (Darbhanga) | 2649.76 | 2016-07-18 | BBCPL-SKPL (JV) | 2197.1602 | 2017-03-31 | 2019-03-30 | Hostel Block-Roof casted (5th Floor) Academic block-Roof shuttering (Terrace floor) | 45% | 1052.29 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
2 | Muzaffarpur | B.Sc Nursing College at SKMCH, Muzaffarpur | 2649.76 | 2016-07-18 | M/S Satyam Builder | 2043.114 | 2017-03-31 | 2019-03-30 | Hostel Block-Roof reinforcement binding (G.F) Academic block-Roof shuttering (F.F) | 25% | 373.36 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
3 | Gaya | B.Sc Nursing College at ANMMCH, Gaya | 2649.76 | 2016-07-18 | Raj Construction | 2000.6939 | 2017-05-05 | 2019-05-04 | College Block- Internal Plaster is in progress (G.F). Hostel Block- Brick work (5th .F) | 45% | 669.2105 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
4 | Bhagalpur | B.Sc Nursing College at JLNMCH, Bhagalpur | 2649.76 | 2016-07-18 | Lalan Kumar, Bhagalpur | 2176.9024 | 2017-03-31 | 2019-03-30 | Hostel Block-Finishing work Academic Block- Finishing work | 72% | 726.256 | Sri Anil Kumar | Sri Sanjeev Ranjan
5 | Nalanda | B.Sc Nursing College at Vardhaman Ayurvigyan Sansthan, Pawapuri, Nalanda | 2649.76 | 2016-07-18 | Balkrishna Bhalotia | 2126.7702 | 2017-03-31 | 2019-03-30 | Hostel Block-Finishing Work Academic Block- Finishing Work | 85% | 1081.92 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
6 | Bettiah | B.Sc Nursing College at Govt. Medical College, Bettiah | 2649.76 | 2016-07-18 | Larsen & Turebo | 51355 | 2017-07-10 | 2020-07-09 | work is going on | 10% | 0 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | Being Constructed with Medical College
7 | Purnea | B.Sc Nursing College at Govt. Medical College, Purnea (Sadar Hospital Campus) & Para Medical Institute | 2649.76 | 2016-07-18 | Umakant Singh, Katihar | 2945.656 | 2017-03-31 | 2019-03-30 | Hostel Block-Column work (4th Floor) | 16% | 274.23 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
8 | Patna | B.Sc Nursing College at PMCH, Patna | 2649.76 | 2016-07-18 | Dhanpat Prasad | 2166.2659 | 2017-08-18 | 2019-08-17 | Not started | 0% | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Work is kept on hold because of PMCH redevelopment
| Total |  | 21198.08 |  |  | 67011.5627 |  |  |  |  | 4177.2665

## GNM 7-Nischay (2)
CONSTRUCTION OF GENERAL NURSE MIDWIFERY (G.N.M)
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) |  | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects | REMARKS
1 | Construction of GNM training school & hostel |  | 30713.74 (1335.38 per unit) |  | 2000 | 3313.6381 |  | 23 | 0 | 12 |  | 11 | -
Detailed Report
SL NO | DISTRICT | NAME OF PLACES | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Arariya | Construction of Combined Building of ANM, GNM & Para medical Institute with Hostel at Mauja- Basantpur Arariya | 630.72+1335.38+998.00=2964.10 | 2016-07-18 | Srinath Builder & Housing co. pvt ltd | 2476.4924 | 2017-03-24 | 2019-03-23 | Academic Block: Plinth Level | 10% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Letter sent to electricity department for removing wire on proposed site
4 |  | Vill-Mirzapur,Khata no.-251, Begusarai | [6 empty] | Foundation started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land available on 02.12.2016, DPR under process.
2 | Arwal | Construction of Combined Building of ANM, GNM & Para medical Institute with Hostel at Sadar Hospital, Arwal | 630.72+1335.38+998.00=2964.10 | 2016-07-18 | B.Rai | 2262.3791 | 2018-02-28 | 2020-02-27 | Academic Block- Roof shuttering (2nd.F) Hostel Block- Column casted (2nd .F) | 23% | 542.0362 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
3 | Katihar | Construction of Combined Building of GNM & Para medical Institute at Sadar Hospital, Katihar | 1335.38+998=2333.38 | 2016-07-18 | Adyaraj Construction | 2048.372 | 2017-04-26 | 2018-10-25 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | redesign work is in process
4 | Khagaria | Construction of Combined Building of GNM & Para medical Institute at Old Subdivisional Hospital, Khagaria | 1335.38+998=2333.38 | 2016-07-18 | Macro Ranjan const. pvt ltd | 2066.1106 | 2017-03-24 | 2018-09-23 | Academic Block- Plaster work,Hostel Block -Roof shuttering (2nd.F) | 45% | 646.83 | Sri Anil Kumar | Sri Rajendra Prasad Singh
5 | Munger | Construction of Combined Building of GNM & Para medical Institute at Leprosy Hospital Munger | 1335.38+998=2333.38 | 2016-07-18 | Lalan Kumar | 2020.1324 | 2017-03-24 | 2018-09-23 | Academic Block- Column work (Mumty) Hostel Block- Roof Shuttering (3rd Floor) | 42% | 844.19 | Sri Anil Kumar | Sri Rajendra Prasad Singh
6 | Nawada | Construction of Combined Building of GNM & Para medical Institute at Budhaul, Nawada | 1335.38+998=2333.38 | 2016-07-18 | Dhanpat Prasad | 1812.2956 | 2018-01-29 | 2019-07-28 | Academic Block-Column work (G.F) Hostel-Plinth work | 17% | 104.97 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
6 |  | Govt. Medical college, Samastipur |  | 2016-07-18 | Samastipur | [5 empty] | To be constructed with Medical College | Sri Anil Kumar | Sri Rajendra Prasad Singh
6.5 |  | Sadar Hospital, Sheohar |  | 2016-07-18 | Sheohar | [5 empty] | DPR in process. | Sri Sunil Kumar | Sri Rajendra Prasad Singh
7 | Jamui | Construction of Combined Building of GNM & Para medical Institute at Vill-Mahuli , Jamui | 1335.38+998=2333.38 | 2016-07-18 | Sudesh Kumar Singh & Company Const. Pvt ltd | 1961.7455 | 2018-02-12 | 2019-08-11 | Academic Block-Roof shuttering (2nd Floor) Hostel-Roof shuttering (2nd Floor) | 23% | 337.02 | Sri Anil Kumar | Sri Rajendra Prasad Singh
8 | Bhojpur | Construction of Combined Building of GNM & Para medical Institute at Bhojpur | 1335.38+998=2333.38 | 2016-07-18 | Simens Construction Corporation | 1903.6832 | 2018-05-29 | 2019-11-28 | Academic Block-Foundation work completed Hostel- Foundation work started | 10% | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
9 | East Champaran | Construction of Combined Building of GNM & Para medical Institute at Sadar Hospital, East Champaran | 1335.38+998=2333.38 | 2016-07-18 | Rama & Sons | 2176.3982 |  |  |  |  | 0 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | LOA issued on 02/02/2018
10 | Siwan | Construction of Combined Building of GNM & Para medical Institute at SDH Mahrajganj, Siwan | 1335.38+998=2333.38 | 2016-07-18 | M/s B.Prasad & Company | 2036.621 | 2018-05-08 | 2019-11-07 | Girl's Hostel- Plinth Beam Completed. Academic Block-Brick work is in progress | 15% | 354 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
11 | Aurangabad | Construction of Combined Building of GNM & Para medical Institute at Sadar Hospital, Aurangabad | 1335.38+998=2333.38 | 2016-07-18 | M/s Raj Construction | 1870.4254 |  |  |  |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on-27/02/2018
12 | Gopalganj | Construction of GNM Training Institute at Sub-Divisional Hospital Hathua, Gopalganj | 1335.38 | 2016-07-18 | AIPLGMC-JV | 1143.7575 | 2018-02-01 | 2019-08-31 | Acadmic Block- Column casted (G.F) Hostel Block -Plinth work is in progress | 10% | 0 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Transformer and Electrical Pole Reloction work in progresss
13 | Lakhisarai | Construction of GNM Training Institute at Balguddar Ashokdham, Lakhisarai | 1335.38 | 2016-07-18 | M/S Kanhaiya Contractor Pvt Ltd | 1119.9246 |  |  |  |  | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | LOA issued on 05/08/2017 (Land recently available)
14 | Supaul | Construction of GNM Training Institute at Mauja- Kharail, ward no-01, Supaul | 1335.38 | 2016-07-18 | Ashok Kumar Patori, Saharsa | 1123.12 | 2018-05-29 | 2019-11-28 | Acadmic Block- Column casted (G.F) Hostel Block -Plinth work is in progress | 18% | 198.5 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
15 | Sitamarhi | Construction of GNM Training Institute at Vill-Mirzapur, Dumra, Dist- Sitamarhi | 1335.38 | 2016-07-18 | Shashikant Singh | 1120.6777 |  |  |  |  | 0 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | 2 Plots given by D.M Sitamarhi have seen, Land demarkation work is in progress
16 | Kaimur | Construction of GNM Training Institute at Vill-Barka Katra, Bhabhua (Kaimur) | 1335.38 | 2016-07-18 | Yashaswi Infrastructure, Ranchi | 1169.4182 | 2018-05-04 | 2019-08-03 | Academic Block-Plinth Level Hostel- Plinth Level | 10% | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
17 | Madhubani | Construction of GNM Training Institute at Mauja-Raghopur Balat, Dist- Madhubani | 1335.38 | 2016-07-18 | SKS & KKT | 1122.585 |  |  | Academic Block-Column work below Plinth Level Hostel- Tie Beam is in progress | 12% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
18 | Nalanda | Construction of Combined Building of GNM & Para medical Institute at Vardhaman Institute of Medical Science Pawapuri Nalanda | 1335.38+998=2333.38 | 2016-07-18 | Satyanarayan Singh | 1924.7252 | 2018-04-28 | 2019-10-27 | Roof Shuttering (F.F) | 15% | 286.0919 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
[7 empty] | Total |  |  |  | 3313.6381

## Para Medical 7-Nischay (2)
PARA-MEDICAL INSTITUTE WITH HOSTEL
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) |  | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of Para Medical Institute |  | 32934.00 (998.00 per unit) |  | 2000 | 5823.4454 | 33 | 0 | 19 | 14 |  | -
Detailed Report
SL NO | DISTRICT | NAME OF PLACES | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Purnea | B.Sc Nursing College at Govt. Medical College, Purnea (Sadar Hospital Campus) & Para Medical Institute | 2649.76 | 2016-07-18 | Umakant Singh, Katihar | 2945.656 | 2017-03-31 | 2019-03-30 | Hostel Block-Column work (4th Floor) | 16% | 274.23 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
2 | Arariya | Construction of Combined Building of ANM, GNM & Para medical Institute with Hostel at Mauja- Basantpur Arariya | 630.72+1335.38+998.00=2964.10 | 2016-07-18 | Srinath Builder & Housing co. pvt ltd | 2476.4924 | 2017-03-24 | 2019-03-23 | Academic Block: Plinth Level | 10% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Letter sent to electricity department for removing wire on proposed site
3 | Arwal | Construction of Combined Building of ANM, GNM & Para medical Institute with Hostel at Sadar Hospital, Arwal | 630.72+1335.38+998.00=2964.10 | 2016-07-18 | B.Rai | 2262.3791 | 2018-02-28 | 2020-02-27 | Academic Block- Roof shuttering (2nd.F) Hostel Block- Column casted (2nd .F) | 23% | 542.0362 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
4 | Katihar | Construction of Combined Building of GNM & Para medical Institute at Sadar Hospital, Katihar | 1335.38+998=2333.38 | 2016-07-18 | Adyaraj Construction | 2048.372 | 2017-04-26 | 2018-10-25 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | redesign work is in process
5 | Khagaria | Construction of Combined Building of GNM & Para medical Institute at Old Subdivisional Hospital, Khagaria | 1335.38+998=2333.38 | 2016-07-18 | Macro Ranjan const. pvt ltd | 2066.1106 | 2017-03-24 | 2018-09-23 | Academic Block- Plaster work,Hostel Block -Roof shuttering (2nd.F) | 45% | 646.83 | Sri Anil Kumar | Sri Rajendra Prasad Singh
6 | Munger | Construction of Combined Building of GNM & Para medical Institute at Leprosy Hospital Munger | 1335.38+998=2333.38 | 2016-07-18 | Lalan Kumar | 2020.1324 | 2017-03-24 | 2018-09-23 | Academic Block- Column work (Mumty) Hostel Block- Roof Shuttering (3rd Floor) | 42% | 844.19 | Sri Anil Kumar | Sri Rajendra Prasad Singh
7 | Nawada | Construction of Combined Building of GNM & Para medical Institute at Budhaul, Nawada | 1335.38+998=2333.38 | 2016-07-18 | Dhanpat Prasad | 1812.2956 | 2018-01-29 | 2019-07-28 | Academic Block-Column work (G.F) Hostel-Plinth work | 17% | 104.97 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
8 | Jamui | Construction of Combined Building of GNM & Para medical Institute at Vill-Mahuli , Jamui | 1335.38+998=2333.38 | 2016-07-18 | Sudesh Kumar Singh & Company Const. Pvt ltd | 1961.7455 | 2018-02-12 | 2019-08-11 | Academic Block-Roof shuttering (2nd Floor) Hostel-Roof shuttering (2nd Floor) | 23% | 337.02 | Sri Anil Kumar | Sri Rajendra Prasad Singh
9 | Bhojpur | Construction of Combined Building of GNM & Para medical Institute at Bhojpur | 1335.38+998=2333.38 | 2016-07-18 | Simens Construction Corporation | 1903.6832 | 2018-05-29 | 2019-11-28 | Academic Block-Foundation work completed Hostel- Foundation work started | 10% | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
10 | East Champaran | Construction of Combined Building of GNM & Para medical Institute at Sadar Hospital, East Champaran | 1335.38+998=2333.38 | 2016-07-18 | Rama & Sons | 2176.3982 |  |  |  |  | 0 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | LOA issued on 02/02/2018
11 | Siwan | Construction of Combined Building of GNM & Para medical Institute at SDH Mahrajganj, Siwan | 1335.38+998=2333.38 | 2016-07-18 | M/s B.Prasad & Company | 2036.621 | 2018-05-08 | 2019-11-07 | Girl's Hostel- Plinth Beam Completed. Academic Block-Brick work is in progress | 15% | 354 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
12 | Aurangabad | Construction of Combined Building of GNM & Para medical Institute at Sadar Hospital, Aurangabad | 1335.38+998=2333.38 | 2016-07-18 | M/s Raj Construction | 1870.4254 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on-27/02/2018
13 | Madhepura | Construction of Combined Building of ANM & Para medical Institute at Vill-Parariya, Madhepura | 630.72+998=1628.72 | 2016-07-18 | M/S Satyanarayan Singh, Jharkhand | 1368.6909 | 2018-03-31 | 2019-09-30 | Girls Hostel : Column casted upto plinth & filling work in progress. Academic Block: Tie-beam casting Completed. | 8% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
14 | Nalanda | Construction of Combined Building of GNM & Para medical Institute at Pavapuri Medical College Campus, Nalanda | 1335.38+998=2333.38 | 2016-07-18 | M/S Satyanarayan Singh, Jharkhand | 1924.7252 | 2018-04-28 | 2019-10-27 | Roof Shuttering (F.F) | 15% | 286.0919 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
15 | Banka | Construction of Para Medical Institute at Sadar Hospital (Old Campus), Banka | 998 | 2016-07-18 | Rana construction | 806.186 | 2017-05-05 | 2018-10-04 | Academic Block-Finishing work. Girls Hostel- Finishing work, Boys Hostel- Brick work (2nd F) | 80% | 550.26 | Sri Anil Kumar | Sri Sanjeev Ranjan
|  | Sherpur, Begusarai | 998 | 2016-07-18 | [7 empty] | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Land made available on 02/12/2016, DPR under process.
16 | Buxar | Construction of Para Medical Institute at Sadar Hospital, Buxar | 998 | 2016-07-18 | B. Prasad | 822.3936 | 2017-08-07 | 2018-11-06 | Girl's Hostel-Finishing work, Boys Hostel- Finishing work Academic Block- Structure completed | 70% | 457.517 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
17 | Gopalganj | Construction of Para Medical Institute at Sub-Divisional Hospital, Gopalganj (Hathuwa) | 998 | 2016-07-18 | G.M construction | 942.277 | 2017-03-31 | 2018-06-30 | Academic Block- Column work (2nd.F), Girls Hostel- Column work (2nd.F), Boys Hostel-Column work (2nd.F) | 30% | 400 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
18 | Jehanabad | Construction of Para Medical Institute at Vill-Jamuawan, Jehanabad | 998 | 2016-07-18 | Kaushlendra Kumar | 820.6657 |  |  | - | 0% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 02/08/2017 (Clear land not available)
|  | Kochhadhaman, Vill-Patkoikla, Kishanganj | 998 | 2016-07-18 | [7 empty] | Sri Anil Kumar | Sri Rajendra Prasad Singh | DPR in process.
19 | Lakhisarai | Construction of Para Medical Institute at Mesona, Lakhisarai | 998 | 2016-07-18 | Kanhaiya Contractor pvt ltd | 817.6537 |  |  |  |  | 0 | Sri Anil Kumar | Sri Sanjeev Ranjan | T.s in process
20 | Madhubani | Construction of Para Medical Institute at Sadar Hospital, Madhubani | 998 | 2016-07-18 | Sanjay Kumar | 879.1656 | 2017-05-09 | 2018-08-08 |  |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Letter sent to D.M for alternative Land
21 | Rohtas | Construction of Para Medical Institute at Sadar Hospital, Rohtas | 998 | 2016-07-18 | Ramesh Kumar Pandey | 838.6326 | 2017-08-05 | 2018-11-04 | Girl's Hostel-Finishing work, Boys Hostel-Finishing work, Admin Block- Finishing work | 95% | 838.6326 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
22 | Saharsa | Construction of Para Medical Institute at Sadar Hospital, Saharsa | 998 | 2016-07-18 | C.S construction | 884.7711 | 2017-03-31 | 2018-08-30 | Academic Block-Tie Beam completed Girls Hostel- Tie Beam Boys Hostel- Tie Beam | 20% | 187.6677 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
|  | Samastipur | 998 | 2016-07-18 |  |  |  |  | Academic Block-Tie Beam completed Girls Hostel- Tie Beam Boys Hostel- Tie Beam |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | To be constructed with medical college
23 | Saran | Construction of Para Medical Institute at Sadar Hospital Chhapra,Saran | 998 | 2016-07-18 | G.M construction | 861.2227 | 2018-05-04 | 2019-08-03 | Academic Block-Plinth Level Girls Hostel- Work start Boys Hostel- Tie Beam | 10% | 0 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
11 |  | Awadhe (In back of HSC), Seikhpura | 998 | 2016-07-18 | [7 empty] | Sri Pankaj Kumar | Sri Rajendra Prasad Singh | DPR in process.
|  | Sadar Hospital, Sheohar | 998 | 2016-07-18 | [7 empty] | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | DPR in process.
24 |  | Sub-Divisional hospital Maharajganj, Siwan | 998 | 2016-07-18 | [7 empty] | Sri Sunil Kumar | Sri Rajendra Prasad Singh
14.194 |  | Rajapakar, Vaishali | 998 | 2016-07-18 | Indra Narayan Singh contract pvt ltd | [6 empty] | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
24 | Sitamarhi | Construction of Para Medical Institute at Sadar Hospital, Sitamarhi | 998 | 2016-07-18 | Shashikant Singh | 838.1931 | [5 empty] | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | 2 Plots given by D.M Sitamarhi have seen, Land demarkation work is in progress
25 | Supaul | Construction of Para Medical Institute at Mauja Supaul, ward no-12, Supaul | 998 | 2016-07-18 | Indra Narayan Singh contract pvt ltd | 854.8981 | [5 empty] | Sri Sunil Kumar | Sri Rajendra Prasad Singh | LOA to be issued
26 | West Champaran | Construction of Para Medical Institute at Sadar Hospital, West Champaran | 998 | 2016-07-18 | Larsen & Turebo | 51355 | 2017-07-10 | 2020-07-09 | Foundation work is going on | 10% | 0 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
27 | Madhepura | Construction of Para Medical Institute at Madhepura | 998 | 2016-07-18 | M/S Satyanarayan Singh, Jharkhand |  | 2018-03-31 | 2019-09-30 | Foundation work is going on | 8% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
28 | Kaimur | Construction of Para Medical Institute at Sarangpur | 998 | 2016-07-18 | Ajay Kumar Singh | 838.7775 | [5 empty] | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | LOA issued on 30/05/2018
29 | Sheikhpura | Construction of Para Medical Institute at Sadar Hospital, Sheikhpura | 998 | 2016-07-18 | Sanjay Kumar Technocrate Pvt. Ltd, Patna | 837.7555 | [5 empty] | Sri Anil Kumar | Sri Rajendra Prasad Singh | LOA issued on-30/05/2018 (T.S in process)
| Total |  |  |  |  | 89594.7868 |  |  |  |  | 5823.4454

## ANM 7-Nischay (2)
CONSTRUCTION OF AUXILIARY NURSE MIDWIFERY (A.N.M)
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) |  | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects | REMARKS
1 | Construction of ANM training school & hostel |  | 34058.88 (630.72 per unit) |  | 4000 | 0 |  | 54 | 0 | 34 |  | 20 | -
Detailed Report
SL NO | DISTRICT | NAME OF PLACES | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Arariya | Construction of Combined Building of ANM, GNM & Para medical Institute with Hostel at Mauja- Basantpur Arariya | 630.72+1335.38+998.00=2964.10 | 2016-07-18 | Srinath Builder & Housing co. pvt ltd | 2476.4924 | 2017-03-24 | 2019-03-23 | Academic Block: Plinth Level | 10% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Letter sent to electricity department for removing wire on proposed site
2 | Arwal | Construction of Combined Building of ANM, GNM & Para medical Institute with Hostel at Sadar Hospital, Arwal | 630.72+1335.38+998.00=2964.10 | 2016-07-18 | B.Rai | 2262.3791 | 2018-02-28 | 2020-02-27 | Academic Block- Roof shuttering (2nd.F) Hostel Block- Column casted (2nd .F) | 23% | 542.0362 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
3 | Madhepura | Construction of Combined Building of ANM & Para medical Institute at Vill-Parariya, Madhepura | 630.72+998.00=1628.72 | 2016-07-18 | M/S Satyanarayan Singh, Jharkhand | 1368.6909 | 2018-03-31 | 2019-09-30 | Girls Hostel : Column casted upto plinth & filling work in progress. Academic Block: Tie-beam casting Completed. | 8% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
4 | Arariya | Construction of ANM Training Institute & Hostel at Sub-Divisional Farbisganj, Arariya | 630.72 | 2016-07-18 | Topline Infra Projects Pvt ltd, Katihar | 568.3513 | 2017-07-24 | 2018-07-23 | Plaster work is in progress | 60% | 229.82 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
6 |  | Sub-Divisional Teghra, Begusarai |  | 2016-07-18 | [6 empty] | Land made available on 02/12/2016, DPR under progress. | Sri Anil Kumar | Sri Sanjeev Ranjan
5 | Bhagalpur | Construction of ANM Training Institute & Hostel atSub-Divisional Kahalgaon, Bhagalpur | 630.72 | 2016-07-18 | Ramesh Kumar, Patna | 526.4984 | 2018-03-15 | 2019-03-14 | Column work (2nd.F) | 27% | 114.0294 | Sri Anil Kumar | Sri Sanjeev Ranjan
6 |  | Sub-Divisional Navgachia, Bhagalpur | 630.72 | 2016-07-18 | [6 empty] | DPR in process. | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
6 | Bhojpur | Construction of ANM Training Institute & Hostel at Sub-Divisional Jagdispur, Bhojpur | 630.72 | 2016-07-18 | Ramesh Kumar Pandey | 509.8036 | 2017-09-06 | 2018-09-05 | Completed | 100% | 192.43 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
7 | Bhojpur | Construction of ANM Training Institute & Hostel at Sub-Divisional Piro, Bhojpur | 630.72 | 2016-07-18 | Anil Kumar | 529.9584 | - | - | Pile cap work is going on | 10% | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
8 |  | Sub-Divisional Dumrao, Buxar | 630.72 | 2016-07-18 | [6 empty] | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
8 | Darbhanga | Construction of ANM Training Institute & Hostel at Sub-Divisional Biraul, Darbhanga | 630.72 | 2016-07-18 | Kuwar Construction | 530.2326 | 2017-11-02 | 2018-11-01 |  |  | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Letter sent to D.M for alternative land
9 | East Champaran | Construction of ANM Training Institute & Hostel at Sub-Divisional Areraj, East Champaran | 630.72 | 2016-07-18 | M/s S. K Enterprises | 535.8296 | 2017-12-02 | 2018-12-01 | Academic Block- Roof Shuttering (2nd.F) Hostel Block- Brick work (Terrace Floor) | 25% | 125.11 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
15 |  | Sub-Divisional Raxaul, East Champaran | 630.72 | 2016-07-18 | [6 empty] | DPR in process. | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
18 |  | Sub-Divisional Pakri Dayal, East Champaran | 630.72 | 2016-07-18 | [7 empty] | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
10 | Gaya | Construction of ANM Training Institute & Hostel at Sub-Divisional Neemchak Bathani, Gaya | 630.72 | 2016-07-18 | Anil Kumar Singh | 508.3432 | 2018-01-04 | 2019-01-03 | Brick work is in going on | 48% | 229.4536 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
11 | Gaya | Construction of ANM Training Institute & Hostel at Sub-Divisional Sherghati, Gaya | 630.72 | 2016-07-18 | Ambe Infra | 461.1001 | 2017-11-02 | 2018-11-01 | Roof Shuttering is in progress (F.F) | 25% | 111.0357 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
12 | Gaya | Construction of ANM Training Institute & Hostel at Sub-Divisional Tekari, Gaya | 630.72 | 2016-07-18 | Mukesh Kumar | 543.0482 | 2017-11-07 | 2018-11-06 | Brick work is in going on | 40% | 200.6521 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
13 | Katihar | Construction of ANM Training Institute & Hostel at Sub-Divisional Barsoi, Katihar | 630.72 | 2016-07-18 | Krishnakant Thakur, Darbhanga | 530.4278 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on-30/05/2018
14 | Katihar | Construction of ANM Training Institute & Hostel at Sub-Divisional Manihari, Katihar | 630.72 | 2016-07-18 | Sudesh Kumar Singh & co. Pvt ltd., Jamui | 521.6393 | 2017-09-21 | 2018-09-20 | Finishing work is in progress | 70% | 256.9952 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
15 | Khagaria | Construction of ANM Training Institute & Hostel at Sub-Divisional Gogri, Khagaria | 630.72 | 2016-07-18 | Arvind Kumar Singh | 530.455 | 2018-01-12 | 2019-01-11 | Acadmic block - Roof casted (G.F), Hostel Block- Roof Shuttering (G.F) | 20% | 129 | Sri Anil Kumar | Sri Rajendra Prasad Singh
16 | Madhepura | Construction of ANM Training Institute & Hostel at Sub-Divisional Uda Kishanganj, Madhepura | 630.72 | 2016-07-18 | C.S. Construction | 556.0964 | 2017-05-05 | 2018-05-04 | Roof shuttering (F.F) | 35% | 200.38 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
17 | Madhubani | Construction of ANM Training Institute & Hostel at Sub-Divisional Jainagar, Madhubani | 630.72 | 2016-07-18 | Maa Tara | 529.7998 | 2017-06-28 | 2018-06-27 | Acadmic block - Finishing work, Hostel Block- Finishing work | 65% | 255.64 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
18 | Madhubani | Construction of ANM Training Institute & Hostel at Sub-Divisional Benipatti, Madhubani | 630.72 | 2016-07-18 | M/s Kuwar Const., Darbhanga | 530.3068 | 2018-05-17 | 2019-05-16 | Acadmic block - Column work (G.F), Hostel Block- Foundation work is going on | 15% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
19 | Madhubani | Construction of ANM Training Institute & Hostel at Sub-Divisional Jhanjharpur, Madhubani | 630.72 | 2016-07-18 | Gridhari Lal Poddar | 521.9843 | 2017-11-07 | 2018-11-06 | College -Plaster work is going on Hostel - Plaster work is going on | 60% | 329.1 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
20 | Madhubani | Construction of ANM Training Institute & Hostel atSub-Divisional Phulparas, Madhubani | 630.72 | 2016-07-18 | Sanjay Kumar,Darbhanga | 528.9036 | 2018-04-28 | 2019-04-27 |  |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Old structure to be demolished
21 | Munger | Construction of ANM Training Institute & Hostel at Sub-Divisional Tarapur, Munger | 630.72 | 2016-07-18 | Lalan Kumar | 529.2102 | 2017-06-16 | 2018-06-15 | Acadmic block - Finishing work, Hostel Block- Finishing work | 75% | 122.25 | Sri Anil Kumar | Sri Rajendra Prasad Singh
22 | Darbhanga | Construction of ANM Training Institute & Hostel at Sub-Divisional Benipur, Darbhanga | 630.72 | 2016-07-18 | Sanjay Kumar | 526.6764 | 2018-05-17 | 2019-05-16 | Column work (G.F) | 14% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
23 | Patna | Sub-Divisional Paliganj, Patna | 630.72 | 2016-07-18 | [6 empty] | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
24 | Purnea | Construction of ANM Training Institute & Hostel at Sub-Divisional Banmankhi, Purnea | 630.72 | 2016-07-18 | Bambam Kumar Singh | 527.2303 | 2018-01-29 | 2019-01-28 | Plaster work is in progress | 60% | 243.05 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
25 | Purnea | Construction of ANM Training Institute & Hostel at Sub-Divisional Dhamdaha, Purnea | 630.72 | 2016-07-18 | M/S C.S Construction, Arariya | 530.0653 | 2017-08-18 | 2018-08-17 | - |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Site not clear
26 | Rohtas | Construction of ANM Training Institute & Hostel at Sub-Divisional Bikramganj, Rohtas | 630.72 | 2016-07-18 | Ram Babu Prasad | 513.0162 | 2018-02-27 | 2019-02-26 | Roof shuttering (Terrace Floor) | 40% | 117 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
27 | Saharsa | Construction of ANM Training Institute & Hostel at Sub-Divisional Simri Bakhtiyarpur, Saharsa | 630.72 | 2016-07-18 | Santosh Singh, Saharsa | 509.3739 | 2017-07-14 | 2018-07-13 | Roof shuttering (G.F) | 18% | 68.27 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land available in Feb'2018
28 | Samastipur | Construction of ANM Training Institute & Hostel at Sub-Divisional Dalsinghsarai, Samastipur | 630.72 | 2016-07-18 | Vinod Kumar Singh | 521.3588 | 2017-10-09 | 2018-10-08 | Acadmic block - Brick work completed, Hostel.Block- Brick work (F.F) | 30% | 137.367 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
29 | Samastipur | Construction of ANM Training Institute & Hostel at Sub-Divisional Patori, Samastipur | 630.72 | 2016-07-18 | Vinod Kumar Singh | 521.4811 | 2017-10-09 | 2018-10-08 | Roof casted (Terrace Floor) | 35% | 140.4 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
30 | Saran | Construction of ANM Training Institute & Hostel at Sub-Divisional Madhaura, Saran | 630.72 | 2016-07-18 | [6 empty] | 0 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | In Tender, Nit no-39/2017
31 | Saran | Construction of ANM Training Institute & Hostel at Sub-Divisional Sonpur, Saran | 630.72 | 2016-07-18 | Kaushal buildcon | 511.9467 | 2017-07-20 | 2018-07-19 | Column work (2nd.F) | 35% | 170 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
32 | Sitamarhi | Construction of ANM Training Institute & Hostel atSub-Divisional Pupri, Sitamarhi | 630.72 | 2016-07-18 | Sanjay Kumar | 530.03 | 2017-05-17 | 2018-05-16 |  |  |  | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Land provided is in too deep
33 | Supaul | Construction of ANM Training Institute & Hostel at Sub-Divisional Birpur, Supaul | 630.72 | 2016-07-18 | Kunal Kush | 529.6355 | 2017-07-20 | 2018-07-19 | Finishing work is going on | 75% | 372.89 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
34 | Supaul | Construction of ANM Training Institute & Hostel at Sub-Divisional Nirmali, Supaul | 630.72 | 2016-07-18 | Santosh Singh, Saharsa | 540.6893 | 2017-06-16 | 2018-06-15 | Roof shuttering (G.F) | 20% | 86.22 | Sri Anil Kumar | Sri Rajendra Prasad Singh
35 | Vaishali | Construction of ANM Training Institute & Hostel at Sub-Divisional Sahdei Bujurg (Mahnar), Vaishali | 630.72 | 2016-07-18 | Kuwar Construction | 529.5936 | 2017-12-28 | 2018-12-27 | Column casting (3rd.F) | 27% | 65 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
19.6667 |  | CHC Rajapakar, Vaishali | 630.72 | 2016-07-18 | [7 empty] | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
36 | West Champaran | Construction of ANM Training Institute & Hostel at Sub-Divisional Bagha, West Champaran | 630.72 | 2016-07-18 | Shiva Infra Solution pvt ltd, | 545.8651 | 2017-05-17 | 2018-05-16 | Academic block- Fininshing work Hostel Block-Roof reinforcement binding (G.F) | 50% | 307.7365 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
37 | West Champaran | Construction of ANM Training Institute & Hostel at Sub-Divisional Narkatiyaganj, West Champaran | 630.72 | 2016-07-18 | Rama and sons, Patna | 523.1691 | 2017-11-07 | 2018-11-06 | Academic block-Finishing work Hostel Block-Finishing work | 75% | 371 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
38 | East Champaran | Construction of ANM Training Institute & Hostel at Sub-Divisional Sikarhana, East Champaran | 630.72 | 2016-07-18 | M/S Virendra Kumar Chaudhary | 586.34 | 2018-02-01 | 2019-01-31 | Academic block-Brick work (2nd Floor) Hostel Block- Brick work is going on (F.F) | 55% | 309.0354 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
39 | Munger | Construction of ANM Training Institute & Hostel at Sub-Divisional Haveli Khargpur, Munger | 630.72 | 2016-07-18 |  |  |  |  | Not Started |  | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | In Tender
40 | Suapul | Construction of ANM Training Institute & Hostel at Vill- Kharail, Supaul | 630.72 | 2016-07-18 | Arvind Kumar Singh | 530.2539 | 2017-10-22 | 2018-10-21 | Work started |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
41 | Begusarai | Construction of ANM Training Institute & Hostel at Sub-Divisional Baliya, Begusarai | 630.72 | 2016-07-18 | M/S Satyanarayan Singh, Jharkhand | 529.94 | 2018-02-13 | 2019-02-12 | Tie Beam | 10% | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh
42 | Begusarai | Construction of ANM Training Institute & Hostel at Sub-Divisional Bakhri, Begusarai | 630.72 | 2016-07-18 | M/S Satyanarayan Singh, Jharkhand | 529.65 | 2018-02-13 | 2019-02-12 | Not Started | - | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Land is disputed
43 | Begusarai | Construction of ANM Training Institute & Hostel at Sub-Divisional Manjhaul, Begusarai | 630.72 | 2016-07-18 | M/S Satyanarayan Singh, Jharkhand | 529.91 | 2018-02-13 | 2019-02-12 | Not Started | - | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Land is disputed
44 | Purnea | Construction of ANM Training Institute & Hostel at Sub-Divisional Vayasi, Purnea | 630.72 | 2016-07-18 | Umakant Singh | 530.1142 | - | - | - | - | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 16/01/2018, Land not available
45 | Samastipur | Construction of ANM Training Institute & Hostel at Sub-Divisional Rosara, Samastipur | 630.72 | 2016-07-18 | Sanjay Kumar, Darbhanga | 529.7572 | 2018-06-29 | 2019-06-29 | Academic block-Plinth Level Hostel Block- Plinth Level | 15% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
46 | East Champaran | Construction of ANM Training Institute & Hostel at Sub-Divisional Chakia, East Champaran | 630.72 | 2016-07-18 | Asiana Contract Pvt Ltd, Gopalganj | 529.5457 | 2018-03-31 | 2019-03-30 | Academic block-Roof Shuttering work (G.F) is going on Hostel Block- Roof Shuttering work (G.F) is going on | 15% | 67.19 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
47 | Gopalganj | Construction of ANM Training Institute & Hostel at APHC Baikunthpur, Gopalganj | 630.72 | 2016-07-18 | Baranwala Contract Pvt Ltd | 530.4564 | 2018-03-15 | 2019-03-14 | Column work (G.F) | 17% | 0 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
48 | Sitamarhi | Construction of ANM Training Institute & Hostel at Sub-Divisional Belsand, Sitamarhi | 630.72 | 2016-07-18 | Kabbu Khirhar | [6 empty] | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | T.S in process
[7 empty] | Total |  |  |  | 5493.0912

## GNM (3)
CONSTRUCTION OF GENERAL NURSE MIDWIFERY (G.N.M) under GOI schemes
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date with centage (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of GNM training school & hostel |  | 10772.98 | 3625 | 0 |  | 10 | 5 | 5 | 0
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | EXPENDITURE WITH CENTAGE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Rohtas | Construction of G.N.M Training school & hostels in Sadar hospital, Sasaram (Rohtas) | 1220.1724 | 2013-10-03 | M/S B Prasad & co. Anishabad, Patna | 894.3811 | 2014-06-11 | 2015-12-10 | Completed | 100% | 1047.27 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | Banka | Construction of G.N.M at Sadar Hospital Banka | 1222.3616 | 2013-10-03 | M/S Lalan Kumar | 969.1582 | 2014-11-26 | 2016-05-25 | Completed | 100% | 982.35 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
3 | Jahanabad | Construction of G.N.M at Sadar Hospital Jahanabad | 963.5628 | 2013-10-03 | M/S Yashaswi construction, Anishabad (Patna) | 941.7381 | 2015-11-27 | 2017-05-26 | Completed | 100% | 1089.49 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
4 | Saharsa | Construction of G.N.M at Sadar Hospital Saharsa | 1038.9261 | 2013-10-03 | Baba Hans construction Pvt. Ltd | 973.0374 | 2014-12-26 | 2016-06-25 | Completed | 100% | 835.12 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
5 | Saran | Construction of G.N.M at Sadar Hospital Chapra (Saran) | 1255.9296 | 2013-10-03 | M/S Harishankar Prasad | 1019.7473 | 2014-12-26 | 2016-06-25 | Block A-Finishing work Block B- Finishing work | 85% | 748.88 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
6 | Buxar | Construction of G.N.M at Sadar Hospital Buxar | 1004.8402 | 2013-10-03 | Rajesh Kumar | 845.0891 | 2017-05-09 | 2018-11-08 | Finishing work is in progress. | 85% | 671.78 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
7 | Purnea | Construction of G.N.M at Sadar Hospital Purnea | 1020.6944 | 2013-10-03 | M/S Satyanarayan Singh | 894.0844 | 2015-12-15 | 2017-06-14 | Academic Block-Finishing work is in progress | 48% | 283.12 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Clear land not available for hostel block.
8 | Sheikhpura | Construction of G.N.M at Sadar Hospital Sheikhpura | 983.4306 | 2013-10-03 | Arun Deo Kumar | 828.358 | 2015-12-31 | 2017-06-30 | Completed | 100% | 1024.55 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
9 | Madhepura | Construction of G.N.M at Medical College & Hospital Madhepura | 1040.9035 | 2013-10-03 | - | - | - | - | Finishing work is in progress. | 70% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Being constructed with Medical College. Hence separate expenditure not given.
10 | West Champaran | Construction of G.N.M at Bettiah, West Champaran | 1022.1539 | 2013-10-03 | Rama & Sons | 855.7345 | 2017-05-11 | 2018-11-10 | Finishing work is in progress. | 80% | 585.12 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
| Total |  | 10772.9751 |  |  | 8221.328 |  |  |  |  | 7267.68

## ANM (3)
CONSTRUCTION OF AUXILIARY NURSE MIDWIFERY (A.N under GOI schemes
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date with centage (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of ANM training school & hostel |  | 5120.94 | 1376 | 0 |  | 10 | 10 | 0 | - |  | -
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | EXPENDITURE WITH CENTAGE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Darbhanga | Construction of A.N.M school & hostel at refferal hospital Jale, Darbhanga | 584.9925 | 2013-09-24 | Avaneesh Enterprises, Ghaziabad | 436.89 | 2014-07-19 | 2015-07-18 | Completed | 100% | 315.09 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
2 | Nawada | Construction of A.N.M school & hostel at refferal hospital Rajauli, Nawada | 448.7312 | 2013-09-24 | Bipin Kumar, Nawada | 380.7919 | 2014-08-29 | 2015-08-28 | Completed | 100% | 418.34 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
3 | Siwan | Construction of A.N.M Training school & Hostel in Referral hospital, Mairwa (Siwan) | 593.2551 | 2013-09-24 | G.M Construction, Ahmedabad | 408.9828 | 2014-07-26 | 2015-07-25 | Completed | 100% | 385.54 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
4 | Aurangabad | Construction of A.N.M Training school & Hostel in Referral hospital, Daudnagar (Aurangabad) | 468.4109 | 2013-09-24 | Yashswi Infrastructure pvt. Ltd., Ranchi | 385.9641 | 2015-01-19 | 2016-01-18 | Completed | 100% | 416.89 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
5 | Kaimur | Construction of A.N.M Training school & Hostel in Sadar hospital, Bhabhua (Kaimur) | 484.7357 | 2013-09-24 | Anil Kumar, Rohtas | 409.0411 | 2014-08-25 | 24-08-2015 | Completed | 100% | 460.58 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
6 | Khagaria | Construction of A.N.M Training school & Hostel in Sadar hospital, Khagaria | 580.1198 | 2013-09-24 | Surendra Prasad Singh, Begusarai | 400.964 | 2015-01-09 | 2016-01-08 | Completed | 100% | 429.02 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
7 | Lakhisarai | Construction of A.N.M Training school & Hostel in Sadar hospital, Lakhisarai | 472.2124 | 2013-09-24 | Rama construction, Patna | 406.7411 | 2014-07-19 | 2015-07-18 | Completed | 100% | 459.35 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
8 | Supaul | Construction of A.N.M school & hostel at Sub-divisional hospital Triveniganj, Supaul | 502.7791 | 2013-09-24 | Avaneesh Enterprises, Ghaziabad | 426.5652 | 2014-07-18 | 2015-07-17 | Completed | 100% | 364.59 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
9 | Sheohar | Construction of A.N.M school & hostel at sadar hospital, sheohar | 501.5786 | 2013-09-24 | Virendra Kumar Chaudhary | 401.3985 | 2014-12-29 | 2015-12-28 | Completed | 100% | 447.94 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
10 | Jamui | Construction of A.N.M at Refferal Hospital Lakshmipur (Jamui) | 484.1236 | 2013-09-24 | M/S Balkrishan Dholakiya construction pvt ltd | 396.8122 | 2015-08-19 | 2016-05-18 | Completed | 100% | 424.58 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
| Total |  | 5120.9389 |  |  | 4054.151 |  |  |  |  | 4121.92

## DFID (2)
PROJECTS IN MEDICAL COLLEGES {UNDER DFID (Department for International Development, U.K.) FUNDING}
SL NO | Name of work |  | A.A. RECEIVED FROM | A.A Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Expenditure in Percentage (%) against agrrement | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects | REMARKS
1 | Construction of various project in Medical colleges of Bihar |  | Health Dept. | 16345.42 | 16345.42 | 10929.0271 | 80.76% | 21 | 15 | 5 |  | 1 (Diagnostic Centre)
Detailed Report (DFID)
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE EXPENDITURE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS IN LAKH) |  |  | STAGE | % | (RS IN LAKH)
NMCH, Patna
1 | Patna | CONSTRUCTION OF CENTRE OF EXCELLENCE AT NMCH, PATNA | 4211.7 | 2014-11-08 | M/S B. Rai | 3711.8095 | 2015-11-27 | 2017-05-26 | Completed | 100% | 4070.49 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
2 |  | CONSTRUCTION OF B.SC NURSING AT NMCH, PATNA | 2762.26 | 2015-03-25 | Indra Narayan Singh contractors pvt ltd, Patna | 2350.1997 | 2015-12-09 | 2017-06-08 | Completed | 100% | 24 77.12 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
3 |  | CONSTRUCTION OF VACCINE CENTRE AT NMCH, PATNA | 1094.24 | 2015-09-01 | M/S B. Prasad | 887.3434 | 2016-04-13 | 2017-10-12 | Completed | 100% | 875.83 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
4 |  | CONSTRUCTION OF MODEL RECORD ROOM AT NMCH, PATNA | 170.98 | 2015-04-28 | R.K infra services pvt ltd, Patna | 122.4525 | 2016-02-05 | 2016-11-04 | Completed | 100% | 101.1487 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
|  | Sub Total of NMCH | 8239.18 |  |  | 7071.805
PMCH, Patna
5 | Patna | CONSTRUCTION OF LECTURE THEATRE (250 seater) AT PMCH, PATNA | 275.08 | 2015-03-27 | Ramesh Kumar Pandey | 342.361 | 2015-12-09 | 2017-06-08 | Completed | 100% | 227.29 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
6 |  | CONSTRUCTION OF MODEL RECORD ROOM AT PMCH, PATNA | 170.98 | 2015-04-28 | Ramesh Kumar Pandey |  | 2015-12-09 | 2017-06-08 | Completed | 100% | 155.28 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
7 |  | CONSTRUCTION OF 150 BEDDED HOSTEL AT PMCH, PATNA | 1029.78 | 2015-04-28 | Sudhesh Kumar Singh & company pvt ltd | 812.0747 | 2015-12-09 | 2017-06-08 | Completed | 100% | 787.13 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
|  | Sub Total of PMCH | 1475.84 |  |  | 1154.4356
ANMMCH, Gaya
8 | Gaya | CONSTRUCTION OF CENTRAL LIBRARY AT ANMMCH, GAYA | 584.55 | 2015-04-28 | Simens construction corporation, Patna | 2703.6702 | 2015-12-31 | 2017-12-30 | Finishing work is in progress | 90% | 588.98 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
9 |  | CONSTRUCTION OF MODEL RECORD ROOM AT ANMMCH, GAYA (Above central library) | 170.98 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 |  |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
10 |  | CONSTRUCTION OF EMERGENCY WARD AT ANMMCH, GAYA | 1294.74 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 | Finishing work is in progress | 95% | 639.6097 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
11 |  | CONSTRUCTION OF 136 BEDDED GIRLS HOSTEL AT ANMMCH, GAYA | 1109 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 | Finishing work is in progress | 95% | 903.1949 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
12 |  | CONSTRUCTION OF 250 SEATER LECTURE THEATRE (2 units) ANMMCH, GAYA | 550.16 | 2015-03-27 |  |  | 2015-12-31 | 2017-12-30 | Finishing work is in progress | 90% | 382.6237 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
|  | Sub Total of ANMMCH, Gaya | 3709.43 |  |  | 2703.6702
SKMCH, Muzaffarpur
13 | Muzaffarpur | CONSTRUCTION OF 75 BEDDED GIRLS HOSTELAT SKMCH, MUZAFFARPUR | 499.12 | 2015-03-27 | Mother India pvt ltd | 972.9731 | 2015-12-15 | 2017-06-14 | Completed | 100% | 375.5403 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
14 |  | CONSTRUCTION OF 250 CAPACITY LECTURE THEATRE (2 units) AT SKMCH, MUZAFFARPUR | 550.16 | 2015-03-27 |  |  | 2015-12-15 | 2017-06-14 | Completed | 100% | 373.2826 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
15 |  | CONSTRUCTION OF MODEL RECORD ROOM AT SKMCH, MUZAFFARPUR | 170.98 | 2015-04-28 |  |  | 2015-12-15 | 2017-06-14 | Completed | 100% | 135.5105 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
|  | Sub Total of SKMCH, Muzaffarpur | 1220.26 |  |  | 972.9731
JLNMCH, Bhagalpur
16 | Bhagalpur | CONSTRUCTION OF CENTRAL LIBRARY AT JLNMCH, BHAGALPUR | 584.55 | 2015-04-28 | Nandlal & Company | 1199.64 | 2015-09-09 | 2017-03-08 | Completed | 100% | 465.44 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
17 |  | CONSTRUCTION OF GIRL'S HOSTEL (75 capacity) AT JLNMCH, BHAGALPUR | 499.12 | 2015-03-27 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% | 400 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
18 |  | CONSTRUCTION OF 250 CAPACITY LECTURE THEATRE (1 units) JLNMCH, BHAGALPUR | 275.08 | 2015-03-27 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% | 334.2 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
19 |  | CONSTRUCTION OF MODEL RECORD ROOM AT JLNMCH, BHAGALPUR | 170.98 | 2015-04-28 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% |  | Sri Anil Kumar | Sri Sanjeev Ranjan
|  | Sub Total of JLNMCH, Bhagalpur | 1529.73 |  |  | 1199.64
DMCH, Darbhanga
20 | Darbhanga | CONSTRUCTION OF MODEL RECORD ROOM AT DMCH, DARBHANGA | 170.98 | 2015-04-28 | Shaurya Premier Infrastructure Pvt ltd | 125.0267 | 2016-08-30 | 2017-08-29 | Completed | 100% | 113.4767 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
|  | Total | 16345.42 |  |  | 13227.5508 |  |  |  |  | 10929.0271

## PHC TO CHC (Health) (2)
PHC TO CHC (30 BEDDED) {Health deptt-38 nos}
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects |  | REMARKS
1 | Construction of PHC to CHC (Health deptt.) |  | 14036.06 | 24433.92 | 9122.2398 | 38 | 12 | 26 |  | 0
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | JAMUI | CHC AT PHC GIDHAURE (JAMUI) | 369.37 | 2014-09-03 | Ashok & co niwas pvt ltd, Jamui | 338.9408 | 2015-08-31 | 2016-08-30 | Completed | 100% | 338.94 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
2 | VAISHALI | CHC AT PHC RAJAPAKAR (VAISHALI) | 369.37 | 2014-09-03 | Rana construction, Kadamkuan (Patna) | 318.9036 | 2015-08-31 | 2016-08-30 | Completed | 100% | 330.65 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
3 | EAST CHAMPARAN | CHC AT PHC SANGRAMPUR (EAST CHAMPARAN) | 369.37 | 2014-09-03 | Nagendra Mishra, Muzaffarpur | 311.077 | 2015-08-31 | 2016-08-30 | Completed | 100% | 300.51 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | Handed over
4 | NAWADA | CHC AT PHC NARDIGANJ (NAWADA) | 369.37 | 2014-09-03 | Arun Deo Kumar, Nalanda | 343.2544 | 2015-09-09 | 2016-09-08 | Completed | 100% | 336.0447 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
5 | JEHANABAD | CHC AT PHC HULASGANJ (JEHANABAD) | 369.37 | 2014-09-03 | M/S Om Sai construction, Jehanabad | 316.8986 | 2015-08-31 | 2016-08-30 | Completed | 100% | 336.0447 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
6 | SUPAUL | CHC AT SARAIGARH BHAPTIYAHI (SUPAUL) | 369.37 | 2014-09-03 | Indra Narayan Singh Contract pvt ltd, Patna | 352.8981 | 2016-04-28 | 2017-04-27 | Completed | 100% | 370.72 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
7 | BHAGALPUR | CHC AT ISMAILPUR (BHAGALPUR) | 369.37 | 2014-09-03 | Pankaj construction | 404.5614 | 2016-06-08 | 2017-06-07 | Completed | 100% | 356.49 | Sri Anil Kumar | Sri Sanjeev Ranjan
8 | SITAMARHI | CHC AT BOKHRA (SITAMARHI) | 369.37 | 2014-09-03 | Sanjay Kumar | 336.2289 | 2016-05-12 | 2017-05-11 | Completed | 100% | 310.84 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
9 | SAMASTIPUR | CHC AT MOHANPUR (SAMASTIPUR) | 369.37 | 2014-09-03 | Vinesh Kumar | 324.5352 | 2016-05-12 | 2017-05-11 | Finishing work is in progrerss | 78% | 230.29 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
10 | SAMASTIPUR | CHC AT KHANPUR (SAMASTIPUR) | 369.37 | 2014-09-03 | M/S Shyam babu Chaudhary | 322.4152 | 2016-05-12 | 2017-05-11 | Roof Shuttering (3rd.F) | 50% | 165.8 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land available on May-2017
11 | VAISHALI | CHC AT PHC BHAGWANPUR (VAISHALI) | 369.37 | 2014-09-03 | Nagendra Mishra, Muzaffarpur | 327.0614 | 2016-08-22 | 2017-08-21 | Completed | 100% | 282.18 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
12 | SIWAN | CHC AT PHC HASANPURA (SIWAN) | 369.37 | 2014-09-03 | Asiana contract pvt ltd, Gopalganj | 310.537 | 2015-08-31 | 2016-08-30 | Finishing work is in progress | 80% | 159.71 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
13 | GOPALGANJ | CHC AT PHC THAWE (GOPALGANJ) | 369.37 | 2014-09-03 | G.M Construction, Siwan | 330.1727 | 2015-08-31 | 2016-08-30 | Completed | 100% | 265.2 | Sri Birendra Purbey | Sri Rajendra Prasad Singh
14 | GAYA | CHC AT PHC MOHRA (GAYA) | 369.37 | 2014-09-03 | Mohan Sharma, Gaya | 315.1639 | 2016-11-14 | 2017-11-13 | Almost Completed | 99% | 315.1639 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
15 | SAMASTIPUR | CHC AT BITHAN (SAMASTIPUR) | 369.37 | 2014-09-03 | M/S Surendra Prasad Singh, Begusarai | 341.2774 | 2017-03-06 | 2018-03-05 | Completed | 100% | 341.27 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
16 | MADHUBANI | CHC AT KALUAHI (MADHUBANI) | 369.37 | 2014-09-03 | Abhay kumar Singh, Sitamarhi | 323.463 | 2017-02-17 | 2018-02-16 | Column work (3rd.F) | 45% | 161.23 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
17 | ARWAL | CHC AT KALER (ARWAL) | 369.37 | 2014-09-03 | B.M Construction, Jehanabad | 330.5846 | 2017-10-16 | 2018-10-15 | Plaster work is in progress | 55% | 264.35 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
18 | SAHARSA | CHC AT SATAR KATAIYA (SAHARSA) | 369.37 | 2014-09-03 | M/S R. K. Construction, Begusarai | 382.8534 | 2016-10-31 | 2017-10-30 | Finishing work is in progress | 90% | 231.65 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
19 | NAWADA | CHC AT KASHICHAK (NAWADA) | 369.37 | 2014-09-03 | Avani Devcon pvt ltd, Patna | 300.6933 | 2017-02-13 | 2018-02-12 | Finishing work is in progress | 85% | 194.92 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
20 | MUZAFFARPUR | CHC AT BANDRA (MUZAFFARPUR) | 369.37 | 2014-09-03 | Nalin Ranjan | 297.0852 | 2016-12-27 | 2017-12-26 | Layout |  | 0 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Land recently available
21 | SIWAN | CHC AT LAKRI NABIGANJ (SIWAN) | 369.37 | 2014-09-03 | Asiana contract pvt ltd, Gopalganj | 316.7612 | 2016-08-11 | 2017-08-10 | Completed | 100% | 235.43 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
22 | JAMUI | CHC AT HARLALNAGAR,ALIGANJ (JAMUI) | 369.37 | 2014-09-03 | A.K Construction | 289.6844 | 2016-06-08 | 2017-06-07 | Finishing work is in progrerss | 75% | 230.36 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Land available on Nov-16
23 | DARBHANGA | CHC AT HANUMAN NAGAR (DARBHANGA) | 369.37 | 2014-09-03 | Sanjay Kumar | 335.7558 | 2017-03-06 | 2018-03-05 | Finishing work is in progrerss | 78% | 236.09 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
24 | KATIHAR | CHC AT SAMAILI (KATIHAR) | 369.37 | 2014-09-03 | M/S C.S Construction | 350.8302 | 2016-09-08 | 2017-09-07 | Finishing work is in progrerss | 80% | 233.74 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
25 | KATIHAR | CHC AT MANSAHI (KATIHAR) | 369.37 | 2014-09-03 | M/S C.S Construction | 339.4581 | 2016-09-08 | 2017-09-07 | Finishing work is in progrerss | 75% | 260.04 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
26 | SHEOHAR | CHC AT DUGRI KATHSARI (SHEOHAR) | 369.37 | 2014-09-03 | Sri Ashok Kumar Singh, Sitamarhi | 337.1786 | 2017-02-17 | 2018-02-16 | Column work (G.F) | 15% | 0 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
27 | GAYA | CHC AT BANKEBAZAR (GAYA) | 369.37 | 2014-09-03 | Kishor Kumar Singh, Aurangabad | 354.3128 | 2016-10-07 | 2017-10-06 | Finishing work is in progress | 85% | 308.4399 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
28 | MADHEPURA | CHC AT PURAINI (MADHEPURA) | 369.37 | 2014-09-03 | Topline Infra Projects pvt ltd, Kolkata | 357.3348 | 2016-12-27 | 2017-12-26 | Completed | 100% | 434.66 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
29 | SITAMARHI | CHC AT SUPPI (SITAMARHI) | 369.37 | 2014-09-03 | Sri Sanjeev Kumar, Patna | 326.8855 | 2018-05-17 | 2019-05-16 | Roof Shuttering (G.F) | 30% | 90 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
30 | JEHANABAD | CHC AT RATNIFARIDPUR (JAHANABAD) | 369.37 | 2014-09-03 | Sri Nripendra Kumar Sinha, Patna | 289.928 | 2017-08-18 | 2018-08-17 | Finishing work is in progress | 70% | 172.19 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
31 | MADHEPURA | CHC AT GWALPARA (MADHEPURA) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 385.2323 | 2017-02-17 | 2018-02-16 | Finishing work is in progrerss | 85% | 244.6 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
32 | SUPAUL | CHC AT PRATAPGANJ (SUPAUL) | 369.37 | 2014-09-03 | Indra Narayan Singh Contract pvt ltd, Patna | 366.6581 | 2017-02-17 | 2018-02-16 | Finishing work is in progrerss | 85% | 270.45 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
33 | BHAGALPUR | CHC AT RANGRACHOWK (BHAGALPUR) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 359.1162 | 2017-01-13 | 2018-01-12 | Finishing work is in progress | 95% | 223.85 | Sri Anil Kumar | Sri Sanjeev Ranjan
34 | MADHUBANI | CHC AT LAKHNAUR (MADHUBANI) | 369.37 | 2014-09-03 | Mother India const. pvt ltd | 360.4508 | 2017-03-20 | 2018-03-19 | Brick work (F.F) | 55% | 145.24 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
35 | SITAMARHI | CHC AT CHORAUT (SITAMARHI) | 369.37 | 2014-09-03 | Mother India const. pvt ltd | 334.7301 | 2017-07-20 | 2018-07-19 | Finishing work is in progress | 82% | 307.7365 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
36 | MADHEPURA | CHC AT BIHARIGANJ (MADHEPURA) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 388.3457 | 2017-02-17 | 2018-02-16 | Finishing work is in progress | 70% | 231.53 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
37 | NAWADA | CHC AT MESKAUR (NAWADA) | 369.37 | 2014-09-03 | Archana Contractor pvt ltd | 307.1294 | 2017-07-14 | 2018-07-13 | Excavation work | 2% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Work sttoped due to hard rock
38 | KATIHAR | CHC AT DANDKHORA (KATIHAR) | 369.37 | 2014-09-03 | Bambam Kumar Singh | 343.7676 | 2017-05-15 | 2018-05-14 | Finishing work is in progress | 80% | 205.88 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
[5 empty] | Total | [5 empty] | 9122.2398

## PHC TO CHC (Single) (2)
PHC TO CHC (30 BEDDED) (Individual)
SL NO | Name of work | A.A. RECEIVED FROM | A.A Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) |  | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of PHC to CHC | Health Dept. | 8386.7567 | 0 |  | 4139.1789 | 15 | 10 | 2 | 3
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT (Rs in lakh) | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT (IN RS. LAKH) | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  |  |  |  | STAGE | %
1 | MADHUBANI | CHC ARARIA SANGRARM,BLOCK-JHANJHARPUR | 476 | 2014-02-28 | M/S Dhramnath construction, Madhubani | 388.34 | 2015-08-11 | 2016-08-10 | Completed | 100% | 339.5805 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
2 | NAWADA | CHC KHANWA, | 476 | 2014-02-28 | Sri Bipin Kumar, Nawada | 345.2 | 2015-08-28 | 2016-08-27 | Completed | 100% | 279.15 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
3 | PATNA | CHC PHULWARISARIFF, | 543.23 | 2015-02-06 | M/S B.Prasad & Company, Patna | 439.04 | 2015-12-15 | 2016-12-14 | Completed | 100% | 493.04 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
4 | Gopalganj | CHC AT PAKRI, BLOCK- SIDHWALIA | 577.1179 | 0 | M/S Cohesive Infrastructure Pvt. Ltd, Patna | 318.86 | 2015-09-09 | 2016-08-09 | Completed | 100% | 294.272 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed Over
5 | DARBHANGA | CHC ALINAGAR, BLOCK-ALINAGAR | 577.1179 | 2015-03-31 | Sanjay Kumar, Darbhanga | 502.5476 | 2016-09-06 | 2017-09-05 | Completed | 100% | 473.83 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
6 | PATNA | CHC AT BAKHTIYARPUR, | 577.1179 | 2015-07-21 | Prasad Associates, Ranchi | 413.1895 | 2016-06-16 | 2017-06-15 | Completed | 100% | 424.11 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
7 | JAHANABAD | CHC SHAKURABAD, BLOCK-RATNIFARIDPUR | 577.1179 | 2014-11-24 | Mukesh Kumar, Gaya | 345.2113 | 2016-06-08 | 2017-06-07 | Completed | 100% | 332.89 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
8 | SUPAUL | CHC BALUA BAJAR, BLOCK-CHHATAPUR, | 577.1179 | 2014-11-24 | INCPL, Patna | 417.2285 | 2016-07-06 | 2017-07-05 | Completed | 100% | 407.39 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
9 | GAYA | CHC MAHKAR, BLOCK-KHIZIRSARAI | 577.1179 | 2014-11-24 | Kaushlendra Kumar, Jehanabad | 368.0233 | 2016-07-20 | 2017-07-19 | Completed | 100% | 407.9264 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
10 | W. CHAMPARAN | CHC BALMIKINAGAR BAGHA-2, DIST-WEST CHAMPARAN | 543.23 | 2014-11-24 | Maa Vindhyavasini construction, W. Champaran | 389.1026 |  |  | Not started |  | 0 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | (Agreement done on 08/07/2016) Land not available
11 | SARAN | CHC ISUAPUR, DIST-SARAN | 577.1179 | 2015-08-05 | Yashaswi Infrastructure pvt ltd | 491.5484 |  |  | Brick work is in progress | 45% | 86 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Land made available on 20 July 2017
12 | NALANDA | CHC ISLAMPUR, Dist-NALANDA | 577.1179 | 2015-08-05 | M/S B.Prasad & Company, Patna | 439.2971 | 2016-09-06 | 2017-09-05 | Completed | 100% | 373.12 |  | Sri Sanjeev Ranjan
13 | MUZAFFARPUR | CHC MUSHARI, DIST- MUZAFFARPUR | 577.1179 |  | Mohan Prasad Developers & construction pvt ltd | 480.1992 | 2017-03-06 | 2018-03-05 | Finishing work is going on | 70% | 227.87 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
14 | ROHTAS | CHC KOCHAS, BLOCK-KOCHAS | 577.1179 | 2015-06-16 |  | 0 |  |  | Not started |  |  | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Tender to be done
15 | ROHTAS | CHC KARGAHAR, BLOCK-KARGAHAR | 577.1179 | 2015-06-16 | M/s Pankaj Construction, Rohtas | 462.5784 |  |  | Not started |  |  | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | LOA issued
| Total |  | 8386.7567 |  |  | 5800.366 |  |  |  |  | 4139.1789

## PHC TO CHC (minority) (2)
PHC TO CHC (30 BEDDED) (Under MSDP)
SL NO | Name of work |  | A.A. Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects |  |  | REMARKS
1 | Construction of PHC to CHC (Minority) |  | 11776.25 (471.05 per unit) | 0 | 2829.7105 | 25 | 6 | 7 |  | 12
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS in lakh) |  |  | STAGE | % | (RS in lakh)
1 | KISHANGANJ | CHC AT DIGHALBANK, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 385.564 | 2016-04-28 | 2017-04-27 | Completed | 100% | 273.54 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
2 | KISHANGANJ | CHC AT THAKURGANJ, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 386.2479 | 2016-04-28 | 2017-04-27 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Letter sent to D.M for land
3 | KISHANGANJ | CHC AT BAHADURGANJ, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 381.5506 | 2016-04-28 | 2017-04-27 | Completed | 100% | 266.56 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
4 | KISHANGANJ | CHC AT KOCHADHAMAN, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 384.9058 | 2016-04-28 | 2017-04-27 | Completed | 100% | 193.43 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
5 | ARARIYA | CHC AT PALASI, ARARIYA | 471.05 | 2015-04-13 | Topline Infra | 389.7501 | 2016-04-28 | 2017-04-27 | Completed | 100% | 384 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
6 | KATIHAR | CHC AT AZAMNAGAR, KATIHAR | 471.05 | 2015-04-13 | Pankaj Kumar Singh | 387.1691 | 2016-04-29 | 2017-04-28 | Completed | 100% | 312.0882 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
7 | BHAGALPUR | CHC AT JAGDISHPUR, BHAGALPUR | 471.05 | 2015-04-13 | Balkrishna Bhalotia construction pvt ltd, jamui | 368.774 | 2016-04-28 | 2017-04-27 | Completed | 100% | 360 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
8 | KATIHAR | CHC AT BALRAMPUR, KATIHAR | 471.05 | 2015-04-13 | Birendra Kumar Singh, Katihar | 367.8626 | 2016-05-31 | 2017-05-30 | Column work (G.F) | 18% | 81.11 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
9 | KATIHAR | CHC AT AMADABAD, KATIHAR | 471.05 | 2015-04-13 | Birendra Kumar Singh, Katihar | 362.0746 | 2016-05-27 | 2017-05-26 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | (Land not available) Letter sent to D.M for land
10 | ARARIYA | CHC AT RANIGANJ, ARARIYA | 471.05 | 2015-04-13 | INSCPL | 369.6559 | 2016-07-06 | 2017-07-05 | Finishing work | 75% | 174.41 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
11 | MADHUBANI | CHC AT MADHUBANI SADAR, MADHUBANI | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.591 | 2016-07-20 | 2017-07-19 | Not Started |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Work will be started after demolished the old building
12 | KATIHAR | CHC AT KADWA, KATIHAR | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.9165 | 2016-06-08 | 2017-06-07 | Finishing work is in progress | 92% | 294.51 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
13 | KATIHAR | CHC AT BARSOI, KATIHAR | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.6211 | 2016-06-08 | 2017-06-07 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available, Letter send for land
14 | KATIHAR | CHC AT BARARI, KATIHAR | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.9071 | 2016-06-08 | 2017-06-07 | Finishing work | 92% | 295.782 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
15 | ARARIYA | CHC AT SIKTI, ARARIYA | 471.05 | 2015-04-13 | Basant Banijya Limited, Gaya | 379.1134 | 2018-02-27 | 2019-02-26 | Roof shuttering (F.F) | 25% | 61.134 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
16 | ARARIYA | CHC AT TERHAGACH, ARARIYA | 471.05 | 2015-04-13 | M/S C.S construction | 378.2944 | 2016-09-06 | 2017-09-05 | Column work (G.F) | 20% | 63.7662 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | work started after demolished the old building
17 | DARBHANGA | CHC AT KIRATPUR, DARBHANGA | 471.05 | 2015-04-13 | Kuwar construction | 352.2968 | 2017-07-15 | 2018-07-14 | Not Started | - | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available, Letter send to D.M
18 | KISHANGANJ | CHC AT POTHIA, KISHANGANJ | 471.05 | 2015-04-13 | Anil Kumar | 369.4717 | 2017-06-02 | 2018-06-01 | Steel Binding (Terrace Floor) | 30% | 69.38 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land made available after Tree cutting on 02 August 2017
19 | KATIHAR | CHC AT HASANGANJ, KATIHAR | 471.05 | 2015-04-13 | Rita Devi | 371.2069 | 2017-07-25 | 2018-07-24 | Not Started | - | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Letter sent for land
20 | EAST CHAMPARAN | CHC AT BANJARIA, EAST CHAMPARAN | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | In Tender
21 | VAISHALI | CHC AT CHEHRA KALAN, VAISHALI | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | In Tender
22 | ARARIYA | CHC AT JOKIHAT, ARARIYA | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | In Tender
23 | KATIHAR | CHC AT KATIHAR SADAR, KATIHAR | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available (Letter Send to P.S MWD, Bihar vide Letter no-BMSIC/80015/05-2016/959, Dated-21/06/2016
24 | ARARIYA | CHC AT FORBESGANJ, ARARIYA | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Project dropped
25 | KATIHAR | CHC AT MANIHARI, KATIHAR | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Project dropped
[8 empty] | Total |  |  | 2829.7105

## APHC (2)
ADDITIONAL PRIMARY HEALTH CENTRE (A.P.H.C)
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT (in rs lakh) | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  |  |  |  | STAGE | % | AMOUNT (Rs in lakh)
1 | PATNA | CONSTRUCTION OF APHC IN SAMASTICHAK, PATNA | 75.99 | 2011-03-12 | Pintu Construction, Masaurhi | 68.748 | 2013-04-20 | 2014-01-19 | completed | 100% | 81.4691 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | KAIMUR | CONSTRUCTION OF APHC IN NATAIYA, KAIMUR | 75.99 | 2012-09-18 | Smt Rita Devi | 68.748 | 2013-07-03 | 2014-04-02 | completed | 100% | 88.11 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
3 | SAMASTIPUR | APHC NARHAN, DIST-SAMASTIPUR (FROM SHS) | 75.99 | 2011-03-12 | - | - | - | - | - | - | - | - | - | Tender not Invited
4 | SAMASTIPUR | CONSTRUCTION OF APHC IN BANDHAR, SAMASTIPUR | 75.99 | 2012-08-28 | Mr. A Khan | 68.748 | 2013-08-16 | 2014-05-15 | completed | 100% | 90.68 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
5 | GAYA | CONSTRUCTION OF APHC IN MAIN GRAM, GAYA | 75.99 | 2012-10-03 | M/S Rita Devi | 66.4527 | 2013-09-12 | 2014-06-11 | completed | 100% | 79.1999 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
6 | SIWAN | CONSTRUCTION OF APHC NARENDARPUR, SIWAN | 75.99 |  | Jiradei Narendrapur Engineering & Construction Company | 73.6227 | 2013-08-14 | 2014-05-13 | completed | 100% | 80.5457 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
7 | VAISHALI | APHC BHAGWANPURRATI, DIST-VAISHALI (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Synergy thrillingston, chandigarh | - | - | - | completed | 100% | 59 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | CONSTRUCTRED AS MODEL UNDER 100 APHC SANCTIONED BY HEALTH DEPT.
8 | VAISHALI | APHC ROOPNARAYANPUR, BLOCK-JANDAHA, DIST-VAISHALI (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Revirie Ventures Pvt. Ltd, Chhatishgarh | - | - | - | completed | 100% | 69.05 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
9 | PATNA | APHC DATMAI, BLOCK-MASAURHI, DIST-PATNA (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Sai Baba Builders & Consultants Pvt. Ltd | - | - | - | completed | 100% | 35.65 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
10 | GAYA | CONSTRUCTION OF APHC AT MAHKAR, BLOCK-KHIZIRISARAI (GAYA) BY PRE-FAB MATERIAL | 112.49 | 2014-06-23 | Acme Cleantech Solutions Ltd,Gurgaon (Haryana) | 84.735 | 2014-08-26 | 2014-11-25 | completed | 100% | 69.55 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
11 | NALANDA | CONSTRUCTION OF APHC AT KACHHARIYA, BLOCK-THARTHARI (NALANDA) BY PRE-FAB MATERIAL | 112.49 | 2014-07-22 | Beardsell ltd. | 93.7837 | 2014-12-29 | 2015-04-28 |  | - | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | (work rescined)
12 | BEGUSARAI | CONSTRUCTION OF APHC AT SONVARSA,SAMHO (BEGUSARAI) | 90.008 | 2014-01-17 | Ramniwas Kumar, Begusarai | 76.4628 | 2015-08-19 | 2016-05-18 | Completed | 100% | 76.46 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
13 | GOPALGANJ | CONSTRUCTION OF APHC AT SIDHWALIA,GOPALGANJ | 120.66 |  | Bajrangi Singh,Chhapra | 104.9228 | 2015-08-14 | 2016-05-13 | Completed | 100% | 93.8511 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
14 | GOPALGANJ | CONSTRUCTION OF APHC AT BALRA,BARAULI (GOPALGANJ) | 87.05 | 2014-11-10 | Baranwala Contact Pvt. Ltd, Gopalganj | 78.4366 | 2015-08-19 | 2016-02-18 | Completed | 100% | 78.44 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
15 | GOPALGANJ | CONSTRUCTION OF APHC AT REVTITH, BAIKUNTHPUR (GOPALGANJ) | 87.05 | 2014-11-10 | Baranwala Contact Pvt. Ltd, Gopalganj | 77.753 | 2015-08-19 | 2016-02-18 | Completed | 100% | 77.55 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
16 | JAHANABAD | APHC AT MURAHARA, BLOCK-RATNIFARIDPUR, DIST-JAHANABAD | 122.347 | 2015-02-04 | Smt Rita Devi, Sasaram | 181.6154 | 2015-09-01 | 2015-06-30 | completed | 100% | 64.0027 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
17 | JAHANABAD | APHC AT AVGILLA, BLOCK-RATNIFARIDPUR, DIST-JAHANABAD | 122.35 | 2015-02-04 |  |  |  |  | completed | 100% | 86.3631 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
18 | ROHTAS | CONSTRUCTION OF APHC AT BARHARI BLOCK-KARGAHAR,DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram | 284.1295 | 2015-08-31 | 2016-05-30 | Completed | 100% | 312 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
19 | ROHTAS | CONSTRUCTION OF APHC AT KOWATH ,BLOCK-DAWATH, DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram |  | 2015-08-31 | 2016-05-30 | completed | 100% |  | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
20 | ROHTAS | CONSTRUCTION OF APHC AT KHAIRHI, BLOCK-DAWATH, DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram |  | 2015-08-31 | 2016-05-30 | completed | 100% |  | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
21 | VAISHALI | CONSTRUCTION OF APHC AT SONHO, BLOCK-GOROUL (VAISHALI) | 102.05 |  | Randhir Kumar | 97.3991 | 2015-09-09 | 2016-06-08 | completed | 100% | 97.46 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
22 | NALANDA | CONSTRUCTION OF APHC AT AMBA (NALANDA) | 122.34 |  | Lallu Kumar | 97.4972 | 2016-01-04 | 2016-10-03 | completed | 100% | 96.8593 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
23 | BHAGALPUR | CONSTRUCTION OF APHC AT POTHIA SANHAULA (BHAGALPUR) | 81.309 | 2014-01-27 | Lalan Kumar | 71.13 | 2017-08-18 | 2018-05-17 | Tie Beam | 12% | 0 | Sri Anil Kumar | Sri Sanjeev Ranjan | Land available on=06/06/2018
24 | KAIMUR | APHC AT BITHWAR DIST-KAIMUR | 122.34 |  | Kamlesh Kumar Singh | 94.7102 | 2016-05-12 | 2017-05-11 | Completed | 100% | 108 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
25 | PATNA | APHC AT GOPALPUR (MANER) DIST-PATNA | 122.34 |  | Brajesh Kumar | 98.5084 | 2016-03-03 | 2016-12-02 |  |  | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Land not available
26 | JAHANABAD | APHC AT KIYUR, BLOCK-HULASHGANJ, DIST-JEHANABAD | 122.34 | 2015-07-13 | Kaushlendra Kumar | 91.5403 | 2016-10-28 | 2017-07-27 | completed | 100% | 91.54 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
27 | BEGUSARAI | SMRITISHESH PARMESHWARI DEVI APHC AT KESAWE, BARAUNI, DIST-BEGUSARAI | 122.34 |  | Agni Kumar Singh | 109.48 | 2017-05-05 | 2018-02-04 | completed | 100% | 109.48 | Sri Anil Kumar | Sri Rajendra Prasad Singh
28 | BEGUSARAI | APHC AT BAHALPUR (NAYAGAON) MATIHANI, DIST-BEGUSARAI | 90.008 | 2014-01-22 | Ramniwas kumar | 74.9338 | 2017-03-24 | 2017-12-23 | completed | 100% | 73.2588 | Sri Rajendra Prasad Singh | Sri Rajendra Prasad Singh
29 | PATNA | APHC SAKSOHRA AT BELCHI, DIST-PATNA | 114.7 |  | M/s Devendra Prasad Singh | 120.3879 | 2017-05-05 | 2018-03-04 | completed | 100% | 71.41 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
30 | MUNGER | APHC AT BANGALWA, DIST-MUNGER | 122.49 | 2014-02-28 | P PRAKASH CONT. | 104.6441 |  |  |  |  | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | LOA issued on 13/02/2018
31 | MUNGER | APHC AT GHATWARI, DIST-MUNGER | 122.49 | 2014-02-28 | P PRAKASH CONT. | 99.1267 | 2017-02-22 | 2017-11-21 |  |  | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Land not available
32 | VAISHALI | APHC AT MADARNA DIST-VAISHALI | 102.05 | 2014-09-02 | Rohit Raj Construction, Patna | 96.6814 | 2016-08-11 | 2017-05-10 | completed | 100% | 99.69 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
33 | MADHUBANI | APHC AT BHAIRAVSTHAN BLOCK-JHANJHARPUR, DIST-MADHUBANI | 114.07 | 2015-02-09 | M/S Delta Enterprises | 102.7246 | 2017-02-22 | 2017-11-21 | Almost Completed | 96% | 86.93 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
34 | BEGUSARAI | APHC AT SIHMA, BLOCK-MATIHANI DIST-BEGUSARAI | 122.34 |  | M/S Surendra Prasad Singh, Begusarai | 103.5026 | 2017-02-17 | 2017-11-16 | completed | 100% | 103.5 | Sri Anil Kumar | Sri Rajendra Prasad Singh
35 | SAMASTIPUR | APHC AT DEVDHA, (HASANPUR) DIST-SAMASTIPUR | 122.34 | 2015-02-03 | [7 empty] | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Retender invited by NIT-22/2017
36 | MADHUBANI | APHC AT BASAITH, BLOCK-BENIPATTI (MADHUBANI) | 122.34 | 2016-02-09 | Tufail Ahmed Khan const. pvt ltd | 98.1208 | 2017-05-05 | 2018-02-04 | completed | 100% | 106.8118 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
37 | MADHUBANI | APHC AT NAWANI, BLOCK-JHANJHARPUR, DIST-MADHUBANI | 126.97 | 2016-08-29 | Regal Infratrading Pvt. Ltd., Patna | 126.1928 | 2017-02-08 | 2017-11-07 | Roof casted (F.F) | 50% | 31.448 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
38 | MADHUBANI | APHC AT BHAUR, BLOCK-PANDAUL, DIST-MADHUBANI | 122.34 | 2016-08-29 | MDS Infranirman Pvt ltd, Patna | 105.3907 | 2017-07-15 | 2018-04-14 | Roof casted(G.F) | 35% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
39 | ARWAL | APHC AT LARI, BLOCK-KURTHA, DIST-ARWAL | 122.34 | 2017-01-18 | Praveen Kumar, Jehanabad | 124.5004 | 2017-09-21 | 2018-06-20 | Finishing work | 60% | 40.49 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
40 | MADHUBANI | APHC AT MOHAN BARIYAM,NARPAT NAGAR , BLOCK-PANDAUL, DIST-MADHUBANI | 0 |  | Shaurya Premiere Infrastructure pvt ltd, Patna | 106.95 | 2017-10-06 | 2017-07-05 | Brick work completed | 45% | 27.85 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
41 | WEST CHAMPARAN | APHC AT PATILAR, DIST-WEST CHAMPARAN | 0 | 2016-05-05 | Anil Kumar Mishra | 105.1289 | 2018-02-02 | 2018-09-01 | Plaster work | 40% | 56.77 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
42 | SIWAN | APHC AT NANDA MUNDA, BLOCK-SISWAN, DIST-SIWAN | 126.97 | 2016-09-20 | Pratap Construction, New Delhi | 102.58 | [5 empty] | Sri Birendra Purbey | Sri Rajendra Prasad Singh | LOA issued
43 | SIWAN | APHC AT JAMO BLOCK-GORIYAKOTHI, DIST-SIWAN | 122.34 | 2017-09-05 | Savitri Technocrate Pvt Ltd, Gopalganj | 102.5817 |  |  | Foundation work is going on | 2% |  | Sri Birendra Purbey | Sri Rajendra Prasad Singh | LOA issued on 13/02/2018
44 | NALANDA | CONSTRUCTION OF APHC AT HUSAINPUR, BLOCK-RAHUI (NALANDA) | 122.34 |  | R.K Infraservices | 98.775 | 2018-05-17 | 2019-02-16 | Work started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
45 | DARBHANGA | CONSTRUCTION OF APHC JAMALPUR, BLOCK-KIRATPUR | 127.2842 | 2016-12-09 | Rampukar Yadav | 104.0309 | [7 empty] | LOA to be issued
46 | JAHANABAD | APHC AT ANANTPUR, BLOCK-MODANGANJ, DIST-JEHANABAD | 122.34 | 2016-03-21 | Rohit Raj Construction, Patna | 98.9155 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 30/05/2018
47 | JAHANABAD | APHC AT SUGAON, BLOCK-MAKHDUMPUR, DIST-JEHANABAD |  |  | Praveen Kumar, Jehanabad | 98.9155 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 09/05/2018
48 | JAHANABAD | APHC AT BAJITPUR, BLOCK-GHOSHI, DIST-JEHANABAD | 122.34 |  | Praveen Kumar, Jehanabad | 98.9155 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 30/05/2018
49 | SAMASTIPUR | CONSTRUCTION OF APHC AT DARWA, BLOCK-MORWA,SAMASTIPUR |  |  | M/S Gautam Construction | 137.9109 | [7 empty] | LOA iisued on-06/09/2018
50 | PATNA | APHC AT SIGORI, BLOCK- PALIGANJ, DIST-PATNA |  |  | Praveen Kumar, Jehanabad | 102.0941 | [5 empty] | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | LOA issued on 30/05/2018
|  | SUBTOTAL | 4402.987 | [7 empty] | 1796.345

## APHC (MSDP)1 (2)
CONSTRUCTION OF ADDITIONAL PRIMARY HEALTH CENTRE (MSDP)
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS in Lakh) |  |  | STAGE | % | AMOUNT (RS in Lakh)
1 | Darbhanga | Brahmpur (Darbhanga) | 124.31 |  | C.G.G construction | 303.0228 | 2016-02-17 | 2017-02-16 | Completed | 100% | 52.8841 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
2 | Darbhanga | Kamtaul (Darbhanga) | 124.31 |  |  |  | 2016-02-17 | 2017-02-16 | Completed | 100% | 47.6674 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
3 | Darbhanga | Sarwara (Darbhanga) | 124.31 |  |  |  | 2016-02-17 | 2017-02-16 | Finishing work is going on | 70% | 21.7282 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
4 | Katihar | Morsanda (katihar) | 124.31 |  | B.K Singh | 299.5476 | 2016-06-08 | 2017-06-07 | Roof casted | 40% | 38 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
5 | Katihar | Bharwara (katihar) | 124.31 |  |  |  | 2016-06-08 | 2017-06-07 | Finishing work is in progress | 80% | 73 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
6 | Katihar | Surjapur (katihar) | 124.31 |  |  |  | 2016-06-08 | 2017-06-07 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
7 | West Champaran | Gokhula (West Champaran) | 124.31 |  | Sharda chandel contract pvt ltd. | 194.8329 | 2016-04-11 | 2017-04-10 | Finishing work is in progress | 92% | 105.3268 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
8 | West champaran | Dumaria (West Champaran) | 124.31 |  |  |  | 2016-04-11 | 2017-04-10 | Finishing work is in progress | 92% |  | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
9 | Kishanganj | Kalpeer, Tedhagach (Kishanganj) | 124.31 |  | M/S Shankar Construction, Begusarai | 101.5409 | 2016-12-27 | 2017-09-26 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
10 | Kishanganj | Bual Dah, Block- Kochadhaman (Kishanganj) | 124.31 |  | M/S Shankara Construction, Begusarai | 206.3582 | 2016-12-27 | 2017-09-26 | Finishing work is in progress | 95% | 89.4377 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
11 | Kishanganj | Maudha, Block- Kochadhaman (Kishanganj) | 124.31 |  |  |  | 2016-12-27 | 2017-09-26 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
12 | Supaul | Deenbandhu, Basantpur (Supaul) | 124.31 |  | Mahendra Kumar Mishra | 96.677 |  |  |  |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | LOA issued on 12/05/2016
13 | Kishanganj | chichubadi, Kasba-Kaliyaganj , Block- Pothia (Kishanganj) | 124.31 |  | Sri Narayan Mandal, Katihar | 205.0883 | 2017-01-13 | 2017-10-12 | Plaster work is in progress | 60% | 57.34 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
14 | Kishanganj | Tipijhari Magurjohn , Block- Pothia (Kishanganj) | 124.31 |  |  |  | 2017-01-13 | 2017-10-12 | - | - | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
15 | Purnea | Abdullah Nagar (Purnea) | 124.31 |  | Rana pratap Singh | 97.7068 | 2017-10-09 | 2018-07-08 | Finishing work is in progress | 90% | 66.57 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
16 | Madhubani | Loha,Kaluahi (Madhubani) | 124.31 |  | M/S Dayaram Singh | 99.6446 | - | - | Not Started |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | LOA issued on 12/05/2016 (Land not available)
17 | East Champaran | Karsahiya, Barharwa Lakhansen, (Dhaka E. Champaran) | 124.31 |  | Vikash Kumar Gupta | 209.1866 | 2017-07-20 | 2018-04-19 | Karsahiya-Foundation work . Barharwa Lakhansen- roof level | 20% | 22.2955 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
18 | Kishanganj | Powakhali Thakurganj (Kishanganj) | 124.31 |  | Sudesh Kumar Singh &co. construction pvt ltd, jamui | 97.2558 | 2017-02-17 | 2017-11-16 | Finishing is in progress | 85% | 57.82 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
19 | Sitamarhi | Bajpatti Got Abidpur (Sitamarhi) | 124.31 | [7 empty] | 0 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Retender to be invited
20 | Darbhanga | Harihath, Block- Alinagar (Darbhanga) | 124.31 |  | Girdhari Lal Poddar | 312.8027 | 2017-03-06 | 2018-03-05 | Not Started |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
21 | Darbhanga | Garaul, Block- Alinagar (Darbhanga) | 124.31 |  | Girdhari Lal Poddar |  | 2017-03-06 | 2018-03-05 | Not Started |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
22 | Darbhanga | Narman, Block- Alinagar (Darbhanga) | 124.31 |  | Girdhari Lal Poddar |  | 2017-03-06 | 2018-03-05 | Completed | 100% | 36.23 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
23 | Kishanganj | Dhangada, Block-Dighalbank (Kishanganj) | 124.31 |  | Anil Kumar | 207.3475 | 2017-01-13 | 2017-10-12 | Finishing work work is in progress. | 90% | 205.88 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
24 | Kishanganj | Baruamani Garnchavdaga, Block-Dighalbank (Kishanganj) | 124.31 |  | Anil Kumar |  |  |  | Finishing work work is in progress. | 90% | 63.65 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
25 | Kishanganj | Kadogaon, Block-Thakurganj (Kishanganj) | 124.31 |  | Sudesh Kumar Singh &co. construction pvt ltd, jamui | 97.25 | 2017-02-17 | 2017-11-16 |  |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
26 | Kishanganj | Budhnayi, Block-Pothia (Kishanganj) | 124.31 |  | Sudesh Kumar Singh &co. construction pvt ltd, jamui | 193.9464 | 2017-01-13 | 2017-10-12 | Completed | 100% | 99.58 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
27 | Kishanganj | Fala Tarni Block-Pothia (Kishanganj) | 124.31 |  |  |  | 2017-01-13 | 2017-10-12 | Completed | 100% | 100.38 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
28 | Banka | Pardhadi, Dhuria (Banka) | 124.31 |  | Lalan Kumar | 89.5481 |  |  |  |  | 0 | Sri Anil Kumar | Sri Sanjeev Ranjan | T.S in process
29 | Darbhanga | Jamalpur, Block-Kiratpur (Darbhanga) | 124.31 | 2017-02-06 | Ram Pukar Yadav, Darbhanga | 103.2393 | [5 empty] | Sri Sunil Kumar | Sri Rajendra Prasad Singh | LOA issued on 08/12/2017
30 | Darbhanga | Manighachhi, Block-Manigachhi (Darbhanga) | 124.31 | 2017-02-06 | Mother India Construction Pvt. Ltd., |  |  |  | Roof shuttering (G.F) | 25% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh | LOA issued on 08/12/2017
31 | Darbhanga | Nehra, Block-Manigachhi (Darbhanga) | 124.31 | 2017-02-06 | Mother India Construction Pvt. Ltd., | 103.8815 | [5 empty] | Sri Sunil Kumar | Sri Rajendra Prasad Singh | LOA issued on 08/12/2017
32 | Sitamarhi | Benol, Block-Bokhra (Sitamarhi) | 124.31 | 2017-02-06 | M/s Bharti Const., Sitamarhi | 103.8815 | [5 empty] | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | T.S in Process
33 | Purnea | Mahendrapur, Block-Purnea (Purnea) | 124.31 | 2017-02-06 | Anil Kumar Singh, Katihar | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 08/12/2017
34 | Purnea | Ranipatra, Block-Purnea Purva (Purnea) | 124.31 | 2017-02-06 | Shiv Shankar Singh, Katihar | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 08/12/2017 (T.S in process)
35 | Purnea | Harda, Block-Purnea Purva (Purnea) | 124.31 | 2017-02-06 | Prakash Kumar Sah, katihar | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 08/12/2017
36 | Purnea | Sabdalpur, Block-Kasba (Purnea) | 124.31 | 2017-02-06 | Rohit Raj Construction, Vaishali | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 08/12/2017 (T.S in process)
37 | Purnea | Echalo, Block-Dagarua (Purnea) | 124.31 | 2017-02-06 | Rohit Raj Construction, Vaishali | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 08/12/2017 (T.S in process)
38 | Purnea | Muchhatta, Block-Amaur (Purnea) | 124.31 | 2017-02-06 | Prashant Const., Purnea | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 08/12/2017 (T.S in process)
39 | Purnea | Sirshi, Block-Baisa (Purnea) | 124.31 | 2017-02-06 | Prashant Const., Purnea | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 08/12/2017 (T.S in process)
40 | Purnea | Katorhat, Block-Baisa (Purnea) | 124.31 | 2017-02-06 | Parshant Const., Purnea | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 08/12/2017
41 | Purnea | Kajha, Block-K.Nagar (Purnea) | 124.31 | 2017-02-06 | [7 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | In Tender 07/2017
42 | Purnea | Banbhag, Block-K.Nagar (Purnea) | 124.31 | 2017-02-06 | [7 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | In Tender 07/2017
[8 empty] | Total |  |  | 1137.7897

## HSC MINORITY (2)
HEALTH SUB CENTRE (Under MSDP)
SL NO | NAME OF DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS in lakh) |  |  | STAGE | % | (RS in lakh)
1 | WEST CHAMPARAN | HSC AT MANGALPUR BLOCK-SIKTA (WEST CHAMPARAN) |  |  | Brajesh Kumar, Bettiah | 116.155 | 2015-12-16 | 2016-08-15 | Completed | 100% | 63.89 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
2 | WEST CHAMPARAN | HSC AT BHAURA,BLOCK-SIKTA (WEST CHAMPARAN) |  |  | Brajesh Kumar, Bettiah |  | 2015-12-16 | 2016-08-15 | Completed | 100% |  | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
3 | WEST CHAMPARAN | HSC AT TILOJPUR,BLOCK-MAINATAND (WEST CHAMPARAN) |  |  | Brajesh Kumar, Bettiah |  | 2015-12-16 | 2016-08-15 | Completed | 100% |  | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
4 | WEST CHAMPARAN | HSC AT JIGNA,BLOCK-MAINATAND (WEST CHAMPARAN) |  |  | Brajesh Kumar, Bettiah |  | 2015-12-16 | 2016-08-15 | Completed | 100% |  | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
5 | SIWAN | HSC AT KHODAIBARI,BLOCK-HUSAINGANJ (SIWAN) |  |  | Brajesh Kumar, Bettiah |  | 2015-12-16 | 2016-08-15 | Not Started |  |  | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Land not available
6 | DARBHANGA | HSC AT BASDIH, BLOCK-HAYAGHAT (DARBHANGA) |  |  | Sri vivek Kumar Jha, Darbhanga | 97.7403 | 2017-02-15 | 2017-10-14 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
7 | DARBHANGA | HSC AT SIRNIA, BLOCK-HAYAGHAT (DARBHANGA) |  |  | Sri vivek Kumar Jha, Darbhanga |  | 2017-02-15 | 2017-10-14 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
8 | DARBHANGA | HSC AT RATANPURA, BLOCK-HAYAGHAT (DARBHANGA) |  |  | Sri vivek Kumar Jha, Darbhanga |  | 2017-02-15 | 2017-10-14 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
9 | DARBHANGA | HSC AT HORALPATTI, BLOCK-HAYAGHAT (DARBHANGA) |  |  | Sri vivek Kumar Jha, Darbhanga |  | 2017-02-15 | 2017-10-14 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
10 | DARBHANGA | HSC AT DRAHWAJPUR, BLOCK-DARBHANGA (DARBHANGA) |  |  | Dinesh Pd. Singh | 104.9198 | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
11 | DARBHANGA | HSC AT KHARUA, BLOCK-DARBHANGA (DARBHANGA) |  |  | Dinesh Pd. Singh |  | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
12 | DARBHANGA | HSC AT BHALPATTI, BLOCK-DARBHANGA (DARBHANGA) |  |  | Dinesh Pd. Singh |  | 2017-03-20 | 2017-11-19 | Completed | 100% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
13 | DARBHANGA | HSC AT BADHAUL-DEVRA BANDHAUDI, BLOCK-JALE (DARBHANGA) |  |  | Dinesh Pd. Singh |  | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
14 | DARBHANGA | HSC AT GARDI, BLOCK-JALE (DARBHANGA) |  |  | Dinesh Pd. Singh |  | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
15 | GOPALGANJ | HSC AT BARWA, BLOCK-ADAPUR (GOPALGANJ) |  |  | Sri Shailendra Shekhar Mishra, Gopalganj | 108.762 |  |  | Not Started |  |  | Sri Birendra Purbey | Sri Rajendra Prasad Singh | LOA issued on-04/10/2016 (Agreement Done) Chotka Sakhen- Land not available
16 | GOPALGANJ | HSC AT BRAHBHAIN, BLOCK-ACHKAGAON (GOPALGANJ) |  |  | Sri Shailendra Shekhar Mishra, Gopalganj |  |  |  | Not Started |  |  | Sri Birendra Purbey | Sri Rajendra Prasad Singh
17 | GOPALGANJ | HSC AT BARARI HARKESH, BLOCK-ACHKAGAON (GOPALGANJ) |  |  | Sri Shailendra Shekhar Mishra, Gopalganj |  |  |  | Finishing work is in progress | 75% |  | Sri Birendra Purbey | Sri Rajendra Prasad Singh
18 | GOPALGANJ | HSC AT CHHOTKA SAKHEN, BLOCK-ACHKAGAON (GOPALGANJ) |  |  | Sri Shailendra Shekhar Mishra, Gopalganj |  |  |  | Not Started |  |  | Sri Birendra Purbey | Sri Rajendra Prasad Singh
19 | KISHANGANJ | HSC AT PIPRITHAN PURVI, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram | 133.1481 | 2017-05-05 | 2018-01-04 | Completed | 100% | 126.8 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
20 | KISHANGANJ | HSC AT KHARIBASTI, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Not Started | 0% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Due to unavailability of Land
21 | KISHANGANJ | HSC AT KATHARO, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
22 | KISHANGANJ | HSC AT KHANABARI, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
23 | KISHANGANJ | HSC AT PACKPARA, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
24 | KISHANGANJ | HSC AT JIRANGACH OLDMAICHI, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
25 | KATIHAR | HSC AT PALSA, BLOCK-BALRAMPUR (KATIHAR) |  |  | BHISHMA PRATAP SINGH, SIWAN | 89.989 | 2017-03-06 | 2017-11-05 | Plaster Progress | 70% | 32.1655 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
26 | KATIHAR | HSC AT MALIKPUR, BLOCK-BALRAMPUR (KATIHAR) |  |  | BHISHMA PRATAP SINGH, SIWAN |  | 2017-03-06 | 2017-11-05 | Plaster Progress | 70% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
27 | KATIHAR | HSC AT SINHAGAON BLOCK-BALRAMPUR (KATIHAR) |  |  | BHISHMA PRATAP SINGH, SIWAN |  | 2017-03-06 | 2017-11-05 | Plaster Progress | 70% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
28 | KATIHAR | HSC AT MADHOPUR, BLOCK-BALRAMPUR (KATIHAR) |  |  | BHISHMA PRATAP SINGH, SIWAN |  | 2017-03-06 | 2017-11-05 | - |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
29 | KATIHAR | HSC AT SHARIFNAGAR, BLOCK-BALRAMPUR, KATIHAR |  |  | SARWAR ALAM, KISHANGANJ | 92.8982 | 2017-03-20 | 2017-11-19 | Finishing work | 80% | 19.45 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
30 | KATIHAR | HSC AT BALRAMPUR,BLOCK-BALRAMPUR, KATIHAR |  |  | SARWAR ALAM, KISHANGANJ |  | 2017-03-20 | 2017-11-19 | Finishing work | 80% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
31 | KATIHAR | HSC AT BALUGANJ BLOCK-BALRAMPUR, KATIHAR |  |  | SARWAR ALAM, KISHANGANJ |  | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
32 | KATIHAR | HSC AT KAMRA, BLOCK-BALRAMPUR, KATIHAR |  |  | SARWAR ALAM, KISHANGANJ |  | 2017-03-20 | 2017-11-19 | Roof casted | 57% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
33 | KATIHAR | HSC AT RATNI, BLOCK-HASANGANJ, KATIHAR |  |  | BALMIKI PRASAD SINGH, KATIHAR | 89.9984 | 2017-03-06 | 2017-11-05 | Finishing work | 80% | 20.1899 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
34 | KATIHAR | HSC AT BHARRA, BLOCK-HASANGANJ, KATIHAR |  |  | BALMIKI PRASAD SINGH, KATIHAR |  | 2017-03-06 | 2017-11-05 | Brick work is in progress | 25% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
35 | KATIHAR | HSC AT DHERUA, BLOCK-HASANGANJ, KATIHAR |  |  | BALMIKI PRASAD SINGH, KATIHAR |  | 2017-03-06 | 2017-11-05 | Foundaion work | 5% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
36 | KATIHAR | HSC AT RAMPUR, BLOCK-HASANGANJ, KATIHAR |  |  | BALMIKI PRASAD SINGH, KATIHAR |  | 2017-03-06 | 2017-11-05 | Finishing work | 80% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
37 | KATIHAR | HSC AT JOKER,BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 113.6883 |  |  | - |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Loa issued on 27-12.2016
38 | KATIHAR | HSC AT PIDAL, BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA |  |  |  | Plinth Beam | 10% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
39 | KATIHAR | HSC AT BALUGANJ, BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA |  |  |  | Brick work is in progress | 25% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
40 | KATIHAR | HSC AT BARIA, BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA |  |  |  | - |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
41 | KATIHAR | HSC AT CHANDPUR, BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA |  |  |  | - |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
42 | SUPAUL | HSC AT KATAIYA BLOCK-BASANTPUR, SUPAUL |  |  | Dhirendra Kumar Thakur, Supaul | 42.6685 | 2017-02-08 | 2017-08-07 | Finishing work | 85% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
43 | SUPAUL | HSC AT JIRWA BLOCK-BASANTPUR, SUPAUL |  |  | Dhirendra Kumar Thakur, Supaul |  | 2017-02-08 | 2017-08-07 | Finishing work | 85% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
44 | DARBHANGA | HSC AT NISTA, BLOCK-SINGHWARA (DARBHANGA) |  |  | M/s Delta Enterprises, Patna | 66.4002 | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
45 | DARBHANGA | HSC AT SAKARPUR, BLOCK-SINGHWARA (DARBHANGA) |  |  | M/s Delta Enterprises, Patna |  | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
46 | DARBHANGA | HSC AT KARAUNI, BLOCK-KEWTI (DARBHANGA) |  |  | M/s Delta Enterprises, Patna |  | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
47 | DARBHANGA | HSC AT JAGDISHPUR, BLOCK-MANIGACHHI (DARBHANGA) |  |  | M/s Delta Enterprises, Patna | 66.4002 | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
48 | DARBHANGA | HSC AT BHANDARISAM, BLOCK-MANIGACHHI (DARBHANGA) |  |  | M/s Delta Enterprises, Patna |  | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
49 | DARBHANGA | HSC AT RAMNAGAR, BLOCK-MANIGACHHI (DARBHANGA) |  |  | M/s Delta Enterprises, Patna |  | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
50 | PURNEA | HSC AT CHANKA, BLOCK-SRINAGAR, DIST.-KISHANGANJ |  |  | MDS Infranirman Pvt ltd, Patna | 129.6127 | 2017-03-23 | 2017-11-22 | Not Started |  | 19.94 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
51 | PURNEA | HSC AT UDAYNGAR, BLOCK-SRINAGAR, DIST.-KISHANGANJ |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | B/W is in progress. | 30% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
52 | PURNEA | HSC AT MANKAUL, BLOCK-SRINAGAR, DIST.-KISHANGANJ |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | Finishing work | 75% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
53 | PURNEA | HSC AT GADHIYA, BLOCK-SRINAGAR, DIST.-KISHANGANJ |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | Not Started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
54 | PURNEA | HSC AT LASANPUR, BLOCK-DAGARUA, DIST.-PURNEA |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | Not Started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
55 | PURNEA | HSC AT GADHWAS, BLOCK-DAGARUA, DIST.-PURNEA |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | Finishing work | 80% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
56 | MADHUBANI | HSC AT LAXMIPUR , BALATH, SUNDARPUR BILTHI, SATLAKHA, SAMBHAUR, KHARUVA NAJIRPUR & CHAURI , BLOCK-RAHINA, DIST.-MADHUBANI |  |  | Satish Narayan Singh, E. Champaran | 178.8191 |  |  | Laxmipur-Finishing work, Sundarpur Bilthi-Column work , Sambhaur-Plaster work | 55% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
57 | KATIHAR | HSC AT KURSEL,KAMRU,KURUM, BHRRI & ROSHANGANJ, BLOCK-KADWA, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 112.5097 | 2017-07-15 | 2018-03-14 | Kursel- Roof casted Bhrri- Roof casted, Kurum- Plinth Beam completed | 27% | 20.38 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | KAMRU, & ROSHANGAN -Land not available
58 | KATIHAR | HSC AT TAYABPUR WEST,NISTA, SAGRATH,SHIKARPUR & BHAWNAGAR BLOCK-KADWA, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 112.5097 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
59 | WEST CHAMPARAN | HSC AT PARSI, PIPRA,DHUMNAGAR,ROARI, SUNASATTI, & DHAMINAHA BLOCK-NARKATIYAGANJ, DIST.-WEST CHAMPARAN |  |  | Vikash Kumar Gupta | 137.1294 | 2017-05-05 | 2018-01-04 | ROARI- lintel level, Pipra & Dhaminha- Plinth Level, DHUMNAGAR Sunasatti- Roof Level | 30% | 48.4549 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | Parsi- Local Hindrance
60 | KATIHAR | HSC AT JAUNIYA, THAGDABARI, BHANDARTAL, RONIYA & Durgapur, BLOCK-KADWA, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 111.3366 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
61 | KISHANGANJ | HSC AT KALPEER, PATHARGHATTI, & LOHAGARA BLOCK-DIGHALBANK, DIST.-KISHANGANJ |  |  | M/S Dolphin Construction | 69.2523 | 2017-04-28 | 2017-10-27 | Completed | 100% | 24.39 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
62 | PURNEA | HSC AT MAUKHNAHA DEVINAGAR, BANSAR, HAUSI & BHATHAILI, BLOCK-SRINAGAR JALALGARH, DIST.-PURNEA |  |  | M/s Gautam Construction | 110.6699 | 2017-05-05 | 2018-01-04 | DEVINAGAR- Column work | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Rest site Land not clear
63 | PURNEA | HSC AT PALANKAP,KANJIYA,BHEMRA, SATARO, RAIBER & MIRJAPUR, BLOCK-BAISA, DIST.-PURNEA |  |  | SARWAR ALAM, KISHANGANJ | 115.4776 | 2017-05-09 | 2018-01-08 | Kanjiya- Roof Level | 35% | 14.69 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Rest site Land not clear
64 | PURNEA | HSC AT PARMANANDPUR,CHHATIYA GAURA, MAHARAJPUR & HARDA, BLOCK-PURNEA PURV, DIST.-PURNEA |  |  | Mannu Pratap Rana | 109.3228 | 2017-05-09 | 2018-01-08 | MAHARAJPUR- Completed, GAURA- Roof Casted, Harda- Layout | 60% | 20.42 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Rest site land not clear
65 | SITAMARHI | HSC AT CHAKAUTI, KURHAR & BUDHNAGAR, BLOCK-BOKHRA, DIST.-SITAMARHI |  |  | KUNDAN KUMAR SINGH | 68.446 | 2017-05-15 | 2017-11-14 | Kurhar-Finishing work | 96% | 21.76 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Chakauti & Budhnagar-Land not available
66 | PURNEA | HSC AT CHAPAY, SAUSA, DEVINAGAR, BAKHRIKAUL, MIRAMILIKH & SONGARHA, BLOCK-K. NAGAR, DIST.-PURNEA |  |  | SUDHIR KUMAR | 130.9923 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued (Land not clear)
67 | GOPALGANJ | HSC AT BHERIA, RAMCHANDARPUR, AWADHIYATOLA, GHATIWANA, INDERWASAKIN & BIDHESIATOLA, BLOCK-THAVE, DIST.-GOPALGANJ |  |  | SRI KRISHNA CONST. COMPANY | 114.6877 | 2017-05-11 | 2018-01-10 | GHATIWANA- column work (G.F) | 25% |  | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Rest Site Land not available
68 | KATIHAR | HSC AT BINJI, SIMARIA, PACHMA, CHANDAL & RAUTARA BLOCK-KODHA, DIST.-KATIHAR |  |  | AWANI DEVCON PVT. LTD. | 111.1959 | 2017-07-15 | 2018-03-14 | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
69 | KISHANGANJ | HSC AT PANISAL, HALAWALA, CHHAGALIA, GACHHPARA KAPGANDHA BLOCK-KISHANGANJ, DIST.-KISHANGANJ |  |  | SARWAR ALAM, KISHANGANJ | 114.1947 | 2017-05-09 | 8Months | GACHHPARA- Finishing work, Halawala- Roof casted | 60% | 24.83 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued, Rest site land not clear
70 | KATIHAR | HSC AT KANTNAGAR, SRANICHAK, BHAINSDIRA, BINDHTOLI & HASIMPUR, BLOCK-BARARI, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 111.3366 | 2017-10-09 | 2018-06-08 | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
71 | KISHANGANJ | HSC AT CHAITAL, BHOGDAWAR & MAHESWARI BLOCK-THAKURGANJ, DIST.-KISHANGANJ |  |  | Smt Rita Devi, Sasaram | 66.5741 | 2017-07-14 | 2018-03-13 | Completed | 100% | 66.57 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
72 | KISHANGANJ | HSC AT SHEETALPUR, SIGRI, GOVINDPUR, SAROGORA, POLTHA, HALDAGOAN, BAKSA, HALDIBARI & PAMAL BLOCK-POTHIA, DIST.-KISHANGANJ |  |  | Smt Rita Devi, Sasaram | 199.7222 | 2017-09-14 | 8 Months | SHEETALPUR-Completed ,Sigri-Completed, SAHUGORA-Completed, KOLTHA-Completed, HALDIBARI-Completed & PAMAL-Completed | 100% | 46.72 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Govindpur-Not started, Haldagaon & Baska-Land not clear
73 | KISHANGANJ | HSC AT NEJAGACHH, DUMARIA MADARSATOLA, BESARWATI, PATHAMARI & CHURLI, BLOCK-THAKURGANJ, DIST.-KISHANGANJ |  |  | Smt Rita Devi, Sasaram | 110.9568 | 2017-07-14 | 2018-03-13 | DUMARIA MADARSATOLA- Completed BESARWATI- Completed PATHAMARI-Completed & CHURLI- Completed | 100% | 40.43 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Nejagachh-Land not available
74 | KATIHAR | HSC AT KHERA, PARTAILI CHILMARA & HAJIPUR BLOCK-KATIHAR, DIST.-KATIHAR |  |  | PRAKASH KUMAR SAH | 93.8461 | 2017-05-15 | 2018-01-14 | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
75 | KATIHAR | HSC AT MAKGADPUR, SISIA, RAJWARA, NAKKIPUR & BHATWARA BLOCK-KODHA, DIST.-KATIHAR |  |  | AWANI DEVCON PVT. LTD. | 111.1959 | 2017-07-14 | 2018-03-13 | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
76 | PURNEA | HSC AT KAMALPUR, DARIAPUR, DUBEILI, MANIKPUR, LASANPUR CHAKWA & MARGA, BLOCK-PURNEA, DIST.-PURNEA |  |  | PRAKASH KUMAR SAH | 162.5791 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued (Land not clear)
77 | KISHANGANJ | HSC AT BORHA, BALUA & JAGIR, BLOCK-TEDHAGACHH, DIST.-KISHANGANJ |  |  | NAWNEE KUMAR SINGH | 65.9149 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
78 | KATIHAR | HSC AT BAIDA, KISHNUPUR, CHHOTA LAKHANPUR, BARIA, PAHARPUR PACHHIM TOLA, BLOCK-AMDABAD, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 112.5097 |  |  | BAIDA- Tie beam completed | 10% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
79 | KATIHAR | HSC AT KHATTI, CHAUKIAPUR, MAYAMARI, BABLABANN & PRANPUR BLOCK-AMDABAD, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 112.5097 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
80 | BHAGALPUR | HSC AT CHHOTI NALA, MADEDA, AMBIHA, BANIADIH, BLOCK-SANHAULA, DIST.-BHAGALPUR |  |  | SANJEEV KUMAR | 80.1661 |  |  | Not Started | - |  | sri Anil Kumar | Sri Sanjeev Ranjan | LOA issued
81 | PURNEA | HSC AT KARUA RAHIKA, BELAHAT, POTHIYA RAMPUR, RAMNAGAR, ROSKA KOSHAGARH & BITHNAULI KHEMCHAND BLOCK-K. NAGAR, DIST.-PURNEA |  |  | UNITED INFRA & INDUSTRIES | 139.2142 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued (Land not clear)
82 | KATIHAR | HSC AT SRAJDHANI, BHARSIA, BELGACHHI & RANI SIMARIA,, BLOCK-FALKA, DIST.-KATIHAR |  |  | LARKS BUILDCN PVT. LTD. | 87.2768 | 2017-03-20 | 2017-09-19 | SRAJDHANI- Finishing work,RANI SIMARIA-Plinth beam | 25% | 10.15 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
83 | PURNEA | HSC AT BAKHARI, GANDHAR, BISHARI & KHOKSA BLOCK-VAYSI, DIST.-PURNEA |  |  | SARWAR ALAM, KISHANGANJ | 92.3821 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
84 | PURNEA | HSC AT NAWABGANJ, BAKHARIA, CHOBHRA & MALHARIA, BLOCK-VAYSI, DIST.-PURNEA |  |  | TUFAIL AHMED KHAN | 68.98 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
85 | KISHANGANJ | HSC AT BHATGAON, HATHIDUBA, DUDHAUTI, BHOLMARA, RUPDAH & ADARGARI & KATHALDANGI, BLOCK-THAKURGANJ, DIST.-KISHANGANJ |  |  | Smt Rita Devi, Sasaram | 110.9568 | 2017-07-14 | 2018-03-13 | BHATGAON-Completed HATHIDUBA-Completed BHOLMARA-Completed | - | 20.35 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Dudhuti, & ADARGARI-Land not available
86 | KATIHAR | HSC AT MUKURIA, KHARSOTA, NIMAUL, MURAWATPUR & TEGHRA BLOCK-AZAMNAGAR, DIST.-KATIHAR |  |  | NEW SHIVA CONSTRUCTION | 105.5768 | 2017-05-15 | 2018-01-14 | MUKURIA-Brick work is in progress, KHARSOTA- Lintel Level | 20% | 6.8768 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Murawatpur-Pond
|  | TOTAL |  |  |  | 116.155 |  |  |  |  | 648.4571

## Medical college Schm (2)
CONSTRUCTION OF VARIOUS SCHEMES IN MEDICAL COLLEGE
SL NO | NAME OF DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | PATNA | CONSTRUCTION OF LECTURE THEATRE FOR 350 STUDENTS IN NALANDA MEDICAL COLLEGE & HOSPITAL,PATNA | 354 |  | Kislay Enterprises | 218.974 | 2015-01-16 | 2016-01-15 | Completed | 100% | 259.7921 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | PATNA | CONSTRUCTION OF BOUNDARY WALL AT NALANDA MEDICAL COLLEGE & HOSPITAL, PATNA (Hospital-9450') | 238.611 | 2015-07-07 | Sanjeev Kumar, Patna | 200.7525 | 2015-09-09 | 2016-03-08 | 3000 m work completed | 95% | 225.531 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
3 | PATNA | CONSTRUCTION OF BOUNDARY WALL AT NALANDA MEDICAL COLLEGE & HOSPITAL, PATNA (College-481') | 13.1675 |  | Ganesh Prasad Singh | 12.2914 | 2015-08-11 | 2015-11-10 | Completed | 100% | 13.1154 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
4 | PATNA | CONSTRUCTION OF CENTRAL LIBRARY AT NMCH (3rd floor), PATNA | 0 |  | Pawan Shekher | 75.816 | 2016-05-12 | 2017-02-11 | Completed | 100% | 76.6577 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
5 | PATNA | CONSTRUCTION OF MORTUARY BUILDING AT PMCH, PATNA | 506.6 |  | Ramesh Kumar Pandey | 415.6374 | 2014-12-19 | 2015-12-18 | Completed | 100% | 439.6476 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
6 | PATNA | CONSTRUCTION OF COMMON ROOM AT 1st FLOOR OF OLD BUILDING PMCH, PATNA | 79.18 |  | Lallu Kumar | 58.7125 | 2015-08-17 | 2016-04-16 | Completed | 100% | 66.41 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
7 | PATNA | CONSTRUCTION OF BOUNDARY WALL NEAR DARBHANGA HOUSE AT PATNA MEDICAL COLLEGE & HOSPITAL, PATNA (Hospital-9450') | 0 |  | Lallu Kumar | 22.2227 | 2017-02-22 | 2017-05-21 | Completed | 100% | 16.2858 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
8 | PATNA | UPGRADATION OF EMERGENCY WARD AT PATNA MEDICAL COLLEGE & HOSPITAL, PATNA | 996.795 |  | Rama and Sons | 835.948 | 2017-09-08 | 2018-06-07 | Finishing work in progress. | 98% | 623 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
8 | PATNA | RENOVATION OF KIDNEY TRANSPLANT UNIT WITH MODULAR UNIT AND FURNITURE AT PMCH, PATNA | 1266 | 2017-09-22 | Pan Solution Pvt Ltd, Patna | 907.3754 | [7 empty] | LOA ISSUED on 17/07/2018
9 | DARBHANGA | CONSTRUCTION OF CENTRAL LIBRARY IN DARBHANGA MEDICAL COLLEGE & HOSPITAL, LAHERIASARAI (DARBHANGA) | 985.7 |  | Indra narayan singh contractor pvt. Ltd | 660.4621 | 2014-07-09 | 2016-01-08 | Completed | 100% | 688.8881 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
10 | DARBHANGA | CONSTRUCTION OF P.G GIRLS HOSTEL IN DARBHANGA MEDICAL COLLEGE & HOSPITAL, LAHERIASARAI (DARBHANGA) | 1004.84 |  | Indra narayan singh contractor pvt. Ltd | 853.8188 | 2014-07-09 | 2016-01-08 | Completed | 100% | 667.7131 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
11 | DARBHANGA | CONSTRUCTION OF BOUNDARY WALL AT DARBHANGA MEDICAL COLLEGE & HOSPITAL, LAHERIASARAI (DARBHANGA) | 81.3611 |  | Smt Rita Devi,Sasaram | 69.7102 | 2015-08-06 | 2015-12-05 | 830m B/W completed out of 1100m | 95% | 50.8775 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Work started on 05/01/2016 after New site given by Medical college
13 | BHAGALPUR | CONSTRUCTION OF BOUNDARY WALL AT JAWAHARLAL NEHRU MEDICAL COLLEGE & HOSPITAL BHAGALPUR (Length-8160 m) | 456.85 |  | Anand Consultant | 427.4809 | 2014-08-07 | 2015-08-06 | Completed | 100% | 427.48 | Sri Anil Kumar | Sri Sanjeev Ranjan
13 | BHAGALPUR | CONSTRUCTION OF BOUNDARY WALL AT JAWAHARLAL NEHRU MEDICAL COLLEGE & HOSPITAL BHAGALPUR (Length-8160 m) |  |  | Rohit Raj Construction Pvt Ltd, Vaishali | 283.335 | [5 empty] | Sri Anil Kumar | Sri Sanjeev Ranjan | LOA issued on-09/05/2018
14 | BHAGALPUR | CONSTRUCTION OF 100 BEDDED BOYS HOSTEL AT JLNMCH, BHAGALPUR | 705.28 |  | Lalan Kumar | 941.6415 | 2016-05-20 | 2017-11-19 | Completed | 100% | 930.84 | Sri Anil Kumar | Sri Sanjeev Ranjan
15 | BHAGALPUR | CONSTRUCTION OF 50 BEDDED PG BOYS HOSTEL AT JLNMCH, BHAGALPUR | 550.95 |  | Lalan Kumar |  | 2016-05-20 | 2017-11-19 | Completed | 100% |  | Sri Anil Kumar | Sri Sanjeev Ranjan
16 | BHAGALPUR | CONSTRUCTIN OF LECTURE THEATRE AT JAWAHARLAL NEHRU MEDICAL COLLEGE & HOSPITAL BHAGALPUR | 203.77 |  | Ajay Kumar Chaudhary | 142.2769 | 2014-12-15 | 2015-12-14 | Completed | 100% | 142.28 | Sri Anil Kumar | Sri Sanjeev Ranjan
17 | GAYA | CONSTRUCTION OF VARIOUS BUILDING IN ANUGRAH NARAYAN MAGADH MEDICAL COLLEGE & HOSPITAL GAYA |  |  | M/S Dipansu Promoter & Builder Pvt. Ltd., Ranchi | 2296.2247 | 2014-09-04 | 2016-09-03
|  | (a) Administrative Block | 490.01 | [5 empty] | Completed | 100% | 335.2156 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
|  | (b) Principal Residence | 126.49 | [5 empty] | Completed | 100% | 100.0745 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
|  | (c) P.G boys hostel | 611.68 | [5 empty] | Completed | 100% | 324.9473 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
|  | (d) P.G girls hostel | 573.98 | [5 empty] | Completed | 100% | 342.5583 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
|  | (e) 64 Tutor Residence (2 Blocks) | 1336.03 | [5 empty] | Completed | 100% | 1202.8559 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
18 | MUZAFFARPUR | CONSTRUCTION OF 250 BEDDED NURSES QUARTER AT SRI KRISHNA MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR (1400') |  |  | SKS-KKT, Sitamarhi | 1507.9578 | [5 empty] | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | LOA ISSUED ON-14/06/2018
18 | MUZAFFARPUR | CONSTRUCTION OF BOUNDARY WALL AT SRI KRISHNA MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR (1400') | 28.701 |  | Ramjee Prasad | 24.1566 | 2014-08-19 | 2014-11-18 | Completed | 100% | 17.7537 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
19 | MUZAFFARPUR | CONSTRUCTION OF TUTOR RESIDENCE AT SRI KRISHNA MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR | 0 |  | Arun Deo Kumar | 2084.4857 | 2017-05-15 | 2019-05-14 | Finishing work in progress. | 65% | 251.6359 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
20 | MUZAFFARPUR | CONSTRUCTION OF BOYS HOSTEL AT SRI KRISHNA MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR | 0 |  | Arun Deo Kumar |  | 2017-05-15 | 2019-05-14 | Finishing work in progress. | 65% | 303.4354 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
21 | MUZAFFARPUR | UPGRADATION OF INTERNAL ROAD OF RBTS HOMEOPATHIC MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR | 0 |  | Ashok Kumar Singh, Muzaffarpur | 31.8427 | 2017-09-06 | 2017-12-05 | Completed | 100% | 26.6442 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
22 | BETTIAH | CONSTRUCTION OF 7 LABORATORIES IN GOVT. MEDICAL COLLEGE BETTIAH BY PRE-FABRICATED MATERIAL | 318.9 |  | Shiva infra solution pvt. Ltd | 281.8471 | 2014-11-27 | 2015-03-26 | Completed | 100% | 234.182 | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | Handed over
23 | BETTIAH | EXPENSION OF INTERNAL CAPACITY OF GOVT. MEDICAL COLLEGE BETTIAH | 0 |  | Irfan Akhtar | 37.4214 | 2018-02-02 | 2019-04-01 | 70% work completed | 87% | 31.85 | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
24 | BETTIAH | CONSTRUCTION OF GYMNASIUM AND COMMON ROOM AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH (Prefab) | 0 |  | Fab India | 120 | 2018-03-15 | 2018-07-14 | 25% work completed | 25% | 24 | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
25 | BETTIAH | CONSTRUCTION OF CENTRAL LIBRARY AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH (Prefab) | 0 |  | Shiva Infra Solutions Pvt. Ltd., | 446.45 | 2017-10-16 | 2018-04-15 | 25% work completed | 80% | 312.5 | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
26 | BETTIAH | CONSTRUCTION OF LECTURE THEATRE AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH (Prefab) | 0 |  | Jindal Mectec Pvt. Ltd | 133.39 | - | - | completed | 100% | 112 | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
27 | BETTIAH | CONSTRUCTION OF 100 BEDDED HOSTEL (G+2) AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH (Prefab) | 0 |  | Jindal Mectec Pvt. Ltd | 524.7 | 2018-04-06 | 2018-10-05 | - | - | - | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
28

## Misc (2)
Miscellaneous Work
SL NO | NAME OF DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | Amount (in rs lakh) |  |  | STAGE | % | Amount (in rs lakh)
1 | PATNA | CONSTRUCTION OF 1st & 2nd FLOOR OF GOVT. TIBBI COLLEGE KADAMKUAN, PATNA | 1059.15 |  | M/S Indra Narayan singh cont. pvt. Ltd. | 574.6037 | 2013-11-11 | 2014-11-10 | Completed | 100% | 524.8529 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | MUZAFFARPUR | CONSTRUCTION OF 30 BEDDED MCH WING , PILKHI VILLAGE MUZAFFARPUR | 172 |  | Sri Nalin Ranjan | 159.1053 | 2013-08-20 | 2014-08-19 | Completed | 100% | 164.9623 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
3 | BHOJPUR | CONSTRUCTION OF 180 BEDDED MENTAL HOSPITAL KOILWAR, ARA (BHOJPUR) | 383.283 |  | Revire venture india pvt. Ltd. | 277.8557 | 2014-07-17 | 2014-09-01 | Completed | 100% | 131.8652 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
4 | PATNA | CONSTRUCTION OF ORTHO WARD AT LNJPN HOSPITAL, RAJVANSHI NAGAR (PATNA) | 209.65 |  | Santosh Kumar Singh, Godda (Jharkhand) | 126.6577 | 2015-08-19 | 2016-05-18 | Completed | 100% | 122.963 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
5 | JAMUI | CONSTRUCTION OF BOUNDARY WALL AT PHC BARHAT, JAMUI | 1.219 |  | Sri Shambhu yadav, Jamui | 1.4565 | 2015-11-30 | 2016-02-29 | Completed | 100% | 1.3363 | Sri Anil kumar | Sri Rajendra Prasad Singh | Handed over
6 | SAMASTIPUR | CONSTRUCTION OF BOUNDARY WALL AT APHC BANDHAR (SAMASTIPUR) | 14.66 |  | Abhishek Ranjan, Samastipur | 16.146 | 2015-08-27 | 2016-11-26 | Completed | 100% | 37.3167 | Sri Sunil kumar | Sri Rajendra Prasad Singh | Handed over
7 | JAMUI | CONSTRUCTION OF BOUNDARY WALL AT APHC SONHO, JAMUI (Length-1161') | 19.175 |  | Sri Rajeev Kumar Singh | 20.3331 | 2015-08-19 | 2015-11-18 | Completed | 100% | 20.3307 | Sri Anil kumar | Sri Rajendra Prasad Singh | Handed over
8 | PURNEA | CONSTRUCTION OF MATERNITY HOME AT VYASI, DIST-PURNEA | - | - | M/S Savitri Construction, Patna | 24.5792 | - | - |  |  | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan | MSDP Project, LOA issued
9 | PATNA | CONSTRUCTION OF MAIN GATE & APPROACH ROAD OF STATE HEALTH SOCIETY, PATNA | - |  | Sri Lallu Kumar, Patna | 33.1507 | 2016-10-13 | s | Completed | 100% | 38.1507 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
10 | PATNA | CONSTRUCTION OF STAFF QUARTER AT SUB-DIVISIONAL HOSPITAL, DANAPUR | 115.14 | 2016-01-11 | MDS Infra Nirman Pvt. Ltd. | 91.9278 | 2017-02-07 | 2017-11-06 | Completed | 100% | 91.93 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
11 | NAWADA | CONSTRUCTION OF STAFF QUARTER AT SUB-DIVISIONAL HOSPITAL, NAWADA | 115.14 | 2016-01-11 | Uday Kumar, Rohtas | 82.9098 | 2017-06-29 | 2018-03-28 | Finishing work is going on | 80% | 29.52 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
12 | ARWAL | CONSTRUCTION OF STAFF QUARTER AT SUB-DIVISIONAL HOSPITAL, ARWAL | 115.14 | 2016-01-11 | M/s Triveni Const. | 90.5734 | 2017-05-05 | 2018-02-04 | Completed | 100% | 90.57 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
13 | PATNA | CONSTRUCTION OF DENTAL, SKIN & ENT OPD BUILDING AT GARDANIBAGH HOSPITAL, PATNA | 343.3 | 2015-12-21 | Devendra Prasad Singh | 253.5725 | 2017-05-25 | 2018-02-24 | Finishing work is going on | 70% | 46 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
14 | NALANDA | CONSTRUCTION OF 4 nos DOCTORS QUARTER & 8 nos STAFF QUARTER AT REFFERAL HOSPITAL KALYAN BIGHA, BLOCK- HARNAUT, DIST-NALANDA | 256.94 | 2017-03-07 | A.K Chaudhary | 196.3365 |  |  | Roof Shuttering (1st.F) | 30% | 31.43 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
15 | NALANDA | CONSTRUCTION OF RAMP & TOILET AT REFFERAL HOSPITAL, KALYANBIGHA,BLOCK-HARNAUT, DISTT-NALANDA | 60.0048 | 2017-03-10 | Lallu Kumar, Barh | 50.4662 |  |  | Completed | 100% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
16 | SAMASTIPUR | CONSTRUCTION OF JAN NAYAK KARPURI THAKUR REFFERAL HOSPITAL TAJPUR, SAMASTIPUR | - | - | Satyanarayan Singh | 580.622 | 2018-05-17 | 2019-08-16 | Roof casted (G.F) | 25% | 0 | Sri Sunil kumar | Sri Rajendra Prasad Singh
17 | PATNA | RENOVATION OF BUILDING & B/W AT GOVT. DRUG TESTING LABORATRY AGAMKUAN, PATNA | - | - | Regal Infratrading Pvt Ltd, Patna | 66.8107 | 2018-05-17 | 2018-08-16 | 60% work completed |  | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
18 | PATNA | RENOVATION & EXTENSION OF 104 CALL CENTRE AT 2nd FLOOR AT STATE HEALTH SOCIETY, PATNA | - | - | Dhanmendra Sharma | 7.0269 | 2018-07-12 | 2018-11-11 | Work is going on | 80% | 0 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
19 | SHEIKHPURA | CONSTRUCTION OF REFFERAL HOSPITAL AT BARBIGHA, SHEIKHPURA | - | - | Lallu Kumar, Barh | 460 | 2018-06-19 | 2019-06-18 | Roof casted (G.F) | 15% | 44.1666 | Sri Anil Kumar | Sri Sanjeev Ranjan
|  | TOTAL | 2864.8018 |  |  | 3114.1338 |  |  |  |  | 1375.3945

## DEIC & mch (2)
DISTRICT EARLY INTERVENTION CENTRE
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | BHAGALPUR | CONSTRUCTION OF DEIC AT JLNMCH,BHAGALPUR | 122.4381 | 2016-03-18 | Ajay Kumar Chaudhary | 98.4078 | 2017-05-09 | 2018-02-08 | Finishing work is in progress | 85% | 40 | Sri Anil Kumar | Sri Sanjeev Ranjan
2 | SAHARSA | CONSTRUCTION OF DEIC AT SADAR HOSPITAL, SAHARSA | 122.4381 | 2016-03-18 | Bambam Singh | 99.3508 | 2017-06-02 | 2018-03-01 | Brick work is in progress | 55% | 36 | Sri Sunil Kumar | Sri Rajendra Prasad
3 | MUZAFFARPUR | CONSTRUCTION OF DEIC AT SADAR HOSPITAL, MUZAFFARPUR | 122.4381 | 2016-03-18 | Md. Nabi | 96.9552 | 2017-06-29 | 2018-03-28 | Completed | 100% | 83.96 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad | Handed Over
4 | GAYA | CONSTRUCTION OF DEIC AT PRABHAWATI HOSPITAL, GAYA | 123.692 | 2016-03-18 | Ram Pukar Singh, Gaya | 90.2932 | 2017-08-23 | 2018-05-22 | Completed | 100% | 68 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
| TOTAL |  | 491.0064 |  |  | 385.0071 |  |  |  |  | 227.96
MCH WING
1 | BHAGALPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT JLNMCH,BHAGALPUR | 1335.61 | 2016-06-16 | Devine Lotus Infrastructure Pvt Ltd | 1080.3916 | 2018-05-24 | 2019-11-23 | Foundation work is going on | 5% | 0 | Sri Anil Kumar | Sri Sanjeev Ranjan
2 | MUZAFFARPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT SKMCH, MUZAFFARPUR | 1337.89 | 2016-06-16 | Arun Deo Kumar | 1078.6605 | 2018-03-23 | 2019-09-22 | Roof casted (F.F) | 30% | 125 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad
3 | MUZAFFARPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT SADAR HOSPITAL MUZAFFARPUR | 1342.31 | 2016-06-16 | Kishor Kumar | 1082.8245 | 2018-03-23 | 2019-09-22 | Roof casted (F.F) | 20% | 105 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad
4 | GAYA | CONSTRUCTION OF 100 BEDDED MCH WING AT ANMMCH, GAYA | 1325.04 | 2016-06-16 | Akshit Engineering | 1026.7457 | 2018-06-01 | 2019-12-31 | 0 | 0 | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Old buiding to be demolished
5 | DARBHANGA | CONSTRUCTION OF 100 BEDDED MCH WING AT DMCH, DARBHANGA | 1312.06 | 2016-06-16 | Sanjay Kumar, Darbhanga | 1024.4141 | 2018-06-29 | 2019-12-28 | 0 | 0 | 0 | Sri Sunil Kumar | Sri Rajendra Prasad | Land not decided
6 | SITAMARHI | CONSTRUCTION OF 100 BEDDED MCH WING AT SADAR HOSPITAL SITAMARHI |  | 2016-06-16 | Shashikant Singh, Sheohar | 1080.07 | [5 empty] | Sri Arjun Kumar Mishra | Sri Rajendra Prasad | LOA issued on 10/05/2018
|  | TOTAL | 4015.81 |  |  | 6373.1064

## Eye Bank
EYE BANK
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Patna | RENOVATION OF EYE BANK AT PMCH, PATNA | 118.5988 | 2018-02-21 | M/s Gauri Homes Pvt. Ltd. | 19.06 | 2018-06-29 | 2018-08-28 | Completed | 100% | 7.78 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | Bhagalpur | RENOVATION OF EYE BANK AT JLMNCH, BHAGALPUR | 117.32 | 2018-02-21 | Shabnam Sharma | 18.1 | 2018-06-21 | 2018-08-20 | Completed | 100% | 18.1 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed over
3 | Muzaffarpur | CONSTRUCTION OF EYE BANK AT SKMCH, MUZAFFARPUR | 124.36 | 2018-02-21 | M/s Harendra Construction | 23.98 | 2018-07-09 | 2018-10-08 | Finishing work | 70% | 4.36 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad
4 | Darbhanga | CONSTRUCTION OF EYE BANK AT DMCH, DARBHANGA | 124.36 | 2018-02-21 | M/s Harendra Construction | 23.83 | 2018-07-05 | 2018-10-04 | Plaster work is going on | 60% | 5.5797 | Sri Sunil Kumar | Sri Rajendra Prasad
5 | Gaya | CONSTRUCTION OF EYE BANK AT ANMMCH, GAYA | 148.63 | 2018-02-21 | M/s Gauri Homes Pvt. Ltd. | 43.14 | 2018-07-25 | 2018-10-24 | Plaster work is going on | 50% | 4.69 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
6 | Bettiah | CONSTRUCTION OF EYE BANK AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH | 124.36 | 2018-02-21 | M/s Harendra Construction | 24.41 | 2018-07-18 | 2018-10-17 | Roof casted | 60% | 6.6469 | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad
7 | Patna | RENOVATION OF EYE BANK AT NMCH, PATNA | 124.15 | 2018-02-21 | Asha Homes Infra Pvt Ltd | 23.67 | 2018-07-18 | 2018-10-17 | - | - |  | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Kept on hold