## ANM (3)
CONSTRUCTION OF AUXILIARY NURSE MIDWIFERY (A.N under GOI schemes
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date with centage (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of ANM training school & hostel |  | 5120.94 | 1376 | 0 |  | 10 | 10 | 0 | - |  | -
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | EXPENDITURE WITH CENTAGE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Darbhanga | Construction of A.N.M school & hostel at refferal hospital Jale, Darbhanga | 584.9925 | 2013-09-24 | Avaneesh Enterprises, Ghaziabad | 436.89 | 2014-07-19 | 2015-07-18 | Completed | 100% | 315.09 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
2 | Nawada | Construction of A.N.M school & hostel at refferal hospital Rajauli, Nawada | 448.7312 | 2013-09-24 | Bipin Kumar, Nawada | 380.7919 | 2014-08-29 | 2015-08-28 | Completed | 100% | 418.34 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
3 | Siwan | Construction of A.N.M Training school & Hostel in Referral hospital, Mairwa (Siwan) | 593.2551 | 2013-09-24 | G.M Construction, Ahmedabad | 408.9828 | 2014-07-26 | 2015-07-25 | Completed | 100% | 385.54 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
4 | Aurangabad | Construction of A.N.M Training school & Hostel in Referral hospital, Daudnagar (Aurangabad) | 468.4109 | 2013-09-24 | Yashswi Infrastructure pvt. Ltd., Ranchi | 385.9641 | 2015-01-19 | 2016-01-18 | Completed | 100% | 416.89 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
5 | Kaimur | Construction of A.N.M Training school & Hostel in Sadar hospital, Bhabhua (Kaimur) | 484.7357 | 2013-09-24 | Anil Kumar, Rohtas | 409.0411 | 2014-08-25 | 24-08-2015 | Completed | 100% | 460.58 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
6 | Khagaria | Construction of A.N.M Training school & Hostel in Sadar hospital, Khagaria | 580.1198 | 2013-09-24 | Surendra Prasad Singh, Begusarai | 400.964 | 2015-01-09 | 2016-01-08 | Completed | 100% | 429.02 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
7 | Lakhisarai | Construction of A.N.M Training school & Hostel in Sadar hospital, Lakhisarai | 472.2124 | 2013-09-24 | Rama construction, Patna | 406.7411 | 2014-07-19 | 2015-07-18 | Completed | 100% | 459.35 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
8 | Supaul | Construction of A.N.M school & hostel at Sub-divisional hospital Triveniganj, Supaul | 502.7791 | 2013-09-24 | Avaneesh Enterprises, Ghaziabad | 426.5652 | 2014-07-18 | 2015-07-17 | Completed | 100% | 364.59 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
9 | Sheohar | Construction of A.N.M school & hostel at sadar hospital, sheohar | 501.5786 | 2013-09-24 | Virendra Kumar Chaudhary | 401.3985 | 2014-12-29 | 2015-12-28 | Completed | 100% | 447.94 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
10 | Jamui | Construction of A.N.M at Refferal Hospital Lakshmipur (Jamui) | 484.1236 | 2013-09-24 | M/S Balkrishan Dholakiya construction pvt ltd | 396.8122 | 2015-08-19 | 2016-05-18 | Completed | 100% | 424.58 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
| Total |  | 5120.9389 |  |  | 4054.151 |  |  |  |  | 4121.92

## GNM (3)
CONSTRUCTION OF GENERAL NURSE MIDWIFERY (G.N.M) under GOI schemes
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date with centage (in Rs Lakh) |  | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of GNM training school & hostel |  | 10772.98 | 3625 | 7526.37 |  | 11 | 7 | 4 | 0
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | EXPENDITURE WITH CENTAGE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Rohtas | Construction of G.N.M Training school & hostels in Sadar hospital, Sasaram (Rohtas) | 1220.1724 | 2013-10-03 | M/S B Prasad & co. Anishabad, Patna | 894.3811 | 2014-06-11 | 2015-12-10 | Completed | 100% | 1047.27 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | Banka | Construction of G.N.M at Sadar Hospital Banka | 1222.3616 | 2013-10-03 | M/S Lalan Kumar | 969.1582 | 2014-11-26 | 2016-05-25 | Completed | 100% | 982.35 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
3 | Jahanabad | Construction of G.N.M at Sadar Hospital Jahanabad | 963.5628 | 2013-10-03 | M/S Yashaswi construction, Anishabad (Patna) | 941.7381 | 2015-11-27 | 2017-05-26 | Completed | 100% | 1089.49 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
4 | Saharsa | Construction of G.N.M at Sadar Hospital Saharsa | 1038.9261 | 2013-10-03 | Baba Hans construction Pvt. Ltd | 973.0374 | 2014-12-26 | 2016-06-25 | Completed | 100% | 835.12 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over
5 | Buxar | Construction of G.N.M at Sadar Hospital Buxar | 1004.8402 | 2013-10-03 | Rajesh Kumar | 845.0891 | 2017-05-09 | 2018-11-08 | Completed | 100% | 741.47 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
6 | Sheikhpura | Construction of G.N.M at Sadar Hospital Sheikhpura | 983.4306 | 2013-10-03 | Arun Deo Kumar | 828.358 | 2015-12-31 | 2017-06-30 | Completed | 100% | 1024.55 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
7 | West Champaran | Construction of G.N.M at Bettiah, West Champaran | 1022.1539 | 2013-10-03 | Rama & Sons | 855.7345 | 2017-05-11 | 2018-11-10 | Completed | 100% | 685.12 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
8 | Saran | Construction of G.N.M at Sadar Hospital Chapra (Saran) | 1255.9296 | 2013-10-03 | M/S Harishankar Prasad | 1019.7473 | 2014-12-26 | 2016-06-25 | Block A-Finishing work Block B- Finishing work | 95% | 837.88 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Contractor debarred for participating in tender due to delay in work
9 | Purnea | Construction of G.N.M at Sadar Hospital Purnea | 1020.6944 | 2013-10-03 | M/S Satyanarayan Singh | 894.0844 | 2015-12-15 | 2017-06-14 | Academic Block-Finishing work is in progress | 48% | 283.12 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | 1. Academic Block near completion. 2. Land available for hostel block.
10 | Madhepura | Construction of G.N.M at Medical College & Hospital Madhepura | 1040.9035 | 2013-10-03 | - | - | - | - | Finishing work is in progress. | 85% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Being constructed with Medical College. Hence separate expenditure not given.
11 | Gaya | Construction of G.N.M at ANMMCH, Gaya | 1330.42 | 2017-12-14 | Prasad Associates | 1110.8 | 2019-03-02 | 2020-09-01 | work started
| Total |  | 12103.3951 |  |  | 9332.128 |  |  |  |  | 7526.37

## Sub-Divisional
SUB-DIVISIONAL HOSPITAL
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | SITAMARHI | CONSTRUCTIN OF SUB-DIVISIONAL HOSPITAL AT BELSAND, DIST-SITAMARHI | 1374.23 | 2017-03-06 | Kamalpura Construction Pvt Ltd, Muzaffarpur | 1155.6773 | 2018-12-19 | 2020-06-18 | Roof casted (Terrace Floor) | 35% | - | Sri Pankaj Kumar | Sri Sanjeev Ranjan
2 | VAISHALI | CONSTRUCTIN OF SUB-DIVISIONAL HOSPITAL AT MAHNAR, DIST-VAISHALI | 1238.64 | 2017-03-06 | M/S Satyanarayan Singh | 1040.07 | 2019-03-02 | 2020-09-01 | Not Started | - | - | Sri Sandeep Kumar | Sri Sanjeev Ranjan | Work to be started
3 | MADHUBANI | CONSTRUCTIN OF SUB-DIVISIONAL HOSPITAL AT BENIPATTI, DIST-MADHUBANI | 1310.11 | 2017-03-06 | - | - | - | - | Not Started | - | - | Sri Sunil Kumar | Md. Shamim Ahmad | Financial bid opened, Lottery to be done
4 | MUNGER | CONSTRUCTIN OF SUB-DIVISIONAL HOSPITAL AT HAWELI KHARAGPUR, DIST-MUNGER | 1180.34 | 2017-03-06 | M/S Satyanarayan Singh | 991.8986 | 2019-03-08 | 2020-09-07 | Not Started | - | - | Sri Anil Kumar | Sri Rajendra Prasad Singh | LOA issued on- 07/12/2018
5 | BEGUSARAI | CONSTRUCTIN OF SUB-DIVISIONAL HOSPITAL AT BAKHRI, DIST-BEGUSARAI | 1409.22 | 2017-03-06 | M/s Surendra Prasad Singh | 1185.18 | - | - | Not Started | - | - | Sri Anil Kumar | Sri Rajendra Prasad Singh | Land not available. Letter sent to D.M vide Letter no-4631, Dated-31/12/2018
6 | BEGUSARAI | CONSTRUCTIN OF SUB-DIVISIONAL HOSPITAL AT TEGHRA, DIST-BEGUSARAI | 1305.04 | 2017-03-06 | Kaushal Buildcon Pvt Ltd | 1097.67 | 2019-03-08 | 2020-09-07 | Foundation work is going on | 5% | - | Sri Anil Kumar | Md. Shamim Ahmed | LOA issued on- 07/12/2018
7 | SARAN | CONSTRUCTIN OF SUB-DIVISIONAL HOSPITAL AT MADHAURA, DIST-SARAN | 1314.58 | 2017-03-06 | M/s Highway Construction co, Jharkhand | 1105.4011 | - | - | Not Started | - | - | Sri Sagar Jaiswal | Sri Rajendra Prasad Singh | Land not available. Letter sent to Land reform DC vide Letter no-3498, Dated-26/10/2018 & Letter sent to D.M vide Letter no-4318, Dated-11/12/2018
|  | Total | 9132.16 |  |  | 6575.897

## DFID (2)
PROJECTS IN MEDICAL COLLEGES {UNDER DFID (Department for International Development, U.K.) FUNDING}
SL NO | Name of work |  | A.A. RECEIVED FROM | A.A Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Expenditure in Percentage (%) against agrrement | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects | REMARKS
1 | Construction of various project in Medical colleges of Bihar |  | Health Dept. | 16345.42 | 16345.42 | 10929.0271 | 80.76% | 21 | 20 | - |  | 1 (Diagnostic Centre)
Detailed Report (DFID)
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE EXPENDITURE | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS IN LAKH) |  |  | STAGE | % | (RS IN LAKH)
NMCH, Patna
1 | Patna | CONSTRUCTION OF CENTRE OF EXCELLENCE AT NMCH, PATNA | 4211.7 | 2014-11-08 | M/S B. Rai | 3711.8095 | 2015-11-27 | 2017-05-26 | Completed | 100% | 4070.49 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
2 |  | CONSTRUCTION OF B.SC NURSING AT NMCH, PATNA | 2762.26 | 2015-03-25 | Indra Narayan Singh contractors pvt ltd, Patna | 2350.1997 | 2015-12-09 | 2017-06-08 | Completed | 100% | 24 77.12 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
3 |  | CONSTRUCTION OF VACCINE CENTRE AT NMCH, PATNA | 1094.24 | 2015-09-01 | M/S B. Prasad | 887.3434 | 2016-04-13 | 2017-10-12 | Completed | 100% | 875.83 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
4 |  | CONSTRUCTION OF MODEL RECORD ROOM AT NMCH, PATNA | 170.98 | 2015-04-28 | R.K infra services pvt ltd, Patna | 122.4525 | 2016-02-05 | 2016-11-04 | Completed | 100% | 101.1487 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
|  | Sub Total of NMCH | 8239.18 |  |  | 7071.805
PMCH, Patna
5 | Patna | CONSTRUCTION OF LECTURE THEATRE (250 seater) AT PMCH, PATNA | 275.08 | 2015-03-27 | Ramesh Kumar Pandey | 342.361 | 2015-12-09 | 2017-06-08 | Completed | 100% | 227.29 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
6 |  | CONSTRUCTION OF MODEL RECORD ROOM AT PMCH, PATNA | 170.98 | 2015-04-28 | Ramesh Kumar Pandey |  | 2015-12-09 | 2017-06-08 | Completed | 100% | 155.28 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
7 |  | CONSTRUCTION OF 150 BEDDED HOSTEL AT PMCH, PATNA | 1029.78 | 2015-04-28 | Sudhesh Kumar Singh & company pvt ltd | 812.0747 | 2015-12-09 | 2017-06-08 | Completed | 100% | 787.13 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
|  | Sub Total of PMCH | 1475.84 |  |  | 1154.4356
ANMMCH, Gaya
8 | Gaya | CONSTRUCTION OF CENTRAL LIBRARY AT ANMMCH, GAYA | 584.55 | 2015-04-28 | Simens construction corporation, Patna | 2703.6702 | 2015-12-31 | 2017-12-30 | Completed | 100% | 588.98 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
9 |  | CONSTRUCTION OF MODEL RECORD ROOM AT ANMMCH, GAYA (Above central library) | 170.98 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
10 |  | CONSTRUCTION OF EMERGENCY WARD AT ANMMCH, GAYA | 1294.74 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 | Completed | 100% | 639.6097 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
11 |  | CONSTRUCTION OF 136 BEDDED GIRLS HOSTEL AT ANMMCH, GAYA | 1109 | 2015-04-28 |  |  | 2015-12-31 | 2017-12-30 | Completed | 100% | 903.1949 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
12 |  | CONSTRUCTION OF 250 SEATER LECTURE THEATRE (2 units) ANMMCH, GAYA | 550.16 | 2015-03-27 |  |  | 2015-12-31 | 2017-12-30 | Completed | 100% | 382.6237 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
|  | Sub Total of ANMMCH, Gaya | 3709.43 |  |  | 2703.6702
SKMCH, Muzaffarpur
13 | Muzaffarpur | CONSTRUCTION OF 75 BEDDED GIRLS HOSTELAT SKMCH, MUZAFFARPUR | 499.12 | 2015-03-27 | Mother India pvt ltd | 972.9731 | 2015-12-15 | 2017-06-14 | Completed | 100% | 375.5403 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
14 |  | CONSTRUCTION OF 250 CAPACITY LECTURE THEATRE (2 units) AT SKMCH, MUZAFFARPUR | 550.16 | 2015-03-27 |  |  | 2015-12-15 | 2017-06-14 | Completed | 100% | 373.2826 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
15 |  | CONSTRUCTION OF MODEL RECORD ROOM AT SKMCH, MUZAFFARPUR | 170.98 | 2015-04-28 |  |  | 2015-12-15 | 2017-06-14 | Completed | 100% | 135.5105 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed Over
|  | Sub Total of SKMCH, Muzaffarpur | 1220.26 |  |  | 972.9731
JLNMCH, Bhagalpur
16 | Bhagalpur | CONSTRUCTION OF CENTRAL LIBRARY AT JLNMCH, BHAGALPUR | 584.55 | 2015-04-28 | Nandlal & Company | 1199.64 | 2015-09-09 | 2017-03-08 | Completed | 100% | 465.44 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
17 |  | CONSTRUCTION OF GIRL'S HOSTEL (75 capacity) AT JLNMCH, BHAGALPUR | 499.12 | 2015-03-27 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% | 400 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
18 |  | CONSTRUCTION OF 250 CAPACITY LECTURE THEATRE (1 units) JLNMCH, BHAGALPUR | 275.08 | 2015-03-27 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% | 334.2 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
19 |  | CONSTRUCTION OF MODEL RECORD ROOM AT JLNMCH, BHAGALPUR | 170.98 | 2015-04-28 |  |  | 2015-09-09 | 2017-03-08 | Completed | 100% |  | Sri Anil Kumar | Sri Sanjeev Ranjan
|  | Sub Total of JLNMCH, Bhagalpur | 1529.73 |  |  | 1199.64
DMCH, Darbhanga
20 | Darbhanga | CONSTRUCTION OF MODEL RECORD ROOM AT DMCH, DARBHANGA | 170.98 | 2015-04-28 | Shaurya Premier Infrastructure Pvt ltd | 125.0267 | 2016-08-30 | 2017-08-29 | Completed | 100% | 113.4767 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
|  | Total | 16345.42 |  |  | 13227.5508 |  |  |  |  | 10929.0271

## PHC TO CHC (Health) (2)
PHC TO CHC (30 BEDDED) {Health deptt-38 nos}
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects |  | REMARKS
1 | Construction of PHC to CHC (Health deptt.) |  | 14036.06 | 24433.92 | 9909.8533 | 38 | 24 | 14 |  | 0
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS | NAME OF SUPERVISION CONSULTANT
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | JAMUI | CHC AT PHC GIDHAURE (JAMUI) | 369.37 | 2014-09-03 | Ashok & co niwas pvt ltd, Jamui | 338.9408 | 2015-08-31 | 2016-08-30 | Completed | 100% | 338.94 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over | SGS India pvt ltd, Kolkata | 4th ra
2 | VAISHALI | CHC AT PHC RAJAPAKAR (VAISHALI) | 369.37 | 2014-09-03 | Rana construction, Kadamkuan (Patna) | 318.9036 | 2015-08-31 | 2016-08-30 | Completed | 100% | 330.65 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over | K&J projects pvt ltd, Nagpur | fb
3 | EAST CHAMPARAN | CHC AT PHC SANGRAMPUR (EAST CHAMPARAN) | 369.37 | 2014-09-03 | Nagendra Mishra, Muzaffarpur | 311.077 | 2015-08-31 | 2016-08-30 | Completed | 100% | 300.51 | Md Nasim Akhtar Ansari | Md. Shamim Ahmad | Handed over | Chaitanya Project consultancy pvt. Ltd | 4th ra
4 | NAWADA | CHC AT PHC NARDIGANJ (NAWADA) | 369.37 | 2014-09-03 | Arun Deo Kumar, Nalanda | 343.2544 | 2015-09-09 | 2016-09-08 | Completed | 100% | 336.0447 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over | Arch- en-Design, Lucknow | 5th ra
5 | JEHANABAD | CHC AT PHC HULASGANJ (JEHANABAD) | 369.37 | 2014-09-03 | M/S Om Sai construction, Jehanabad | 316.8986 | 2015-08-31 | 2016-08-30 | Completed | 100% | 336.0447 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over | Shiva consultancy services pvt ltd | 4th ra
6 | SUPAUL | CHC AT SARAIGARH BHAPTIYAHI (SUPAUL) | 369.37 | 2014-09-03 | Indra Narayan Singh Contract pvt ltd, Patna | 352.8981 | 2016-04-28 | 2017-04-27 | Completed | 100% | 370.72 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over | SGS India pvt ltd, Maharashtra | 7th ra
7 | BHAGALPUR | CHC AT ISMAILPUR (BHAGALPUR) | 369.37 | 2014-09-03 | Pankaj construction | 404.5614 | 2016-06-08 | 2017-06-07 | Completed | 100% | 356.49 | Sri Anil Kumar | Sri Sanjeev Ranjan |  | SGS India pvt ltd, Maharashtra | 2nd ra | G+1
8 | SITAMARHI | CHC AT BOKHRA (SITAMARHI) | 369.37 | 2014-09-03 | Sanjay Kumar | 336.2289 | 2016-05-12 | 2017-05-11 | Completed | 100% | 310.84 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over | Chaitanya Project consultancy | 4th ra
9 | SAMASTIPUR | CHC AT MOHANPUR (SAMASTIPUR) | 369.37 | 2014-09-03 | Vinesh Kumar | 324.5352 | 2016-05-12 | 2017-05-11 | Finishing work is in progrerss | 80% | 230.29 | Sri Sunil Kumar | Md. Shamim Ahmed |  | Dynamic
10 | SAMASTIPUR | CHC AT KHANPUR (SAMASTIPUR) | 369.37 | 2014-09-03 | M/S Shyam babu Chaudhary | 322.4152 | 2016-05-12 | 2017-05-11 | Finishing work is in progrerss | 65% | 165.8 | Sri Sunil Kumar | Md. Shamim Ahmed | Land available on May-2017 | Dynamic
11 | VAISHALI | CHC AT PHC BHAGWANPUR (VAISHALI) | 369.37 | 2014-09-03 | Nagendra Mishra, Muzaffarpur | 327.0614 | 2016-08-22 | 2017-08-21 | Completed | 100% | 282.18 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over | Amulya Traders | 2nd ra
12 | SIWAN | CHC AT PHC HASANPURA (SIWAN) | 369.37 | 2014-09-03 | Asiana contract pvt ltd, Gopalganj | 310.537 | 2015-08-31 | 2016-08-30 | Completed | 100% | 159.71 | Sri Sagar Jaiswal | Md. Shamim Ahmad | Handed over | K&J projects pvt ltd, Nagpur | 2nd ra
13 | GOPALGANJ | CHC AT PHC THAWE (GOPALGANJ) | 369.37 | 2014-09-03 | G.M Construction, Siwan | 330.1727 | 2015-08-31 | 2016-08-30 | Completed | 100% | 265.2 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over | K&J projects pvt ltd, Nagpur
14 | GAYA | CHC AT PHC MOHRA (GAYA) | 369.37 | 2014-09-03 | Mohan Sharma, Gaya | 315.1639 | 2016-11-14 | 2017-11-13 | Completed | 100% | 315.1639 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over | Shiva consultancy services pvt ltd | 1st ra
15 | SAMASTIPUR | CHC AT BITHAN (SAMASTIPUR) | 369.37 | 2014-09-03 | M/S Surendra Prasad Singh, Begusarai | 341.2774 | 2017-03-06 | 2018-03-05 | Completed | 100% | 341.27 | Sri Sunil Kumar | Md. Shamim Ahmed | Handed over | Dynamic
16 | MADHUBANI | CHC AT KALUAHI (MADHUBANI) | 369.37 | 2014-09-03 | Abhay kumar Singh, Sitamarhi | 323.463 | 2017-02-17 | 2018-02-16 | Finishing work is in progress | 95% | 161.23 | Sri Sunil Kumar | Md. Shamim Ahmad |  | Dynamic
17 | ARWAL | CHC AT KALER (ARWAL) | 369.37 | 2014-09-03 | B.M Construction, Jehanabad | 330.5846 | 2017-10-16 | 2018-10-15 | Finishing work is in progress | 75% | 264.35 | Sri Sandeep Kumar | Sri Sanjeev Ranjan |  | Shiva consultancy services pvt ltd
18 | SAHARSA | CHC AT SATAR KATAIYA (SAHARSA) | 369.37 | 2014-09-03 | M/S R. K. Construction, Begusarai | 382.8534 | 2016-10-31 | 2017-10-30 | Completed | 100% | 335 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over | M/S SGS india pvt ltd | 2nd ra
19 | NAWADA | CHC AT KASHICHAK (NAWADA) | 369.37 | 2014-09-03 | Avani Devcon pvt ltd, Patna | 300.6933 | 2017-02-13 | 2018-02-12 | Completed | 100% | 194.92 | Sri Pankaj Kumar | Sri Sanjeev Ranjan |  | Arch- en-Design, Lucknow | 1st RA
20 | MUZAFFARPUR | CHC AT BANDRA (MUZAFFARPUR) | 369.37 | 2014-09-03 | Nalin Ranjan | 297.0852 | 2016-12-27 | 2017-12-26 | Plaster work is in progress | 70% | 0 | Sri Vikash Jha | Sri Sanjeev Ranjan | Land available on Aug'18 | Chaitanya Projects
21 | SIWAN | CHC AT LAKRI NABIGANJ (SIWAN) | 369.37 | 2014-09-03 | Asiana contract pvt ltd, Gopalganj | 316.7612 | 2016-08-11 | 2017-08-10 | Completed | 100% | 235.43 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over | K&J projects pvt ltd, Nagpur | 2ND RA |  | Asiana contract pvt ltd, Rajendra Nagar Gopalganj-841428
22 | JAMUI | CHC AT HARLALNAGAR,ALIGANJ (JAMUI) | 369.37 | 2014-09-03 | A.K Construction | 289.6844 | 2016-06-08 | 2017-06-07 | Finishing work is in progrerss | 77% | 240.29 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Land available on Nov-16 | M/S SGS india pvt ltd | 2ND RA
23 | DARBHANGA | CHC AT HANUMAN NAGAR (DARBHANGA) | 369.37 | 2014-09-03 | Sanjay Kumar | 335.7558 | 2017-03-06 | 2018-03-05 | Completed | 100% | 236.09 | Sri Sunil Kumar | Sri Rajendra Prasad Singh |  | Dynamic
24 | KATIHAR | CHC AT SAMAILI (KATIHAR) | 369.37 | 2014-09-03 | M/S C.S Construction | 350.8302 | 2016-09-08 | 2017-09-07 | Finishing work is in progrerss | 80% | 233.74 | Sri Shashi Shekhar | Md. Shamim Ahmad |  | Shiva consultancy services pvt ltd | 4th RA
25 | KATIHAR | CHC AT MANSAHI (KATIHAR) | 369.37 | 2014-09-03 | M/S C.S Construction | 339.4581 | 2016-09-08 | 2017-09-07 | Finishing work is in progrerss | 75% | 260.04 | Sri Shashi Shekhar | Md. Shamim Ahmad |  | M/S SGS india pvt ltd | 1st RA
26 | SHEOHAR | CHC AT DUGRI KATHSARI (SHEOHAR) | 369.37 | 2014-09-03 | Sri Ashok Kumar Singh, Sitamarhi | 337.1786 | 2017-02-17 | 2018-02-16 | Roof shuttering (2nd .F) | 15% | 170 | Sri Pankaj Kumar | Sri Sanjeev Ranjan |  | Chaitanya projects
27 | GAYA | CHC AT BANKEBAZAR (GAYA) | 369.37 | 2014-09-03 | Kishor Kumar Singh, Aurangabad | 354.3128 | 2016-10-07 | 2017-10-06 | Completed | 100% | 308.4399 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over | Shiva consultancy services pvt ltd
28 | MADHEPURA | CHC AT PURAINI (MADHEPURA) | 369.37 | 2014-09-03 | Topline Infra Projects pvt ltd, Kolkata | 357.3348 | 2016-12-27 | 2017-12-26 | Completed | 100% | 434.66 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed over | M/S SGS india pvt ltd | 2nd RA
29 | SITAMARHI | CHC AT SUPPI (SITAMARHI) | 369.37 | 2014-09-03 | Sri Sanjeev Kumar, Patna | 326.8855 | 2018-05-17 | 2019-05-16 | Finishing work is going on | 70% | 90 | Sri Pankaj Kumar | Sri Sanjeev Ranjan |  | Mars Planning
30 | JEHANABAD | CHC AT RATNIFARIDPUR (JAHANABAD) | 369.37 | 2014-09-03 | Sri Nripendra Kumar Sinha, Patna | 289.928 | 2017-08-18 | 2018-08-17 | Finishing work is in progress | 95% | 172.19 | Sri Sandeep Kumar | Sri Sanjeev Ranjan |  | Shiva consultancy services pvt ltd
31 | MADHEPURA | CHC AT GWALPARA (MADHEPURA) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 385.2323 | 2017-02-17 | 2018-02-16 | Completed | 100% | 398.25 | Sri Sunil Kumar | Sri Rajendra Prasad Singh |  | M/S SGS india pvt ltd | 2nd RA
32 | SUPAUL | CHC AT PRATAPGANJ (SUPAUL) | 369.37 | 2014-09-03 | Indra Narayan Singh Contract pvt ltd, Patna | 366.6581 | 2017-02-17 | 2018-02-16 | Completed | 100% | 270.45 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over | M/S SGS india pvt ltd
33 | BHAGALPUR | CHC AT RANGRACHOWK (BHAGALPUR) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 359.1162 | 2017-01-13 | 2018-01-12 | Completed | 100% | 359.79 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over | M/S SGS india pvt ltd
34 | MADHUBANI | CHC AT LAKHNAUR (MADHUBANI) | 369.37 | 2014-09-03 | Mother India const. pvt ltd | 360.4508 | 2017-03-20 | 2018-03-19 | Finishing work is going on | 65% | 145.24 | Sri Sunil Kumar | Md. Shamim Ahmad |  | Dynamic
35 | SITAMARHI | CHC AT CHORAUT (SITAMARHI) | 369.37 | 2014-09-03 | Mother India const. pvt ltd | 334.7301 | 2017-07-20 | 2018-07-19 | Finishing work is going on | 95% | 329 | Sri Pankaj Kumar | Sri Sanjeev Ranjan |  | Chaitanya Projects
36 | MADHEPURA | CHC AT BIHARIGANJ (MADHEPURA) | 369.37 | 2014-09-03 | Trimurti Engicon & Traders Pvt. Ltd, Patna | 388.3457 | 2017-02-17 | 2018-02-16 | Completed | 100% | 231.53 | Sri Sunil Kumar | Sri Rajendra Prasad Singh |  | M/S SGS india pvt ltd
37 | NAWADA | CHC AT MESKAUR (NAWADA) | 369.37 | 2014-09-03 | Archana Contractor pvt ltd | 307.1294 | 2017-07-14 | 2018-07-13 | Plinth Level | 15% | 46 | Sri Sandeep Kumar | Sri Sanjeev Ranjan |  | Arch- en-Design, Lucknow
38 | KATIHAR | CHC AT DANDKHORA (KATIHAR) | 369.37 | 2014-09-03 | Bambam Kumar Singh | 343.7676 | 2017-05-15 | 2018-05-14 | Completed | 100% | 353.36 | Sri Shashi Shekhar | Md. Shamim Ahmad |  | M/S SGS india pvt ltd
[5 empty] | Total | [5 empty] | 9909.8533

## PHC TO CHC (Single) (2)
PHC TO CHC (30 BEDDED) (Individual)
SL NO | Name of work | A.A. RECEIVED FROM | A.A Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) |  | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects | Not Started Projects |  | REMARKS
1 | Construction of PHC to CHC | Health Dept. | 8386.7567 | 0 |  | 4511.1789 | 15 | 12 | 2 | 1 |  | Balmikinagar- Land not available
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT (Rs in lakh) | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT (IN RS. LAKH) | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  |  |  |  | STAGE | %
1 | MADHUBANI | CHC ARARIA SANGRARM,BLOCK-JHANJHARPUR | 476 | 2014-02-28 | M/S Dhramnath construction, Madhubani | 388.34 | 2015-08-11 | 2016-08-10 | Completed | 100% | 339.5805 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
2 | NAWADA | CHC KHANWA, | 476 | 2014-02-28 | Sri Bipin Kumar, Nawada | 345.2 | 2015-08-28 | 2016-08-27 | Completed | 100% | 279.15 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
3 | PATNA | CHC PHULWARISARIFF, | 543.23 | 2015-02-06 | M/S B.Prasad & Company, Patna | 439.04 | 2015-12-15 | 2016-12-14 | Completed | 100% | 493.04 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
4 | Gopalganj | CHC AT PAKRI, BLOCK- SIDHWALIA | 577.1179 | 0 | M/S Cohesive Infrastructure Pvt. Ltd, Patna | 318.86 | 2015-09-09 | 2016-08-09 | Completed | 100% | 294.272 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed Over
5 | DARBHANGA | CHC ALINAGAR, BLOCK-ALINAGAR | 577.1179 | 2015-03-31 | Sanjay Kumar, Darbhanga | 502.5476 | 2016-09-06 | 2017-09-05 | Completed | 100% | 473.83 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
6 | PATNA | CHC AT BAKHTIYARPUR, | 577.1179 | 2015-07-21 | Prasad Associates, Ranchi | 413.1895 | 2016-06-16 | 2017-06-15 | Completed | 100% | 424.11 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed Over
7 | JAHANABAD | CHC SHAKURABAD, BLOCK-RATNIFARIDPUR | 577.1179 | 2014-11-24 | Mukesh Kumar, Gaya | 345.2113 | 2016-06-08 | 2017-06-07 | Completed | 100% | 332.89 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
8 | SUPAUL | CHC BALUA BAJAR, BLOCK-CHHATAPUR, | 577.1179 | 2014-11-24 | INCPL, Patna | 417.2285 | 2016-07-06 | 2017-07-05 | Completed | 100% | 407.39 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Handed Over
9 | GAYA | CHC MAHKAR, BLOCK-KHIZIRSARAI | 577.1179 | 2014-11-24 | Kaushlendra Kumar, Jehanabad | 368.0233 | 2016-07-20 | 2017-07-19 | Completed | 100% | 407.9264 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
10 | W. CHAMPARAN | CHC BALMIKINAGAR BAGHA-2, DIST-WEST CHAMPARAN | 543.23 | 2014-11-24 | Maa Vindhyavasini construction, W. Champaran | 389.1026 | - | - | Not started | - | 0 | Sri Sagar Jaiswal | Md. Shamim Ahmad | Land not available
11 | SARAN | CHC ISUAPUR, DIST-SARAN | 577.1179 | 2015-08-05 | Yashaswi Infrastructure pvt ltd | 491.5484 | 2018-01-04 | 2019-01-03 | Completed | 100% | 458 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed Over
12 | NALANDA | CHC ISLAMPUR, Dist-NALANDA | 577.1179 | 2015-08-05 | M/S B.Prasad & Company, Patna | 439.2971 | 2016-09-06 | 2017-09-05 | Completed | 100% | 373.12 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
13 | MUZAFFARPUR | CHC MUSHARI, DIST- MUZAFFARPUR | 577.1179 | 2015-08-05 | Mohan Prasad Developers & construction pvt ltd | 480.1992 | 2017-03-06 | 2018-03-05 | Completed | 100% | 227.87 | Sri Vikash Jha | Sri Rajendra Prasad Singh
14 | ROHTAS | CHC KOCHAS, BLOCK-KOCHAS | 577.1179 | 2015-06-16 | Sharda Security & Alied Services | 490.9156 | 2019-03-08 | 2020-03-07 | Column work (G.F) | 16% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
15 | ROHTAS | CHC KARGAHAR, BLOCK-KARGAHAR | 577.1179 | 2015-06-16 | M/s Pankaj Construction, Rohtas | 462.5784 | 2019-03-02 | 2020-03-01 | Roof Shuttering (G.F) | 20% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
| Total |  | 8386.7567 |  |  | 6291.2816 |  |  |  |  | 4511.1789

## PHC TO CHC (minority) (2)
PHC TO CHC (30 BEDDED) (Under MSDP)
SL NO | Name of work |  | A.A. Amount (in Rs. Lakh) | Amount Received (in Rs. Lakh) | Expenditure Till Date (in Rs Lakh) | Total no. of Projects | Completed Projects | Ongoing Projects |  | Not Started Projects |  |  | REMARKS
1 | Construction of PHC to CHC (Minority) |  | 11776.25 (471.05 per unit) | 0 | 3019.2421 | 25 | 9 | 5 |  | 8 |  |  | Project Dropped-3 (Barsoi, Manihari, Farbisganj)
Detailed Report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS in lakh) |  |  | STAGE | % | (RS in lakh)
1 | KISHANGANJ | CHC AT DIGHALBANK, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 385.564 | 2016-04-28 | 2017-04-27 | Completed | 100% | 273.54 | Sri Shashi Shekhar | Md. Shamim Ahmad
2 | KISHANGANJ | CHC AT THAKURGANJ, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 386.2479 | 2016-04-28 | 2017-04-27 | Not Started |  | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad | Letter sent to D.M for land
3 | KISHANGANJ | CHC AT BAHADURGANJ, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 381.5506 | 2016-04-28 | 2017-04-27 | Completed | 100% | 266.56 | Sri Shashi Shekhar | Md. Shamim Ahmad | Handed Over
4 | KISHANGANJ | CHC AT KOCHADHAMAN, KISHANGANJ | 471.05 | 2015-04-13 | Shafique Alam | 384.9058 | 2016-04-28 | 2017-04-27 | Completed | 100% | 193.43 | Sri Shashi Shekhar | Md. Shamim Ahmad | Handed Over
5 | ARARIYA | CHC AT PALASI, ARARIYA | 471.05 | 2015-04-13 | Topline Infra | 389.7501 | 2016-04-28 | 2017-04-27 | Completed | 100% | 384 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
6 | KATIHAR | CHC AT AZAMNAGAR, KATIHAR | 471.05 | 2015-04-13 | Pankaj Kumar Singh | 387.1691 | 2016-04-29 | 2017-04-28 | Completed | 100% | 312.0882 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
7 | BHAGALPUR | CHC AT JAGDISHPUR, BHAGALPUR | 471.05 | 2015-04-13 | Balkrishna Bhalotia construction pvt ltd, jamui | 368.774 | 2016-04-28 | 2017-04-27 | Completed | 100% | 360 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
8 | ARARIYA | CHC AT RANIGANJ, ARARIYA | 471.05 | 2015-04-13 | INSCPL | 369.6559 | 2016-07-06 | 2017-07-05 | Completed | 100% | 174.41 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
9 | KATIHAR | CHC AT KADWA, KATIHAR | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.9165 | 2016-06-08 | 2017-06-07 | Completed | 100% | 389.9165 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
10 | KATIHAR | CHC AT BARARI, KATIHAR | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.9071 | 2016-06-08 | 2017-06-07 | Completed | 100% | 389.9071 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed Over
11 | KATIHAR | CHC AT BALRAMPUR, KATIHAR | 471.05 | 2015-04-13 | Birendra Kumar Singh, Katihar | 367.8626 | 2016-05-31 | 2017-05-30 | Roof shuttering (G.F) | 25% | 81.11 | Sri Shashi Shekhar | Md. Shamim Ahmad
12 | ARARIYA | CHC AT SIKTI, ARARIYA | 471.05 | 2015-04-13 | Basant Banijya Limited, Gaya | 379.1134 | 2018-02-27 | 2019-02-26 | Finishing work is in progress | 95% | 61.134 | Sri Shashi Shekhar | Md. Shamim Ahmad
13 | ARARIYA | CHC AT TERHAGACH, ARARIYA | 471.05 | 2015-04-13 | M/S C.S construction | 378.2944 | 2016-09-06 | 2017-09-05 | Column work (G.F) | 20% | 63.7662 | Sri Shashi Shekhar | Md. Shamim Ahmad | work started after demolished the old building
14 | DARBHANGA | CHC AT KIRATPUR, DARBHANGA | 471.05 | 2015-04-13 | Kuwar construction | 352.2968 | 2017-07-15 | 2018-07-14 | Plinth Level | 15% | 0 | Sri Sunil Kumar | Md. Shamim Ahmad
15 | KISHANGANJ | CHC AT POTHIA, KISHANGANJ | 471.05 | 2015-04-13 | Anil Kumar | 369.4717 | 2017-06-02 | 2018-06-01 | Finishing work is in progress | 90% | 69.38 | Sri Shashi Shekhar | Md. Shamim Ahmad | Land made available after Tree cutting on 02 August 2017
16 | KATIHAR | CHC AT HASANGANJ, KATIHAR | 471.05 | 2015-04-13 | Rita Devi | 371.2069 | 2017-07-25 | 2018-07-24 | Not Started | - | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad | Letter sent for land
17 | KATIHAR | CHC AT AMADABAD, KATIHAR | 471.05 | 2015-04-13 | Birendra Kumar Singh, Katihar | 362.0746 | 2016-05-27 | 2017-05-26 | Not Started |  | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad | (Land not available) Letter sent to D.M for land
18 | MADHUBANI | CHC AT MADHUBANI SADAR, MADHUBANI | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.591 | 2016-07-20 | 2017-07-19 | Not Started |  | 0 | Sri Sunil Kumar | Md. Shamim Ahmad | Work will be started after demolished the old building
19 | EAST CHAMPARAN | CHC AT BANJARIA, EAST CHAMPARAN | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Sagar Jaiswal | Md. Shamim Ahmad | In Tender
20 | VAISHALI | CHC AT CHEHRA KALAN, VAISHALI | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Sandeep Kumar | Sri Sanjeev Ranjan | In Tender
21 | ARARIYA | CHC AT JOKIHAT, ARARIYA | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad | In Tender
22 | KATIHAR | CHC AT KATIHAR SADAR, KATIHAR | 471.05 | 2015-04-13 | - | - | - | - | Not Started |  | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad | Land not available (Letter Send to P.S MWD, Bihar vide Letter no-BMSIC/80015/05-2016/959, Dated-21/06/2016
23 | KATIHAR | CHC AT BARSOI, KATIHAR | 471.05 | 2015-04-13 | Satyanarayan Singh, Deoghar | 389.6211 | 2016-06-08 | 2017-06-07 | - | - | - | - | - | Project Dropped
24 | ARARIYA | CHC AT FORBESGANJ, ARARIYA | 471.05 | 2015-04-13 | - | - | - | - | - | - | - | - | - | Project dropped
25 | KATIHAR | CHC AT MANIHARI, KATIHAR | 471.05 | 2015-04-13 | - | - | - | - | - | - | - | - | - | Project dropped
[8 empty] | Total |  |  | 3019.2421

## APHC (2)
ADDITIONAL PRIMARY HEALTH CENTRE (A.P.H.C)
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT (in rs lakh) | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  |  |  |  | STAGE | % | AMOUNT (Rs in lakh)
1 | PATNA | CONSTRUCTION OF APHC IN SAMASTICHAK, PATNA | 75.99 | 2011-03-12 | Pintu Construction, Masaurhi | 68.748 | 2013-04-20 | 2014-01-19 | completed | 100% | 81.4691 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | KAIMUR | CONSTRUCTION OF APHC IN NATAIYA, KAIMUR | 75.99 | 2012-09-18 | Smt Rita Devi | 68.748 | 2013-07-03 | 2014-04-02 | completed | 100% | 88.11 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
5 | GAYA | CONSTRUCTION OF APHC IN MAIN GRAM, GAYA | 75.99 | 2012-10-03 | M/S Rita Devi | 66.4527 | 2013-09-12 | 2014-06-11 | completed | 100% | 79.1999 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
6 | SIWAN | CONSTRUCTION OF APHC NARENDARPUR, SIWAN | 75.99 |  | Jiradei Narendrapur Engineering & Construction Company | 73.6227 | 2013-08-14 | 2014-05-13 | completed | 100% | 80.5457 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
7 | VAISHALI | APHC BHAGWANPURRATI, DIST-VAISHALI (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Synergy thrillingston, chandigarh | - | - | - | completed | 100% | 59 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | CONSTRUCTRED AS MODEL UNDER 100 APHC SANCTIONED BY HEALTH DEPT.
8 | VAISHALI | APHC ROOPNARAYANPUR, BLOCK-JANDAHA, DIST-VAISHALI (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Revirie Ventures Pvt. Ltd, Chhatishgarh | - | - | - | completed | 100% | 69.05 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
9 | PATNA | APHC DATMAI, BLOCK-MASAURHI, DIST-PATNA (BY PREFAB MATERIAL) | 53.15 | 2009-11-06 | Sai Baba Builders & Consultants Pvt. Ltd | - | - | - | completed | 100% | 35.65 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
10 | GAYA | CONSTRUCTION OF APHC AT MAHKAR, BLOCK-KHIZIRISARAI (GAYA) BY PRE-FAB MATERIAL | 112.49 | 2014-06-23 | Acme Cleantech Solutions Ltd,Gurgaon (Haryana) | 84.735 | 2014-08-26 | 2014-11-25 | completed | 100% | 69.55 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
11 | NALANDA | CONSTRUCTION OF APHC AT KACHHARIYA, BLOCK-THARTHARI (NALANDA) BY PRE-FAB MATERIAL | 112.49 | 2014-07-22 | Beardsell ltd. | 93.7837 | 2014-12-29 | 2015-04-28 |  | - | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | (work rescined)
12 | BEGUSARAI | CONSTRUCTION OF APHC AT SONVARSA,SAMHO (BEGUSARAI) | 90.008 | 2014-01-17 | Ramniwas Kumar, Begusarai | 76.4628 | 2015-08-19 | 2016-05-18 | Completed | 100% | 76.46 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Handed over
13 | GOPALGANJ | CONSTRUCTION OF APHC AT SIDHWALIA,GOPALGANJ | 120.66 |  | Bajrangi Singh,Chhapra | 104.9228 | 2015-08-14 | 2016-05-13 | Completed | 100% | 93.8511 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
14 | GOPALGANJ | CONSTRUCTION OF APHC AT BALRA,BARAULI (GOPALGANJ) | 87.05 | 2014-11-10 | Baranwala Contact Pvt. Ltd, Gopalganj | 78.4366 | 2015-08-19 | 2016-02-18 | Completed | 100% | 78.44 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
15 | GOPALGANJ | CONSTRUCTION OF APHC AT REVTITH, BAIKUNTHPUR (GOPALGANJ) | 87.05 | 2014-11-10 | Baranwala Contact Pvt. Ltd, Gopalganj | 77.753 | 2015-08-19 | 2016-02-18 | Completed | 100% | 77.55 | Sri Birendra Purbey | Sri Rajendra Prasad Singh | Handed over
16 | JAHANABAD | APHC AT MURAHARA, BLOCK-RATNIFARIDPUR, DIST-JAHANABAD | 122.347 | 2015-02-04 | Smt Rita Devi, Sasaram | 181.6154 | 2015-09-01 | 2015-06-30 | completed | 100% | 64.0027 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
17 | JAHANABAD | APHC AT AVGILLA, BLOCK-RATNIFARIDPUR, DIST-JAHANABAD | 122.35 | 2015-02-04 |  |  |  |  | completed | 100% | 86.3631 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
18 | ROHTAS | CONSTRUCTION OF APHC AT BARHARI BLOCK-KARGAHAR,DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram | 284.1295 | 2015-08-31 | 2016-05-30 | Completed | 100% | 312 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
19 | ROHTAS | CONSTRUCTION OF APHC AT KOWATH ,BLOCK-DAWATH, DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram |  | 2015-08-31 | 2016-05-30 | completed | 100% |  | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
20 | ROHTAS | CONSTRUCTION OF APHC AT KHAIRHI, BLOCK-DAWATH, DIST-ROHTAS | 120.655 | 2015-02-04 | Sri Rajesh Kumar,Sasaram |  | 2015-08-31 | 2016-05-30 | completed | 100% |  | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
21 | VAISHALI | CONSTRUCTION OF APHC AT SONHO, BLOCK-GOROUL (VAISHALI) | 102.05 |  | Randhir Kumar | 97.3991 | 2015-09-09 | 2016-06-08 | completed | 100% | 97.46 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
22 | NALANDA | CONSTRUCTION OF APHC AT AMBA (NALANDA) | 122.34 |  | Lallu Kumar | 97.4972 | 2016-01-04 | 2016-10-03 | completed | 100% | 96.8593 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
23 | BHAGALPUR | CONSTRUCTION OF APHC AT POTHIA SANHAULA (BHAGALPUR) | 81.309 | 2014-01-27 | Lalan Kumar | 71.13 | 2017-08-18 | 2018-05-17 | Completed | 100% | 35.33 | Sri Anil Kumar | Sri Sanjeev Ranjan
24 | KAIMUR | APHC AT BITHWAR DIST-KAIMUR | 122.34 |  | Kamlesh Kumar Singh | 94.7102 | 2016-05-12 | 2017-05-11 | Completed | 100% | 108 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
25 | PATNA | APHC AT GOPALPUR (MANER) DIST-PATNA | 122.34 |  | Brajesh Kumar | 98.5084 | 2016-03-03 | 2016-12-02 |  |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
26 | JAHANABAD | APHC AT KIYUR, BLOCK-HULASHGANJ, DIST-JEHANABAD | 122.34 | 2015-07-13 | Kaushlendra Kumar | 91.5403 | 2016-10-28 | 2017-07-27 | completed | 100% | 91.54 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
27 | BEGUSARAI | SMRITISHESH PARMESHWARI DEVI APHC AT KESAWE, BARAUNI, DIST-BEGUSARAI | 122.34 |  | Agni Kumar Singh | 109.48 | 2017-05-05 | 2018-02-04 | completed | 100% | 109.48 | Sri Anil Kumar | Sri Rajendra Prasad Singh
28 | BEGUSARAI | APHC AT BAHALPUR (NAYAGAON) MATIHANI, DIST-BEGUSARAI | 90.008 | 2014-01-22 | Ramniwas kumar | 74.9338 | 2017-03-24 | 2017-12-23 | completed | 100% | 73.2588 | Sri Rajendra Prasad Singh | Sri Rajendra Prasad Singh
29 | PATNA | APHC SAKSOHRA AT BELCHI, DIST-PATNA | 114.7 |  | M/s Devendra Prasad Singh | 120.3879 | 2017-05-05 | 2018-03-04 | completed | 100% | 71.41 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
30 | MUNGER | APHC AT BANGALWA, DIST-MUNGER | 122.49 | 2014-02-28 | P PRAKASH CONT. | 104.6441 |  |  |  |  | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Land not Available
31 | MUNGER | APHC AT GHATWARI, DIST-MUNGER | 122.49 | 2014-02-28 | P PRAKASH CONT. | 99.1267 | 2017-02-22 | 2017-11-21 |  |  | 0 | Sri Anil Kumar | Sri Rajendra Prasad Singh | Land not available
32 | VAISHALI | APHC AT MADARNA DIST-VAISHALI | 102.05 | 2014-09-02 | Rohit Raj Construction, Patna | 96.6814 | 2016-08-11 | 2017-05-10 | completed | 100% | 99.69 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
33 | MADHUBANI | APHC AT BHAIRAVSTHAN BLOCK-JHANJHARPUR, DIST-MADHUBANI | 114.07 | 2015-02-09 | M/S Delta Enterprises | 102.7246 | 2017-02-22 | 2017-11-21 | completed | 100% | 86.93 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
34 | BEGUSARAI | APHC AT SIHMA, BLOCK-MATIHANI DIST-BEGUSARAI | 122.34 |  | M/S Surendra Prasad Singh, Begusarai | 103.5026 | 2017-02-17 | 2017-11-16 | completed | 100% | 103.5 | Sri Anil Kumar | Sri Rajendra Prasad Singh
35 | SAMASTIPUR | APHC AT DEVDHA, (HASANPUR) DIST-SAMASTIPUR | 122.34 | 2015-02-03 | [7 empty] | Sri Sunil Kumar | Sri Rajendra Prasad Singh
36 | MADHUBANI | APHC AT BASAITH, BLOCK-BENIPATTI (MADHUBANI) | 122.34 | 2016-02-09 | Tufail Ahmed Khan const. pvt ltd | 98.1208 | 2017-05-05 | 2018-02-04 | completed | 100% | 106.8118 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
37 | MADHUBANI | APHC AT NAWANI, BLOCK-JHANJHARPUR, DIST-MADHUBANI | 126.97 | 2016-08-29 | Regal Infratrading Pvt. Ltd., Patna | 126.1928 | 2017-02-08 | 2017-11-07 | Roof casted (F.F) | 50% | 31.448 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
38 | MADHUBANI | APHC AT BHAUR, BLOCK-PANDAUL, DIST-MADHUBANI | 122.34 | 2016-08-29 | MDS Infranirman Pvt ltd, Patna | 105.3907 | 2017-07-15 | 2018-04-14 | Roof casted(G.F) | 35% | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
39 | ARWAL | APHC AT LARI, BLOCK-KURTHA, DIST-ARWAL | 122.34 | 2017-01-18 | Praveen Kumar, Jehanabad | 124.5004 | 2017-09-21 | 2018-06-20 | Finishing work | 90% | 40.49 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
40 | MADHUBANI | APHC AT MOHAN BARIYAM,NARPAT NAGAR , BLOCK-PANDAUL, DIST-MADHUBANI | 0 |  | Shaurya Premiere Infrastructure pvt ltd, Patna | 106.95 | 2017-10-06 | 2017-07-05 | Brick work completed | 45% | 27.85 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
41 | WEST CHAMPARAN | APHC AT PATILAR, DIST-WEST CHAMPARAN | 0 | 2016-05-05 | Anil Kumar Mishra | 105.1289 | 2018-02-02 | 2018-09-01 | completed | 100% | 56.77 | Sri Sagar Jaiswal | -
42 | SIWAN | APHC AT NANDA MUNDA, BLOCK-SISWAN, DIST-SIWAN | 126.97 | 2016-09-20 | Pratap Construction, New Delhi | 102.58 |  |  | Tie Beam | 12% |  | Sri Sagar Jaiswal
43 | SIWAN | APHC AT JAMO BLOCK-GORIYAKOTHI, DIST-SIWAN | 122.34 | 2017-09-05 | Savitri Technocrate Pvt Ltd, Gopalganj | 102.5817 | 2018-02-13 | 2019-11-12 | Brick work completed | 45% |  | Sri Sagar Jaiswal
44 | NALANDA | CONSTRUCTION OF APHC AT HUSAINPUR, BLOCK-RAHUI (NALANDA) | 122.34 |  | R.K Infraservices | 98.775 | 2018-05-17 | 2019-02-16 | Brick work completed | 65% | 63 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
45 | DARBHANGA | CONSTRUCTION OF APHC JAMALPUR, BLOCK-KIRATPUR | 127.2842 | 2016-12-09 | Rampukar Yadav | 104.0309 | [7 empty] | LOA to be issued
46 | JAHANABAD | APHC AT ANANTPUR, BLOCK-MODANGANJ, DIST-JEHANABAD | 122.34 | 2016-03-21 | Rohit Raj Construction, Patna | 98.9155 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 30/05/2018 (Land not available)
47 | JAHANABAD | APHC AT SUGAON, BLOCK-MAKHDUMPUR, DIST-JEHANABAD | 122.34 |  | Praveen Kumar, Jehanabad | 98.9155 | 2018-11-17 | 9 Months. | Foundation work | 5% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
48 | JAHANABAD | APHC AT BAJITPUR, BLOCK-GHOSHI, DIST-JEHANABAD | 122.34 |  | Praveen Kumar, Jehanabad | 98.9155 | 2018-11-17 | 9 Months. | Foundation work | 2% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
49 | SAMASTIPUR | CONSTRUCTION OF APHC AT DARWA, BLOCK-MORWA,SAMASTIPUR | 122.34 |  | M/S Gautam Construction | 137.9109 |  |  | Foundation work |  |  | Sri Sunil Kumar | Md. Shamim Ahmed
50 | PATNA | APHC AT SIGORI, BLOCK- PALIGANJ, DIST-PATNA | 122.34 |  | Praveen Kumar, Jehanabad | 102.0941 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 30/05/2018
51 | VAISHALI | APHC AT SHAMBHUPUR KWARI | 122.34 |  | R.N group of company | 102.894 | 2018-07-09 | 2019-04-08 | Plaster work | 65% | 32.01 | Sri sandeep Kumar
51 | MUZAFFARPUR | APHC AT RAIPUR MAHADEVA, BLOCK-SARAIYA |  |  | Sanjeev Sharma | 136.5831 | [5 empty] | Sri Vikash Jha | Sri Sanjeev Ranjan | LOA issued on …./01/2019
51 | NALANDA | APHC AT KHUDAGANJ, BLOCK-ISLAMPUR | 122.34 |  | Lallu Kumar | 132.9522 |  |  | Not started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on …./01/2019
51 | WEST CHAMPARAN | APHC ATLAURIYA, BLOCK-LAURIYA |  |  | Sakal Deo Mishra | 145 | 2018-11-17 | 2019-08-16 | Tie Beam | 10% |  | Sri Sagar Jaiswal
51 | SAHARSA | APHC AT ARAN | [6 empty] | Column work (G.F) | 20%
|  | SUBTOTAL | 4251.007 | [7 empty] | 1831.675

## APHC 23 SHS
ADDITIONAL PRIMARY HEALTH CENTRE (A.P.H.C) as on 25.02.2019
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | No of Projects |  | In Tender Stage |  | Total no. of Projects | Tender Finalized | Ongoing Projects | Not Started | Remarks
1 | Construction of APHC |  | 2927.54 (127.28 per unit) | 23 |  | 1 (Kiyajori) |  | 23 | 22 | 12 | 8 | Bhairavsthan- Completed, Kaliyaganj- Project cancelled
Detailed report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | UP TO DATE PAYMENT | PHYSICAL |  | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | AMOUNT (in lakh) | STAGE | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Arariya | CONSTRUCTION OF APHC KALIYAGANJ, BLOCK-PALASI | 127.2842 | 2016-12-09 | Dinesh Kumar | 106.9385 |  |  |  | Not started | - | According to C.S building already constructed. Hence project cancelled
2 | Aurangabad | CONSTRUCTION OF APHC BANDEYA, BLOCK-GOHA | 127.2842 | 2016-12-09 | Urveshi Construction | 107.753 | 2018-01-06 | 2018-09-05 | - | Plinth Level | 15% | Land availabe on 10.12.2018
3 | East Champaran | CONSTRUCTION OF APHC DHILIYA BAJAR, BLOCK-KESHARIYA | 127.2842 | 2016-12-09 | Rana Construction | 106.9668 | 2018-08-14 | 2019-05-13 |  | Not Started | 0% | Land not available, Letter sent to CS vide letter no-2984 & 2497 dated-31.08.2018 & 29.09.2018 respectively
4 | Gaya | CONSTRUCTION OF APHC JAMUARA, BLOCK-TEKARI | 127.2842 | 2016-12-09 | Mukesh Kumar | 103.94 |  |  |  | Not Started |  | Land not available, Letter sent to CS vide letter no-5184, 2892, 1188 dated-28.01.2019, 26.09.2018, 20.06.2018 respectively
5 | Gaya | CONSTRUCTION OF APHC TAJPUR, BLOCK-KHIJARSARAI | 127.2842 | 2016-12-09 | Lallu Kumar | 101.9 |  |  |  | Not Started |  | Land not available, Letter sent to CS vide letter no-1187, 2939, 4084, 5183 dated-20.06.2018, 27.09.2018, 29.11.2018, 28.01.2019 respectively
6 | Jamui | CONSTRUCTION OF APHC KIYAJORI, BLOCK-CHAKAI | 127.2842 | 2016-12-09 | [5 empty] | Not Started |  | Retender to be invited
7 | Katihar | CONSTRUCTION OF APHC CHOWKI, BLOCK-KADWA | 127.2842 | 2016-12-09 | Pradeep Kumar Singh | 106.9593 |  |  |  | Not Started |  | Land not available
8 | Nalanda | CONSTRUCTION OF APHC SAIDPUR, BLOCK-BEN | 127.2842 | 2016-12-09 | A.K Choudhary | 101.7817 | 2019-03-02 | 2019-12-01 |  | Foundation work | 10%
9 | Purnea | CONSTRUCTION OF APHC DAMAILI, BLOCK-DHAMDAHA | 127.2842 | 2016-12-09 | Sona Infrastructure | 105.18 |  |  |  | Not Started |  | Work order to be issued
10 | Saharsa | CONSTRUCTION OF APHC SONPUR, BLOCK-SIMRI BAKHTIYARPUR | 127.2842 | 2016-12-09 | Narayan Prasad Singh | 105.8102 |  |  | 24 | Finishing work | 65%
11 | Saharsa | CONSTRUCTION OF APHC BIHARA, BLOCK-PANCHGACHIYA / SATARKATAIYA | 127.2842 | 2016-12-09 | Narayan Prasad Singh | 105.8102 |  |  | 23 | Brick work | 30%
12 | Sheikhpura | CONSTRUCTION OF APHC BERMA, BLOCK-SHEIKHPURA | 127.2842 | 2016-12-09 | Sanjay Kumar Technocrate | 103.381 | 2018-05-30 | 02/29/2019 | 54.95 | Finishing work | 80%
13 | Sheikhpura | CONSTRUCTION OF APHC BIMAN, BLOCK-ARIYARI | 127.2842 | 2016-12-09 | Shambhu Yadav, Jamui | 103.3809 | 2018-06-29 | 2019-03-28 | 24.65 | Finishing work | 75%
14 | Sheikhpura | CONSTRUCTION OF APHC BHADAUS, BLOCK-GHATKUSUMBA | 127.2842 | 2016-12-09 | Lallu Kumar | 103.3809 | 2018-08-31 | 2019-05-30 | 0 | Column work (G.F.) | 20%
15 | Sheikhpura | CONSTRUCTION OF APHC GAGRI, BLOCK-SHEIKHPURA | 127.2842 | 2016-12-09 | Sanjay Kumar Technocrate | 103.3809 | 2018-05-30 | 02/29/2019 | 54.88 | Finishing work | 75%
16 | Sheohar | CONSTRUCTION OF APHC RAMBAN, BLOCK-DUMRI KATHSARI | 127.2842 | 2016-12-09 | Md. Nabi | 103.3809 |  |  |  | Not Started |  | T.s in progress
17 | Sitamarhi | CONSTRUCTION OF APHC RASALPUR, BLOCK-BAJPATTI | 127.2842 | 2016-12-09 | Bharti Construction | 105.9087 |  |  |  | Roof casted(G.F.) | 30%
18 | Supaul | CONSTRUCTION OF APHC BAJIDPUR, BLOCK-TRIVENIGANJ | 127.2842 | 2016-12-09 | Pradeep Kumar Singh | 106.579 | 2018-06-01 | 2019-03-30 | 22 | Brick work | 30%
19 | Supaul | CONSTRUCTION OF APHC CHANDPIPAR, BLOCK-SARAIGARH-BHAPTIYAHI | 127.2842 | 2016-12-09 | Dhiraj Kumar Agarwal, Supaul | 106.579 | 2018-05-30 | 2019-02-28 | 48 | Completed | 100%
20 | Supaul | CONSTRUCTION OF APHC KHAKHAI, BLOCK-KISHANPUR | 127.2842 | 2016-12-09 | Md. Ziaul khan | 106.57 |  |  |  | Not Started |  | Old building available on proposed site
21 | Madhubani | CONSTRUCTION OF APHC MOHAN BARIYAM, BLOCK-NARPATNAGAR | 127.2842 | 2016-12-09 | Shaurya Premiere Infrastructure pvt ltd, Patna | 106.95 |  |  |  | Finishing work | 92%
22 | Kishanganj | CONSTRUCTION OF APHC BUALDAH, BLOCK-KOCHADHAMAN | 127.2842 | 2016-12-09 | Shankara Construction | 103.18 |  |  |  | Finishing work | 90% | Being constructed by MSDP
23 | Madhubani | CONSTRUCTION OF APHC BHAIRVSTHAN, BLOCK-JHANJHARPUR | 127.2842 | 2016-12-09 | M/S Delta Enterprises | 102.7246 |  |  |  | Completed | 100% | Constructed by Health Deptt.
|  | Total | 2927.5357

## APHC (MSDP)1 (2)
CONSTRUCTION OF ADDITIONAL PRIMARY HEALTH CENTRE (MSDP)
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS in Lakh) |  |  | STAGE | % | AMOUNT (RS in Lakh)
1 | Darbhanga | Brahmpur (Darbhanga) | 124.31 |  | C.G.G construction | 303.0228 | 2016-02-17 | 2017-02-16 | Completed | 100% | 52.8841 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
2 | Darbhanga | Kamtaul (Darbhanga) | 124.31 |  |  |  | 2016-02-17 | 2017-02-16 | Completed | 100% | 47.6674 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
3 | Darbhanga | Sarwara (Darbhanga) | 124.31 |  |  |  | 2016-02-17 | 2017-02-16 | Finishing work is going on | 70% | 21.7282 | Sri Sunil Kumar | Md. Shamim Ahmad
4 | Katihar | Morsanda (katihar) | 124.31 |  | B.K Singh | 299.5476 | 2016-06-08 | 2017-06-07 | Brick work isgoing on | 55% | 38 | Sri Shashi Shekhar | Md. Shamim Ahmad
5 | Katihar | Bharwara (katihar) | 124.31 |  |  |  | 2016-06-08 | 2017-06-07 | Finishing work is in progress | 80% | 73 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
6 | Katihar | Surjapur (katihar) | 124.31 |  |  |  | 2016-06-08 | 2017-06-07 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
7 | West Champaran | Gokhula (West Champaran) | 124.31 |  | Sharda chandel contract pvt ltd. | 194.8329 | 2016-04-11 | 2017-04-10 | Finishing work is in progress | 92% | 105.3268 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
8 | West champaran | Dumaria (West Champaran) | 124.31 |  |  |  | 2016-04-11 | 2017-04-10 | Finishing work is in progress | 92% |  | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
9 | Kishanganj | Kalpeer, Tedhagach (Kishanganj) | 124.31 |  | M/S Shankar Construction, Begusarai | 101.5409 | 2016-12-27 | 2017-09-26 | Not Started |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
10 | Kishanganj | Bual Dah, Block- Kochadhaman (Kishanganj) | 124.31 |  | M/S Shankara Construction, Begusarai | 206.3582 | 2016-12-27 | 2017-09-26 | Finishing work is in progress | 95% | 89.4377 | Sri Shashi Shekhar
11 | Kishanganj | Maudha, Block- Kochadhaman (Kishanganj) | 124.31 |  |  |  | 2016-12-27 | 2017-09-26 | Column work (G.F) | 25% | 0 | Sri Shashi Shekhar
12 | Supaul | Deenbandhu, Basantpur (Supaul) | 124.31 |  | Mahendra Kumar Mishra | 96.677 |  |  |  |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
13 | Kishanganj | chichubadi, Kasba-Kaliyaganj , Block- Pothia (Kishanganj) | 124.31 |  | Sri Narayan Mandal, Katihar | 205.0883 | 2017-01-13 | 2017-10-12 | Plaster work is in progress | 60% | 57.34 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
14 | Kishanganj | Tipijhari Magurjohn , Block- Pothia (Kishanganj) | 124.31 |  |  |  | 2017-01-13 | 2017-10-12 | - | - | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
15 | Purnea | Abdullah Nagar (Purnea) | 124.31 |  | Rana pratap Singh | 97.7068 | 2017-10-09 | 2018-07-08 | Finishing work is in progress | 90% | 66.57 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
16 | Madhubani | Loha,Kaluahi (Madhubani) | 124.31 |  | M/S Dayaram Singh | 99.6446 | - | - | Not Started |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | (Land not available)
17 | East Champaran | Karsahiya, Barharwa Lakhansen, (Dhaka E. Champaran) | 124.31 |  | Vikash Kumar Gupta | 209.1866 | 2017-07-20 | 2018-04-19 | Karsahiya-Plinth Level Barharwa Lakhansen- Finishing work is in progress | 35% | 22.2955 | Sri Sagar Jaiswal | -
18 | Kishanganj | Powakhali Thakurganj (Kishanganj) | 124.31 |  | Sudesh Kumar Singh &co. construction pvt ltd, jamui | 97.2558 | 2017-02-17 | 2017-11-16 | Finishing is in progress | 85% | 57.82 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
19 | Sitamarhi | Bajpatti Got Abidpur (Sitamarhi) | 124.31 | [7 empty] | 0 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Retender to be invited
20 | Darbhanga | Harihath, Block- Alinagar (Darbhanga) | 124.31 |  | Girdhari Lal Poddar | 312.8027 | 2017-03-06 | 2018-03-05 | Not Started |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
21 | Darbhanga | Garaul, Block- Alinagar (Darbhanga) | 124.31 |  | Girdhari Lal Poddar |  | 2017-03-06 | 2018-03-05 | Not Started |  | 0 | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
22 | Darbhanga | Narman, Block- Alinagar (Darbhanga) | 124.31 |  | Girdhari Lal Poddar |  | 2017-03-06 | 2018-03-05 | Completed | 100% | 36.23 | Sri Sunil Kumar | Sri Rajendra Prasad Singh
23 | Kishanganj | Dhangada, Block-Dighalbank (Kishanganj) | 124.31 |  | Anil Kumar | 207.3475 | 2017-01-13 | 2017-10-12 | Finishing work work is in progress. | 90% | 205.88 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
24 | Kishanganj | Baruamani Garnchavdaga, Block-Dighalbank (Kishanganj) | 124.31 |  | Anil Kumar |  |  |  | Finishing work work is in progress. | 90% | 63.65 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
25 | Kishanganj | Kadogaon, Block-Thakurganj (Kishanganj) | 124.31 |  | Sudesh Kumar Singh &co. construction pvt ltd, jamui | 97.25 | 2017-02-17 | 2017-11-16 |  |  | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
26 | Kishanganj | Budhnayi, Block-Pothia (Kishanganj) | 124.31 |  | Sudesh Kumar Singh &co. construction pvt ltd, jamui | 193.9464 | 2017-01-13 | 2017-10-12 | Completed | 100% | 99.58 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
27 | Kishanganj | Fala Tarni Block-Pothia (Kishanganj) | 124.31 |  |  |  | 2017-01-13 | 2017-10-12 | Completed | 100% | 100.38 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
28 | Banka | Pardhadi, Dhuria (Banka) | 124.31 |  | Lalan Kumar | 89.5481 |  |  |  |  | 0 | Sri Anil Kumar | Sri Sanjeev Ranjan | T.S in process
29 | Darbhanga | Jamalpur, Block-Kiratpur (Darbhanga) | 124.31 | 2017-02-06 | Ram Pukar Yadav, Darbhanga | 103.2393 | [5 empty] | Sri Sunil Kumar | Sri Rajendra Prasad Singh
30 | Darbhanga | Manighachhi, Block-Manigachhi (Darbhanga) | 124.31 | 2017-02-06 | Mother India Construction Pvt. Ltd., |  |  |  | Roof shuttering (G.F) | 25% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
31 | Darbhanga | Nehra, Block-Manigachhi (Darbhanga) | 124.31 | 2017-02-06 | Mother India Construction Pvt. Ltd., | 103.8815 | [5 empty] | Sri Sunil Kumar | Sri Rajendra Prasad Singh
32 | Sitamarhi | Benol, Block-Bokhra (Sitamarhi) | 124.31 | 2017-02-06 | M/s Bharti Const., Sitamarhi | 103.8815 | [5 empty] | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh
33 | Purnea | Mahendrapur, Block-Purnea (Purnea) | 124.31 | 2017-02-06 | Anil Kumar Singh, Katihar | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
34 | Purnea | Ranipatra, Block-Purnea Purva (Purnea) | 124.31 | 2017-02-06 | Shiv Shankar Singh, Katihar | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
35 | Purnea | Harda, Block-Purnea Purva (Purnea) | 124.31 | 2017-02-06 | Prakash Kumar Sah, katihar | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
36 | Purnea | Sabdalpur, Block-Kasba (Purnea) | 124.31 | 2017-02-06 | Rohit Raj Construction, Vaishali | 103.2393 |  |  | Plaster Work | 65% | 52 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
37 | Purnea | Echalo, Block-Dagarua (Purnea) | 124.31 | 2017-02-06 | Rohit Raj Construction, Vaishali | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
38 | Purnea | Muchhatta, Block-Amaur (Purnea) | 124.31 | 2017-02-06 | Prashant Const., Purnea | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
39 | Purnea | Sirshi, Block-Baisa (Purnea) | 124.31 | 2017-02-06 | Prashant Const., Purnea | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
40 | Purnea | Katorhat, Block-Baisa (Purnea) | 124.31 | 2017-02-06 | Parshant Const., Purnea | 103.2393 | [5 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
41 | Purnea | Kajha, Block-K.Nagar (Purnea) | 124.31 | 2017-02-06 | [7 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
42 | Purnea | Banbhag, Block-K.Nagar (Purnea) | 124.31 | 2017-02-06 | [7 empty] | Sri Pankaj Kumar | Sri Sanjeev Ranjan
[8 empty] | Total |  |  | 1137.7897

## HSC MINORITY (2)
HEALTH SUB CENTRE (Under MSDP)
SL NO | NAME OF DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (RS in lakh) |  |  | STAGE | % | (RS in lakh)
1 | WEST CHAMPARAN | HSC AT MANGALPUR BLOCK-SIKTA (WEST CHAMPARAN) |  |  | Brajesh Kumar, Bettiah | 116.155 | 2015-12-16 | 2016-08-15 | Completed | 100% | 63.89 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
2 | WEST CHAMPARAN | HSC AT BHAURA,BLOCK-SIKTA (WEST CHAMPARAN) |  |  | Brajesh Kumar, Bettiah |  | 2015-12-16 | 2016-08-15 | Completed | 100% |  | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
3 | WEST CHAMPARAN | HSC AT TILOJPUR,BLOCK-MAINATAND (WEST CHAMPARAN) |  |  | Brajesh Kumar, Bettiah |  | 2015-12-16 | 2016-08-15 | Completed | 100% |  | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
4 | WEST CHAMPARAN | HSC AT JIGNA,BLOCK-MAINATAND (WEST CHAMPARAN) |  |  | Brajesh Kumar, Bettiah |  | 2015-12-16 | 2016-08-15 | Completed | 100% |  | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
5 | SIWAN | HSC AT KHODAIBARI,BLOCK-HUSAINGANJ (SIWAN) |  |  | Brajesh Kumar, Bettiah |  | 2015-12-16 | 2016-08-15 | Not Started |  |  | Sri Sagar Jaiswal | - | Land not available
6 | DARBHANGA | HSC AT BASDIH, BLOCK-HAYAGHAT (DARBHANGA) |  |  | Sri vivek Kumar Jha, Darbhanga | 97.7403 | 2017-02-15 | 2017-10-14 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
7 | DARBHANGA | HSC AT SIRNIA, BLOCK-HAYAGHAT (DARBHANGA) |  |  | Sri vivek Kumar Jha, Darbhanga |  | 2017-02-15 | 2017-10-14 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
8 | DARBHANGA | HSC AT RATANPURA, BLOCK-HAYAGHAT (DARBHANGA) |  |  | Sri vivek Kumar Jha, Darbhanga |  | 2017-02-15 | 2017-10-14 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
9 | DARBHANGA | HSC AT HORALPATTI, BLOCK-HAYAGHAT (DARBHANGA) |  |  | Sri vivek Kumar Jha, Darbhanga |  | 2017-02-15 | 2017-10-14 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
10 | DARBHANGA | HSC AT DRAHWAJPUR, BLOCK-DARBHANGA (DARBHANGA) |  |  | Dinesh Pd. Singh | 104.9198 | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
11 | DARBHANGA | HSC AT KHARUA, BLOCK-DARBHANGA (DARBHANGA) |  |  | Dinesh Pd. Singh |  | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
12 | DARBHANGA | HSC AT BHALPATTI, BLOCK-DARBHANGA (DARBHANGA) |  |  | Dinesh Pd. Singh |  | 2017-03-20 | 2017-11-19 | Completed | 100% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
13 | DARBHANGA | HSC AT BADHAUL-DEVRA BANDHAUDI, BLOCK-JALE (DARBHANGA) |  |  | Dinesh Pd. Singh |  | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
14 | DARBHANGA | HSC AT GARDI, BLOCK-JALE (DARBHANGA) |  |  | Dinesh Pd. Singh |  | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
15 | GOPALGANJ | HSC AT BARWA, BLOCK-ADAPUR (GOPALGANJ) |  |  | Sri Shailendra Shekhar Mishra, Gopalganj | 108.762 |  |  | Not Started |  |  | Sri Sagar Jaiswal |  | Chotka Sakhen- Land not available
16 | GOPALGANJ | HSC AT BRAHBHAIN, BLOCK-ACHKAGAON (GOPALGANJ) |  |  | Sri Shailendra Shekhar Mishra, Gopalganj |  |  |  | Not Started |  |  | Sri Sagar Jaiswal
17 | GOPALGANJ | HSC AT BARARI HARKESH, BLOCK-ACHKAGAON (GOPALGANJ) |  |  | Sri Shailendra Shekhar Mishra, Gopalganj |  |  |  | Finishing work is in progress | 75% |  | Sri Sagar Jaiswal
18 | GOPALGANJ | HSC AT CHHOTKA SAKHEN, BLOCK-ACHKAGAON (GOPALGANJ) |  |  | Sri Shailendra Shekhar Mishra, Gopalganj |  |  |  | Not Started |  |  | Sri Sagar Jaiswal
19 | KISHANGANJ | HSC AT PIPRITHAN PURVI, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram | 133.1481 | 2017-05-05 | 2018-01-04 | Completed | 100% | 126.8 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
20 | KISHANGANJ | HSC AT KHARIBASTI, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Not Started | 0% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Due to unavailability of Land
21 | KISHANGANJ | HSC AT KATHARO, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
22 | KISHANGANJ | HSC AT KHANABARI, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
23 | KISHANGANJ | HSC AT PACKPARA, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
24 | KISHANGANJ | HSC AT JIRANGACH OLDMAICHI, BLOCK-THAKURGANJ (KISHANGANJ) |  |  | Smt Rita Devi, Sasaram |  | 2017-05-05 | 2018-01-04 | Completed | 100% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
25 | KATIHAR | HSC AT PALSA, BLOCK-BALRAMPUR (KATIHAR) |  |  | BHISHMA PRATAP SINGH, SIWAN | 89.989 | 2017-03-06 | 2017-11-05 | Finishing work | 75% | 32.1655 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
26 | KATIHAR | HSC AT MALIKPUR, BLOCK-BALRAMPUR (KATIHAR) |  |  | BHISHMA PRATAP SINGH, SIWAN |  | 2017-03-06 | 2017-11-05 | Finishing work | 75% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
27 | KATIHAR | HSC AT SINHAGAON BLOCK-BALRAMPUR (KATIHAR) |  |  | BHISHMA PRATAP SINGH, SIWAN |  | 2017-03-06 | 2017-11-05 | Finishing work | 75% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
28 | KATIHAR | HSC AT MADHOPUR, BLOCK-BALRAMPUR (KATIHAR) |  |  | BHISHMA PRATAP SINGH, SIWAN |  | 2017-03-06 | 2017-11-05 | - |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
29 | KATIHAR | HSC AT SHARIFNAGAR, BLOCK-BALRAMPUR, KATIHAR |  |  | SARWAR ALAM, KISHANGANJ | 92.8982 | 2017-03-20 | 2017-11-19 | Finishing work | 90% | 19.45 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
30 | KATIHAR | HSC AT BALRAMPUR,BLOCK-BALRAMPUR, KATIHAR |  |  | SARWAR ALAM, KISHANGANJ |  | 2017-03-20 | 2017-11-19 | Finishing work | 85% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
31 | KATIHAR | HSC AT BALUGANJ BLOCK-BALRAMPUR, KATIHAR |  |  | SARWAR ALAM, KISHANGANJ |  | 2017-03-20 | 2017-11-19 | Not Started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
32 | KATIHAR | HSC AT KAMRA, BLOCK-BALRAMPUR, KATIHAR |  |  | SARWAR ALAM, KISHANGANJ |  | 2017-03-20 | 2017-11-19 | Finishing work | 88% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
33 | KATIHAR | HSC AT RATNI, BLOCK-HASANGANJ, KATIHAR |  |  | BALMIKI PRASAD SINGH, KATIHAR | 89.9984 | 2017-03-06 | 2017-11-05 | Finishing work | 98% | 20.1899 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
34 | KATIHAR | HSC AT BHARRA, BLOCK-HASANGANJ, KATIHAR |  |  | BALMIKI PRASAD SINGH, KATIHAR |  | 2017-03-06 | 2017-11-05 | Plaster work | 65% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
35 | KATIHAR | HSC AT DHERUA, BLOCK-HASANGANJ, KATIHAR |  |  | BALMIKI PRASAD SINGH, KATIHAR |  | 2017-03-06 | 2017-11-05 | Plaster work | 65% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
36 | KATIHAR | HSC AT RAMPUR, BLOCK-HASANGANJ, KATIHAR |  |  | BALMIKI PRASAD SINGH, KATIHAR |  | 2017-03-06 | 2017-11-05 | Finishing work | 98% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
37 | KATIHAR | HSC AT JOKER,BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 113.6883 |  |  | Roof Shuttering | 25% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
38 | KATIHAR | HSC AT PIDAL, BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA |  |  |  | Plinth Beam | 10% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
39 | KATIHAR | HSC AT BALUGANJ, BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA |  |  |  | Brick work is in progress | 25% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
40 | KATIHAR | HSC AT BARIA, BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA |  |  |  | - |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
41 | KATIHAR | HSC AT CHANDPUR, BLOCK-AZAMNAGAR, KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA |  |  |  | - |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
42 | SUPAUL | HSC AT KATAIYA BLOCK-BASANTPUR, SUPAUL |  |  | Dhirendra Kumar Thakur, Supaul | 42.6685 | 2017-02-08 | 2017-08-07 | Finishing work | 85% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
43 | SUPAUL | HSC AT JIRWA BLOCK-BASANTPUR, SUPAUL |  |  | Dhirendra Kumar Thakur, Supaul |  | 2017-02-08 | 2017-08-07 | Finishing work | 85% |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
44 | DARBHANGA | HSC AT NISTA, BLOCK-SINGHWARA (DARBHANGA) |  |  | M/s Delta Enterprises, Patna | 66.4002 | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar |  | Land not available
45 | DARBHANGA | HSC AT SAKARPUR, BLOCK-SINGHWARA (DARBHANGA) |  |  | M/s Delta Enterprises, Patna |  | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
46 | DARBHANGA | HSC AT KARAUNI, BLOCK-KEWTI (DARBHANGA) |  |  | M/s Delta Enterprises, Patna |  | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
47 | DARBHANGA | HSC AT JAGDISHPUR, BLOCK-MANIGACHHI (DARBHANGA) |  |  | M/s Delta Enterprises, Patna | 66.4002 | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh | Land not available
48 | DARBHANGA | HSC AT BHANDARISAM, BLOCK-MANIGACHHI (DARBHANGA) |  |  | M/s Delta Enterprises, Patna |  | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
49 | DARBHANGA | HSC AT RAMNAGAR, BLOCK-MANIGACHHI (DARBHANGA) |  |  | M/s Delta Enterprises, Patna |  | 2017-02-08 | 2017-10-07 | Not Started |  |  | Sri Sunil Kumar | Sri Rajendra Prasad Singh
Shiva | PURNEA | HSC AT CHANKA, BLOCK-SRINAGAR, DIST.-KISHANGANJ |  |  | MDS Infranirman Pvt ltd, Patna | 129.6127 | 2017-03-23 | 2017-11-22 | Not Started |  | 19.94 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | HSC Already constructed by the Building ConstructionDepartment IN PASSED
51 | PURNEA | HSC AT UDAYNGAR, BLOCK-SRINAGAR, DIST.-KISHANGANJ |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | B/W is in progress. | 30% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
52 | PURNEA | HSC AT MANKAUL, BLOCK-SRINAGAR, DIST.-KISHANGANJ |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | Finishing work | 75% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
53 | PURNEA | HSC AT GADHIYA, BLOCK-SRINAGAR, DIST.-KISHANGANJ |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | Not Started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
54 | PURNEA | HSC AT LASANPUR, BLOCK-DAGARUA, DIST.-PURNEA |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | Not Started |  |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
55 | PURNEA | HSC AT GADHWAS, BLOCK-DAGARUA, DIST.-PURNEA |  |  | MDS Infranirman Pvt ltd, Patna |  | 2017-03-23 | 2017-11-22 | Finishing work | 80% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
56 | MADHUBANI | HSC AT LAXMIPUR , BALATH, SUNDARPUR BILTHI, SATLAKHA, SAMBHAUR, KHARUVA NAJIRPUR & CHAURI , BLOCK-RAHINA, DIST.-MADHUBANI |  |  | Satish Narayan Singh, E. Champaran | 178.8191 |  |  | Laxmipur-Finishing work, Sundarpur Bilthi-Roof casted , Sambhaur-Plaster work | 58% |  | Sri Sunil Kumar
57 | KATIHAR | HSC AT KURSEL,KAMRU,KURUM, BHRRI & ROSHANGANJ, BLOCK-KADWA, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 112.5097 | 2017-07-15 | 2018-03-14 | Kursel- Roof casted Bhrri- Finishing work, Kurum- Plinth Beam completed | 27% | 20.38 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | KAMRU, & ROSHANGAN -Land not available
58 | KATIHAR | HSC AT TAYABPUR WEST,NISTA, SAGRATH,SHIKARPUR & BHAWNAGAR BLOCK-KADWA, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 112.5097 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not clear
59 | WEST CHAMPARAN | HSC AT PARSI, PIPRA,DHUMNAGAR,ROARI, SUNASATTI, & DHAMINAHA BLOCK-NARKATIYAGANJ, DIST.-WEST CHAMPARAN |  |  | Vikash Kumar Gupta | 137.1294 | 2017-05-05 | 2018-01-04 | Pipra & Sunasatti- Finishing work, DHUMNAGAR Parsi, Roari, Dhaminaha- Roof Level | 30% | 48.4549 | Md Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
60 | KATIHAR | HSC AT JAUNIYA, THAGDABARI, BHANDARTAL, RONIYA & DURGAPUR, BLOCK-KADWA, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 111.3366 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
61 | KISHANGANJ | HSC AT KALPEER, PATHARGHATTI, & LOHAGARA BLOCK-DIGHALBANK, DIST.-KISHANGANJ |  |  | M/S Dolphin Construction | 69.2523 | 2017-04-28 | 2017-10-27 | Completed | 100% | 24.39 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
62 | PURNEA | HSC AT MAUKHNAHA DEVINAGAR, BANSAR, HAUSI & BHATHAILI, BLOCK-SRINAGAR JALALGARH, DIST.-PURNEA |  |  | M/s Gautam Construction | 110.6699 | 2017-05-05 | 2018-01-04 | DEVINAGAR- Column work | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Rest site Land not clear
63 | PURNEA | HSC AT PALANKAP,KANJIYA,BHEMRA, SATARO, RAIBER & MIRJAPUR, BLOCK-BAISA, DIST.-PURNEA |  |  | SARWAR ALAM, KISHANGANJ | 115.4776 | 2017-05-09 | 2018-01-08 | Kanjiya- Roof Level | 35% | 14.69 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Rest site Land not clear
64 | PURNEA | HSC AT PARMANANDPUR,CHHATIYA GAURA, MAHARAJPUR & HARDA, BLOCK-PURNEA PURV, DIST.-PURNEA |  |  | Mannu Pratap Rana | 109.3228 | 2017-05-09 | 2018-01-08 | MAHARAJPUR- Completed, GAURA- Roof Casted, Harda- Layout | 60% | 20.42 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Rest site land not clear
65 | SITAMARHI | HSC AT CHAKAUTI, KURHAR & BUDHNAGAR, BLOCK-BOKHRA, DIST.-SITAMARHI |  |  | KUNDAN KUMAR SINGH | 68.446 | 2017-05-15 | 2017-11-14 | Kurhar-Finishing work | 96% | 21.76 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Chakauti & Budhnagar-Land not available
66 | PURNEA | HSC AT CHAPAY, SAUSA, DEVINAGAR, BAKHRIKAUL, MIRAMILIKH & SONGARHA, BLOCK-K. NAGAR, DIST.-PURNEA |  |  | SUDHIR KUMAR | 130.9923 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued (Land not clear)
67 | GOPALGANJ | HSC AT BHERIA, RAMCHANDARPUR, AWADHIYATOLA, GHATIWANA, INDERWASAKIN & BIDHESIATOLA, BLOCK-THAVE, DIST.-GOPALGANJ |  |  | SRI KRISHNA CONST. COMPANY | 114.6877 | 2017-05-11 | 2018-01-10 | GHATIWANA- Finishing work | 70% |  | Sri Sagar Jaiswal |  | Rest Site Land not available
68 | KATIHAR | HSC AT BINJI, SIMARIA, PACHMA, CHANDAL & RAUTARA BLOCK-KODHA, DIST.-KATIHAR |  |  | AWANI DEVCON PVT. LTD. | 111.1959 | 2017-07-15 | 2018-03-14 | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
69 | KISHANGANJ | HSC AT PANISAL, HALAWALA, CHHAGALIA, GACHHPARA KAPGANDHA BLOCK-KISHANGANJ, DIST.-KISHANGANJ |  |  | SARWAR ALAM, KISHANGANJ | 114.1947 | 2017-05-09 | 8Months | GACHHPARA- Finishing work, Halawala- Roof casted | 60% | 24.83 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued, Rest site land not clear
70 | KATIHAR | HSC AT KANTNAGAR, SRANICHAK, BHAINSDIRA, BINDHTOLI & HASIMPUR, BLOCK-BARARI, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 111.3366 | 2017-10-09 | 2018-06-08 | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
71 | KISHANGANJ | HSC AT CHAITAL, BHOGDAWAR & MAHESWARI BLOCK-THAKURGANJ, DIST.-KISHANGANJ |  |  | Smt Rita Devi, Sasaram | 66.5741 | 2017-07-14 | 2018-03-13 | Completed | 100% | 66.57 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
72 | KISHANGANJ | HSC AT SHEETALPUR, SIGRI, GOVINDPUR, SAROGORA, POLTHA, HALDAGOAN, BAKSA, HALDIBARI & PAMAL BLOCK-POTHIA, DIST.-KISHANGANJ |  |  | Smt Rita Devi, Sasaram | 199.7222 | 2017-09-14 | 8 Months | SHEETALPUR-Completed ,Sigri-Completed, SAHUGORA-Completed, KOLTHA-Completed, HALDIBARI-Completed & PAMAL-Completed | 100% | 46.72 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Govindpur-Not started, Haldagaon & Baska-Land not clear
73 | KISHANGANJ | HSC AT NEJAGACHH, DUMARIA MADARSATOLA, BESARWATI, PATHAMARI & CHURLI, BLOCK-THAKURGANJ, DIST.-KISHANGANJ |  |  | Smt Rita Devi, Sasaram | 110.9568 | 2017-07-14 | 2018-03-13 | DUMARIA MADARSATOLA- Completed BESARWATI- Completed PATHAMARI-Completed & CHURLI- Completed | 100% | 40.43 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Nejagachh-Land not available
74 | KATIHAR | HSC AT KHERA, PARTAILI CHILMARA & HAJIPUR BLOCK-KATIHAR, DIST.-KATIHAR |  |  | PRAKASH KUMAR SAH | 93.8461 | 2017-05-15 | 2018-01-14 | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
75 | KATIHAR | HSC AT MAKGADPUR, SISIA, RAJWARA, NAKKIPUR & BHATWARA BLOCK-KODHA, DIST.-KATIHAR |  |  | AWANI DEVCON PVT. LTD. | 111.1959 | 2017-07-14 | 2018-03-13 | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
76 | PURNEA | HSC AT KAMALPUR, DARIAPUR, DUBEILI, MANIKPUR, LASANPUR CHAKWA & MARGA, BLOCK-PURNEA, DIST.-PURNEA |  |  | PRAKASH KUMAR SAH | 162.5791 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued (Land not clear)
77 | KISHANGANJ | HSC AT BORHA, BALUA & JAGIR, BLOCK-TEDHAGACHH, DIST.-KISHANGANJ |  |  | NAWNEE KUMAR SINGH | 65.9149 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
78 | KATIHAR | HSC AT BAIDA, KISHNUPUR, CHHOTA LAKHANPUR, BARIA, PAHARPUR PACHHIM TOLA, BLOCK-AMDABAD, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 112.5097 |  |  | BAIDA- Plaster work | 65% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan
79 | KATIHAR | HSC AT KHATTI, CHAUKIAPUR, MAYAMARI, BABLABANN & PRANPUR BLOCK-AMDABAD, DIST.-KATIHAR |  |  | ARCHANA CONTRACTOR PVT. LTD., PATNA | 112.5097 |  |  | PRANPUR- Plinth Beam | 15% |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Land not available
80 | BHAGALPUR | HSC AT CHHOTI NALA, MADEDA, AMBIHA, BANIADIH, BLOCK-SANHAULA, DIST.-BHAGALPUR |  |  | SANJEEV KUMAR | 80.1661 |  |  | Not Started | - |  | sri Anil Kumar | Sri Sanjeev Ranjan | Land not available
81 | PURNEA | HSC AT KARUA RAHIKA, BELAHAT, POTHIYA RAMPUR, RAMNAGAR, ROSKA KOSHAGARH & BITHNAULI KHEMCHAND BLOCK-K. NAGAR, DIST.-PURNEA |  |  | UNITED INFRA & INDUSTRIES | 139.2142 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued (Land not clear)
82 | KATIHAR | HSC AT SRAJDHANI, BHARSIA, BELGACHHI & RANI SIMARIA,, BLOCK-FALKA, DIST.-KATIHAR |  |  | LARKS BUILDCN PVT. LTD. | 87.2768 | 2017-03-20 | 2017-09-19 | SRAJDHANI- Finishing work,RANI SIMARIA-Finishing work | 50% | 10.15 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
83 | PURNEA | HSC AT BAKHARI, GANDHAR, BISHARI & KHOKSA BLOCK-VAYSI, DIST.-PURNEA |  |  | SARWAR ALAM, KISHANGANJ | 92.3821 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
84 | PURNEA | HSC AT NAWABGANJ, BAKHARIA, CHOBHRA & MALHARIA, BLOCK-VAYSI, DIST.-PURNEA |  |  | TUFAIL AHMED KHAN | 68.98 |  |  | Not Started | - |  | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued
85 | KISHANGANJ | HSC AT BHATGAON, HATHIDUBA, DUDHAUTI, BHOLMARA, RUPDAH & ADARGARI & KATHALDANGI, BLOCK-THAKURGANJ, DIST.-KISHANGANJ |  |  | Smt Rita Devi, Sasaram | 110.9568 | 2017-07-14 | 2018-03-13 | BHATGAON-Completed HATHIDUBA-Completed BHOLMARA-Completed | - | 20.35 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Dudhuti, & ADARGARI-Land not available
86 | KATIHAR | HSC AT MUKURIA, KHARSOTA, NIMAUL, MURAWATPUR & TEGHRA BLOCK-AZAMNAGAR, DIST.-KATIHAR |  |  | NEW SHIVA CONSTRUCTION | 105.5768 | 2017-05-15 | 2018-01-14 | MUKURIA-Brick work is in progress, KHARSOTA- Lintel Level | 25% | 6.8768 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Murawatpur-Pond
|  | TOTAL |  |  |  | 116.155 |  |  |  |  | 648.4571

## Medical college Schm (2)
CONSTRUCTION OF VARIOUS SCHEMES IN MEDICAL COLLEGE
SL NO | NAME OF DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) |  | (Rs in lakh) |  |  | STAGE | %
1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 13 | 14 | 15
1 | PATNA | CONSTRUCTION OF LECTURE THEATRE FOR 350 STUDENTS IN NALANDA MEDICAL COLLEGE & HOSPITAL,PATNA | 354 | Kislay Enterprises | 218.974 | 2015-01-16 | 2016-01-15 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | PATNA | CONSTRUCTION OF BOUNDARY WALL AT NALANDA MEDICAL COLLEGE & HOSPITAL, PATNA (Hospital-9450') | 238.611 | Sanjeev Kumar, Patna | 200.7525 | 2015-09-09 | 2016-03-08 | 3000 m work completed | 95% | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan
3 | PATNA | CONSTRUCTION OF BOUNDARY WALL AT NALANDA MEDICAL COLLEGE & HOSPITAL, PATNA (College-481') | 13.1675 | Ganesh Prasad Singh | 12.2914 | 2015-08-11 | 2015-11-10 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
4 | PATNA | CONSTRUCTION OF CENTRAL LIBRARY AT NMCH (3rd floor), PATNA | 0 | Pawan Shekher | 75.816 | 2016-05-12 | 2017-02-11 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
5 | PATNA | CONSTRUCTION OF MORTUARY BUILDING AT PMCH, PATNA | 506.6 | Ramesh Kumar Pandey | 415.6374 | 2014-12-19 | 2015-12-18 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
6 | PATNA | CONSTRUCTION OF COMMON ROOM AT 1st FLOOR OF OLD BUILDING PMCH, PATNA | 79.18 | Lallu Kumar | 58.7125 | 2015-08-17 | 2016-04-16 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
7 | PATNA | CONSTRUCTION OF BOUNDARY WALL NEAR DARBHANGA HOUSE AT PATNA MEDICAL COLLEGE & HOSPITAL, PATNA (Hospital-9450') | 0 | Lallu Kumar | 22.2227 | 2017-02-22 | 2017-05-21 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
8 | PATNA | UPGRADATION OF EMERGENCY WARD AT PATNA MEDICAL COLLEGE & HOSPITAL, PATNA | 996.795 | Rama and Sons | 835.948 | 2017-09-08 | 2018-06-07 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
9 | PATNA | RENOVATION OF KIDNEY TRANSPLANT UNIT WITH MODULAR UNIT AND FURNITURE AT PMCH, PATNA | 1266 | Pan Solution Pvt Ltd, Patna | 907.37 | 2018-09-18 | 2019-06-17 | Work is going on | 30% | Sri Pankaj Kumar | Sri Sanjeev Ranjan
10 | PATNA | CONSTRUCTION OF 12 BEDDED ICU AT PMCH, PATNA | 120.6 | Ashishwar Krishna Developers Pvt ltd | 146.04 | 2018-09-20 | 2019-06-19 | Completed | 100% | Sri Pankaj Kumar | Sri Sanjeev Ranjan
11 | PATNA | CONSTRUCTION OF BURN WARD AT PMCH, PATNA | 528.82 | Rama & Sons | 368.46 | 2018-12-14 | 2019-12-13 | Work is going on | 75% | Sri Pankaj Kumar | Sri Sanjeev Ranjan
12 | DARBHANGA | CONSTRUCTION OF CENTRAL LIBRARY IN DARBHANGA MEDICAL COLLEGE & HOSPITAL, LAHERIASARAI (DARBHANGA) | 985.7 | Indra narayan singh contractor pvt. Ltd | 660.4621 | 2014-07-09 | 2016-01-08 | Completed | 100% | Sri Sunil Kumar | Sri Rajendra Prasad Singh
13 | DARBHANGA | CONSTRUCTION OF P.G GIRLS HOSTEL IN DARBHANGA MEDICAL COLLEGE & HOSPITAL, LAHERIASARAI (DARBHANGA) | 1004.84 | Indra narayan singh contractor pvt. Ltd | 853.8188 | 2014-07-09 | 2016-01-08 | Completed | 100% | Sri Sunil Kumar | Sri Rajendra Prasad Singh
14 | DARBHANGA | CONSTRUCTION OF BOUNDARY WALL AT DARBHANGA MEDICAL COLLEGE & HOSPITAL, LAHERIASARAI (DARBHANGA) | 81.3611 | Smt Rita Devi,Sasaram | 69.7102 | 2015-08-06 | 2015-12-05 | Completed | 100% | Sri Sunil Kumar | Sri Rajendra Prasad Singh
15 | BHAGALPUR | CONSTRUCTION OF BOUNDARY WALL AT JAWAHARLAL NEHRU MEDICAL COLLEGE & HOSPITAL BHAGALPUR (Length-8160 m) | 456.85 | Anand Consultant | 427.4809 | 2014-08-07 | 2015-08-06 | Completed | 100% | Sri Anil Kumar | Sri Sanjeev Ranjan
16 | BHAGALPUR | CONSTRUCTION OF BOUNDARY WALL AT JAWAHARLAL NEHRU MEDICAL COLLEGE & HOSPITAL BHAGALPUR (Length-8160 m) |  | Rohit Raj Construction Pvt Ltd, Vaishali | 283.335 |  |  |  |  | Sri Anil Kumar | Sri Sanjeev Ranjan
17 | BHAGALPUR | CONSTRUCTION OF 100 BEDDED BOYS HOSTEL AT JLNMCH, BHAGALPUR | 705.28 | Lalan Kumar | 941.6415 | 2016-05-20 | 2017-11-19 | Completed | 100% | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed over
18 | BHAGALPUR | CONSTRUCTION OF 50 BEDDED PG BOYS HOSTEL AT JLNMCH, BHAGALPUR | 550.95 | Lalan Kumar |  | 2016-05-20 | 2017-11-19 | Completed | 100% | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed over
19 | BHAGALPUR | CONSTRUCTIN OF LECTURE THEATRE AT JAWAHARLAL NEHRU MEDICAL COLLEGE & HOSPITAL BHAGALPUR | 203.77 | Ajay Kumar Chaudhary | 142.2769 | 2014-12-15 | 2015-12-14 | Completed | 100% | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed over
20 | GAYA | CONSTRUCTION OF VARIOUS BUILDING IN ANUGRAH NARAYAN MAGADH MEDICAL COLLEGE & HOSPITAL GAYA |  | M/S Dipansu Promoter & Builder Pvt. Ltd., Ranchi | 2296.2247 | 2014-09-04 | 2016-09-03
|  | (a) Administrative Block | 490.01 |  |  |  |  | Completed | 100% | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
|  | (b) Principal Residence | 126.49 |  |  |  |  | Completed | 100% | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
|  | (c) P.G boys hostel | 611.68 |  |  |  |  | Completed | 100% | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
|  | (d) P.G girls hostel | 573.98 |  |  |  |  | Completed | 100% | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
|  | (e) 64 Tutor Residence (2 Blocks) | 1336.03 |  |  |  |  | Completed | 100% | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
21 | MUZAFFARPUR | CONSTRUCTION OF BOUNDARY WALL AT SRI KRISHNA MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR (1400') | 28.701 | Ramjee Prasad | 24.1566 | 2014-08-19 | 2014-11-18 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
22 | MUZAFFARPUR | CONSTRUCTION OF TUTOR RESIDENCE AT SRI KRISHNA MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR |  | Arun Deo Kumar | 2084.4857 | 2017-05-15 | 2019-05-14 | Completed | 100% | Sri Vikash Jha | Sri Rajendra Prasad Singh
23 | MUZAFFARPUR | CONSTRUCTION OF BOYS HOSTEL AT SRI KRISHNA MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR |  | Arun Deo Kumar |  | 2017-05-15 | 2019-05-14 | Completed | 100% | Sri Vikash Jha | Sri Rajendra Prasad Singh
24 | MUZAFFARPUR | UPGRADATION OF INTERNAL ROAD OF RBTS HOMEOPATHIC MEDICAL COLLEGE & HOSPITAL MUZAFFARPUR |  | Ashok Kumar Singh, Muzaffarpur | 31.8427 | 2017-09-06 | 2017-12-05 | Completed | 100% | Sri Arjun Kumar Mishra | Sri Rajendra Prasad Singh | Handed over
25 | BETTIAH | CONSTRUCTION OF 7 LABORATORIES IN GOVT. MEDICAL COLLEGE BETTIAH BY PRE-FABRICATED MATERIAL | 318.9 | Shiva infra solution pvt. Ltd | 281.8471 | 2014-11-27 | 2015-03-26 | Completed | 100% | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | Handed over
26 | BETTIAH | EXPENSION OF INTERNAL CAPACITY OF GOVT. MEDICAL COLLEGE BETTIAH | 0 | Irfan Akhtar | 37.4214 | 2018-02-02 | 2019-04-01 | Completed | 100% | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh | Handed over
27 | BETTIAH | CONSTRUCTION OF GYMNASIUM AND COMMON ROOM AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH (Prefab) | 0 | Fab India | 120 | 2018-03-15 | 2018-07-14 | Completed | 100% | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
28 | BETTIAH | CONSTRUCTION OF CENTRAL LIBRARY AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH (Prefab) | 0 | Shiva Infra Solutions Pvt. Ltd., | 446.45 | 2017-10-16 | 2018-04-15 | Completed | 100% | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
29 | BETTIAH | CONSTRUCTION OF LECTURE THEATRE AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH (Prefab) | 0 | Jindal Mectec Pvt. Ltd | 133.39 | - | - | Completed | 100% | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh
30 | BETTIAH | CONSTRUCTION OF 100 BEDDED HOSTEL (G+2) AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH (Prefab) | 0 | Jindal Mectec Pvt. Ltd | 524.7 | 2018-04-06 | 2018-10-05 | Completed | 100% | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad Singh

## HSC SHS1 (2)
List of 17 nos of HSC
SL NO | Name of work | Administrative Approval Amount (in Rs. Lakh) | No. of Projects | Ongoing Projects | Remarks
1 | Construction of Health Sub Centre | 408.00 (24.00 per unit) | 17 | 4 | Land not available-6, In Tender-02, Completed-02
S. N. | Name of Work | A.A Amount (in rs Lakh) | Name of Contractor | Physical Status | Remarks
1 | LokLF; midsUnz Hkxugh iz[kaM+&ujirxat ftyk& vjfj;k dk Hkou fuekZ.k dk;ZA | 24 | Dhirendra Kr. Thakur | Not started | Land not available
2 | LokLF; midsUnz fcykjh iz[kaM+&drjhljk; ftyk&ukyank dk Hkou fuekZ.k dk;ZA | 24 | Mahendra Kr. Sinha | Completed | Handed over
3 | LokLF; midsUnz bjkdh iz[kaM+&nso ftyk& vkSjaxkckn dk Hkou fuekZ.k dk;ZAZ | 24 | Shobha Devi | Brick work
4 | LokLF; midsUnz pnW;kuh iz[kaM+&dksap ftyk&x;k dk Hkou fuekZ.k dk;ZA | 24 | Dhananjay Kumar | Finishing work (90%)
5 | LokLF; midsUnz vnkbZ iz[kaM+&dksap ftyk&x;k esa LokLF; midsUnz dk Hkou fuekZ.k dk;ZA | 24 | Dharmendra Sharma | Not started | Land not available. Letter sent to C.S vide letter no-1274, 2938, 3947, 5149 dated-25.06.2018, 27.09.2018, 25.01.2019
6 | LokLF; midsUnz gluiqj gcjgka iz[kaM+&egukj ftyk&oS”kkyh dk Hkou fuekZ.k dk;ZA | 24 | Narayan Roy | Not started | Land not available Letter sent to C.S vide letter no-5450 dated-11.02.2019
7 | LokLF; midsUnz y[kunhjk iz[kaM+&MqejkWo ftyk&cDlj dk Hkou fuekZ.k dk;ZA | 24 | Raju Kumar Pandey | Roof casted
8 | LokLF; midsUnz eksguiqj iz[kaM+&lnj ftyk& Hkkstiqj dk Hkou fuekZ.k dk;ZA | 24 | Kamlesh Kumar | Roof casted
9 | LokLF; midsUnz jkekpqvk iz[kaM+&”kEHkqxat ftyk&ckadk dk Hkou fuekZ.k dk;ZA | 24 | Vaishanavi Buildtech pvt. Ltd. | Not started | Land not available. Letter sent to M.O incharge vide letter no-5121 dated-24.01.2019
10 | LokLF; midsUnz enok iz[kaM+&fHkfi;qj ftyk& Hkkxyiqj dk Hkou fuekZ.k dk;ZA | 24 | Dharmendra Sharma | Not started | Lant not available, Letter sent to C.S.
11 | LokLF; midsUnz eghukFkuxj iz[kaM+&csynkSj ftyk& [kxM+h;k dk Hkou fuekZ.k dk;ZA | 24 | Prashant Kumar | Not started | Agreement in Process
12 | LokLF; midsUnz vnkiqj iz[kaM+&lq;Zx<+ ftyk& y[khljk; dk Hkou fuekZ.k dk;ZAZ | 24 | Sanjeev Kumar | Not started | Land not available
13 | LokLF; midsUnz bUnq[k iz[kaM+&tekyiqj ftyk& eqxsj dk Hkou fuekZ.k dk;ZA | 24 | Dhananjay Kumar, Barh | Completed
14 | LokLF; midsUnz egslqvk iz[kaM+&e/ksiqjk ftyk&e/ksiqjk dk Hkou fuekZ.k dk;ZA | 24 | - | Not started | In Tender
15 | LokLF; midsUnz csykxat iz[kaM+&dnok ftyk&dfVgkj dk Hkou fuekZ.k dk;ZA | 24 | - | Not Started | In Tender
16 | LokLF; midsUnz xuqjk iz[kaM+&eqjkSuk ftyk&lqikSy dk Hkou fuekZ.k dk;ZA | 24 | Dhirendra Kr. Thakur | Not started | Land not available, Letter sent to C.O. vide letter no-1991, dated-01.08.2018
17 | LokLF; midsUnz cyh;k iz[kaM+&egjktxat ftyk&floku dk Hkou fuekZ.k dk;ZA | 24 | M/s B. Prasad | Not started
| Total | 408

## DEIC
DISTRICT EARLY INTERVENTION CENTRE
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
Phase- I
1 | BHAGALPUR | CONSTRUCTION OF DEIC AT JLNMCH,BHAGALPUR | 122.4381 | 2016-03-18 | Ajay Kumar Chaudhary | 98.4078 | 2017-05-09 | 2018-02-08 | Completed | 100% | 78.48 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed Over
2 | SAHARSA | CONSTRUCTION OF DEIC AT SADAR HOSPITAL, SAHARSA | 122.4381 | 2016-03-18 | Bambam Singh | 99.3508 | 2017-06-02 | 2018-03-01 | Completed | 100% | 36 | Sri Sunil Kumar | Sri Rajendra Prasad
3 | MUZAFFARPUR | CONSTRUCTION OF DEIC AT SADAR HOSPITAL, MUZAFFARPUR | 122.4381 | 2016-03-18 | Md. Nabi | 96.9552 | 2017-06-29 | 2018-03-28 | Completed | 100% | 93.96 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad | Handed Over
4 | GAYA | CONSTRUCTION OF DEIC AT PRABHAWATI HOSPITAL, GAYA | 123.692 | 2016-03-18 | Ram Pukar Singh, Gaya | 90.2932 | 2017-08-23 | 2018-05-22 | Completed | 100% | 90.29 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
Phase- II
5 | PATNA | CONSTRUCTION OF DEIC AT NMCH, PATNA | 122.4381 | 2017-12-11 | MDS Infranirman Pvt Ltd, Patna | 100.828 | - | - | Not Started | - | - | - | - | Tender decided, LOA to be issued
6 | MUNGER | CONSTRUCTION OF DEIC AT DISTRICT HOSPITAL, MUNGER | 122.4381 | 2017-12-11 | Rita Devi | 98.2579 | - | - | Not Started | - | - | - | - | Financial bid opened. Due to single bid Tender will be finalized next Board meeting
7 | SARAN | CONSTRUCTION OF DEIC AT DISTRICT HOSPITAL, CHHAPRA | 122.4381 | 2017-12-11 | Shobh Nath Prasad | 97.6895 | - | - | Not Started | - | - | - | - | Financial bid opened. Due to single bid Tender will be finalized next Board meeting
8 | DARBHANGA | CONSTRUCTION OF DEIC AT DMCH, DARBHANGA | 122.4381 | 2017-12-11 | - | - | - | - | Not Started | - | - | - | - | 1st Time tender invited vide Nit no-13/2018 (Two bidder participated in tender & one bid technically disquqlifed. Hence Retender invited vide Nit no-03/2019. Last date of receipt of tender-27/03/2019
9 | PURNEA | CONSTRUCTION OF DEIC AT DISTRICT HOSPITAL, PURNEA | 122.4381 | 2017-12-11 | - | - | - | - | Not Started | - | - | - | - | 1st Time tender invited vide Nit no-13/2018 (Two bidder participated in tender & one bid technically disquqlifed. Hence Retender invited vide Nit no-03/2019. Last date of receipt of tender-27/03/2019
| TOTAL |  | 1103.1972 |  |  | 681.7825 |  |  |  |  | 298.73

## mch
MCH WING
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
Phase- I
1 | BHAGALPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT JLNMCH,BHAGALPUR | 1335.61 | 2016-06-16 | Devine Lotus Infrastructure Pvt Ltd | 1080.3916 | 2018-05-24 | 2019-11-23 | Brick work is going on | 35% | 248.12 | Sri Anil Kumar | Sri Sanjeev Ranjan
2 | MUZAFFARPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT SKMCH, MUZAFFARPUR | 1337.89 | 2016-06-16 | Arun Deo Kumar | 1078.6605 | 2018-03-23 | 2019-09-22 | Finishing work | 83% | 125 | - | Sri Rajendra Prasad
3 | MUZAFFARPUR | CONSTRUCTION OF 100 BEDDED MCH WING AT SADAR HOSPITAL MUZAFFARPUR | 1342.31 | 2016-06-16 | Kishor Kumar | 1082.8245 | 2018-03-23 | 2019-09-22 | Finishing work | 78% | 397.56 | - | Sri Rajendra Prasad
4 | GAYA | CONSTRUCTION OF 100 BEDDED MCH WING AT ANMMCH, GAYA | 1325.04 | 2016-06-16 | Akshit Engineering | 1026.7457 | 2018-06-01 | 2019-12-31 | Roof shuttering (G.F) | 17% | 86 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Work started after demolished old building
5 | DARBHANGA | CONSTRUCTION OF 100 BEDDED MCH WING AT DMCH, DARBHANGA | 1312.06 | 2016-06-16 | Sanjay Kumar, Darbhanga | 1024.4141 | 2018-06-29 | 2019-12-28 | Not Started | 0 | 0 | Sri Sunil Kumar | Sri Rajendra Prasad | Old building available on proposed site
6 | SITAMARHI | CONSTRUCTION OF 100 BEDDED MCH WING AT SADAR HOSPITAL SITAMARHI | 1333 | 2016-06-16 | Shashikant Singh, Sheohar | 1080.07 | 0 | 0 | Foundation work is going on | 5% | 0 | - | Sri Rajendra Prasad
7 | PATNA | CONSTRUCTION OF 100 BEDDED MCH WING AT NMCH, PATNA | 1364 | 2016-06-16 | Indra Narayan Singh Contract pvt ltd | 1132.5562 | 2019-03-02 | 2020-09-01 | Pile cap work is going on | 10% | 50.12 | 0 | 0
8 | PATNA | CONSTRUCTION OF 100 BEDDED MCH WING AT PMCH, PATNA | 1300 | 2016-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project hold due to redevelopment of PMCH, Patna
|  | TOTAL | 10649.91 |  |  | 7505.6626 |  |  |  |  | 906.8

## Trauma Centre
Trauma Centre
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | CURRENT PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Patna | CONSTRUCTION OF TRAUMA CENTRE AT LNJPN HOSPITAL, PATNA (LVL-II) | - | - | Mother India Construction Pvt Ltd | 1252.6201 | 2019-03-02 | 2020-06-01 | Pile work is going on | 10% | 0 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | LOA issued on 30/07/2018
1 | Purnea | CONSTRUCTION OF TRAUMA CENTRE AT DISTRICT HOSPITAL PURNEA (LVL-II) | Building Cost-0.80 Eq. Cost-5.00 = 5.80 | 2016-06-23 | Rana Pratap Singh, Purnea | 125.9583 | 2019-02-13 | 2019-08-12 | Roof shuttering | 30% | 0 | Sri Shashi Shekhar | Md. Shamim Ahmad
2 | Muzaffarpur | TRAUMA CENTRE AT SKMCH, MUZAFFRAPUR (LVL-II) | Building Cost-0.80 Eq. Cost-5.00 = 5.80 | 2016-06-23 | R.K Infraservices, Patna | 125.6187 | 2019-02-12 | 2019-08-11 | roof shuttering | 30% | - | Sri Vikash Jha | Sri Sanjeev Ranjan
3 | Sasaram | CONSTRUCTION OF TRAUMA CENTRE AT DISTRICT HOSPITAL SASARAM (LVL-III) | Building Cost-0.55 Eq. Cost-2.00 = 2.55 | 2016-06-23 | Rita Devi, Rohtas | 92.2019 | 2018-11-06 | 2019-05-05 | Finishing work is going on | 95% | 20 | Sri Pankaj Kumar | Sri Sanjeev Ranjan
4 | Gaya | CONSTRUCTION OF TRAUMA CENTRE AT ANMMCH, GAYA (LVL-II) | Building Cost-0.80 Eq. Cost-5.00 = 5.80 | 2016-06-23 | B.Prasad | 111.2 | 2019-03-02 | 2019-09-01 | Plaster work is going on | 62% | - | Sri sandeep Kumar | Sri Sanjeev Ranjan
5 | Darbhanga | CONSTRUCTION OF TRAUMA CENTRE AT DMCH, DARBHANGA (LVL-II) | Building Cost-0.80 Eq. Cost-5.00 = 5.80 | 2016-06-23 | Alakh Ranjan Construction Pvt Ltd | 113 | 2018-12-07 | 2019-06-06 | Brick work is going on | 30% | 16 | Sri Sunil Kumar | Md. Shamim Ahmad
6 | Madhepura | TRAUMA CENTRE AT DISTRICT HOSPITAL MADHEPURA (LVL-III) | Building Cost-0.65 Eq. Cost-2.00 = 2.65 | 2016-06-23 | Mannu Pratap Rana | 100.94 | - | - | Not Started |  | - | Sri Sunil Kumar | Sri Rajendra Prasad Singh | LOA issued
7 | Kishanganj | TRAUMA CENTRE AT DISTRICT HOSPITAL, KISHANGANJ (LVL-III) | Building Cost-0.65 Eq. Cost-2.00 = 2.65 | 2018-08-14 | Kanika Shree Civcon (OPC) Pvt Ltd | 107.4 | 2019-03-08 | 2019-09-07 | Not Started | - | - | Sri Shashi Shekhar | Md. Shamim Ahmad | Land not clear
8 | Gopalganj | TRAUMA CENTRE AT DISTRICT HOSPITAL, GOPALGANJ (LVL-III) | Building Cost-0.65 Eq. Cost-2.00 = 2.65 | 2018-08-14 | - | - | - | - | Work Not Started |  | - | Sri Sagar Jaiswal | Md. Shamim Ahmad | Re-Tender invited by NIT no-03/2019, Technical evaluation under process
9 | Madhubani | TRAUMA CENTRE AT JHANJHARPUR, MADHUBANI (LVL-III) | Building Cost-0.65 Eq. Cost-2.00 = 2.65 | 2019-01-07 | - | - | - | - | Work Not Started |  | - | Sri Sunil Kumar | Md. Shamim Ahmad | Re-Tender invited by NIT no-03/2019, Technical evaluation under process

## Staff Quarter
Staff Quarter (For Doctor & Staff)
SL NO | Name of work |  | Administrative Approval Amount (in Rs. Lakh) | No of Projects |  | In Tender Stage |  | Total no. of Projects | Tender Finalized | Ongoing Projects |  | Not Started Projects |  | Remarks
1 | Construction of Medical Officer & Staff Quarter |  | 9600.00 (128.00 per unit) | 75 |  | 32 |  | 16 | 43 | 20 |  | 9 |  | -
Detailed report
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | Stage | % | (Rs in lakh)
1 | Nawada | Construction of MO & Staff Quarter at CHC Govindpur | 128 | 2016-11-22 | Md. Rais Khan | 293.2349 | - | - | Brick work is going on | 45% | -
2 | Nawada | Construction of MO & Staff Quarter at CHC Akbarpur | 128 | 2016-11-22 | Md. Rais Khan |  | - | - | Roof casted (1st Floor) | 30% | -
3 | Nawada | Construction of MO & Staff Quarter at CHC Narhat | 128 | 2016-11-22 | Md. Rais Khan |  | - | - | Not Started | - | - |  |  | Land not available, Letter sent to C.S. vide letter no-2147 date-09.08.2018
4 | Arwal | Construction of MO & Staff Quarter at CHC Karpi | 128 | 2016-11-22 | Pawan Shekher | 197.5567 | 2018-08-14 | 2019-05-13 | Finishing stage | 80% | 64.692 |  |  | Work started after tree cutting
5 | Arwal | Construction of MO & Staff Quarter at CHC Kurtha | 128 | 2016-11-22 | Pawan Shekher |  |  |  | Completed | 100%
6 | Aurangabad | Construction of MO & Staff Quarter at CHC Deo | 128 | 2016-11-22 | M/s Sand Stone | 198.5649 | 2018-11-09 | 2019-08-08 | Finishing work | 75% | 60.85
7 | Aurangabad | Construction of MO & Staff Quarter at CHC Madanpur | 128 | 2016-11-22 | M/s Sand Stone |  |  |  | Not started | - | - |  |  | Old building available on proposed site. Letter sent to Medical Officer I/C, Madanpur vide Letter no-1280, Dated- 25.06.2018 for demolition of old building. Civil surgeon vide letter no 1711, Dated-07.09.2018 instructed Medical Officer I/C, Madanpur for the auction.
8 | Gaya | Construction of MO & Staff Quarter at CHC Belaganj | 128 | 2016-11-22 | Mohan Sharma | 193.4605 | 2018-12-07 | 2019-09-06 | Roof shuttering (G.F) | 25% | 27.22
9 | Gaya | Construction of MO & Staff Quarter at CHC Bajirganj | 128 | 2016-11-22 | Mohan Sharma |  |  |  | Roof shuttering (G.F) | 28% |  |  |  | work started after demolished the old building
10 | Gaya | Construction of MO & Staff Quarter at CHC Manpur | 128 | 2016-11-22 | Saroj Kumar | 200.1102 | 2018-12-07 | 2019-09-06 | Foundation work | 5% | -
11 | Gaya | Construction of MO & Staff Quarter at CHC Khijarsarai | 128 | 2016-11-22 | Saroj Kumar |  |  |  | Roof Level (G.F) | 20% | 21.4
12 | Gaya | Construction of MO & Staff Quarter at CHC Konch | 128 | 2016-11-22 | Dhananjay Kumar | - | - | - | Not started | - | - |  |  | LOA to be issued
13 | Gaya | Construction of MO & Staff Quarter at CHC Gurua | 128 | 2016-11-22 | Dhananjay Kumar | - | - | - | Not started | - | - |  |  | LOA to be issued
14 | Gaya | Construction of MO & Staff Quarter at CHC Amas | 128 | 2016-11-22 | Sanju Kumari | 200.1102 | 2018-11-29 | 2018-12-07 | Pile cap work is going on | 10% | -
15 | Gaya | Construction of MO & Staff Quarter at CHC Imamganj | 128 | 2016-11-22 | Sanju Kumari |  |  |  | Roof Level (G.F) | 20% | 16
16 | Gaya | Construction of MO & Staff Quarter at CHC Barachatti | 128 | 2016-11-22 | Ram pukar singh | - | - | - | Not Started | - | - |  |  | Tender Finalized. LOA to be issued
17 | Gaya | Construction of MO & Staff Quarter at CHC Pariya | 128 | 2016-11-22 | Ram pukar singh | - | - | - | Not Started | - | - |  |  | Tender Finalized. LOA to be issued
18 | Jehanabad | Construction of MO & Staff Quarter at CHC Hulasganj | 128 | 2016-11-22 | Mohan Sharma | 209.1775 | 2018-12-07 | 2018-08-06 | Roof shuttering (G.F) | 25%
19 | Jehanabad | Construction of MO & Staff Quarter at CHC Kako | 128 | 2016-11-22 | Mohan Sharma |  |  |  | Not Started | - |  |  |  | Land clearence is in process
20 | Nalanda | Construction of MO & Staff Quarter at CHC Hilsa | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender to be Invited
21 | Nalanda | Construction of MO & Staff Quarter at Sub-Divisional Rajgir | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender to be Invited
22 | Nalanda | Construction of MO & Staff Quarter at Sadar Hospital, Nalanda | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender to be Invited
23 | Bhojpur | Construction of MO & Staff Quarter at CHC Piro | 128 | 2016-11-22 | Santosh Kumar Pandey | 206.9462 | 2018-09-11 | 2019-08-08 | Finishing work | 95%
24 | Bhojpur | Construction of MO & Staff Quarter at CHC Bihiyan | 128 | 2016-11-22 | Santosh Kumar Pandey |  |  |  | Finishing work | 95%
25 | Bhojpur | Construction of MO & Staff Quarter at CHC Udwant Nagar | 128 | 2016-11-22 | Santosh Kumar Pandey | 199.8131 | 2018-09-11 | 2019-08-08 | Finishing work | 95%
26 | Bhojpur | Construction of MO & Staff Quarter at CHC Barhara | 128 | 2016-11-22 | Santosh Kumar Pandey |  |  |  | Finishing work | 95%
27 | Bhojpur | Construction of MO & Staff Quarter at CHC Rajpur | 128 | 2016-11-22 | MDS Infranirman | 214.3617 | 2018-09-17 | 2019-06-16 | Brick work is going on | 55% | 51
28 | Bhojpur | Construction of MO & Staff Quarter at Sadar Hospital, Bhojpur | 128 | 2016-11-22 | MDS Infranirman |  |  |  | Roof casted (F.F) | 55%
29 | Rohtas | Construction of MO & Staff Quarter at CHC Chenari | 128 | 2016-11-22 | Dharmendra Pandey | 100.5029 | 2018-12-05 | 2019-09-04 | Finishing woRK | 80% | 78
30 | Kaimur | Construction of MO & Staff Quarter at CHC Chand | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | Tender Invited vide NIT no-12/2017 (Two bidder participated in this Tender & One bidder technically disqualify). Hence, Retender to be invited)
31 | Kaimur | Construction of MO & Staff Quarter at CHC Chainpur | 128 | 2016-11-22 | - | - | - | - | Not Started | - | -
32 | Kaimur | Construction of MO & Staff Quarter at CHC Bhagwanpur | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | In Tender
33 | Kaimur | Construction of MO & Staff Quarter at CHC Kudra | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | In Tender
34 | Jamui | Construction of MO & Staff Quarter at CHC Sono | 128 | 2016-11-22 | Brajesh Kumar Singh | 197.75 | - | - | Not Started | - | - |  |  | Tender Finalized. LOA to be issued
35 | Jamui | Construction of MO & Staff Quarter at CHC Kahaira | 128 | 2016-11-22 | Brajesh Kumar Singh |  | - | - | Not Started | - | - |  |  | Tender Finalized. LOA to be issued
36 | Jamui | Construction of MO & Staff Quarter at CHC Sikandra | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | Tender Invited vide NIT no-12/2017 (Two bidder participated in this Tender & One bidder technically disqualify). Hence, Retender to be invited)
37 | Jamui | Construction of MO & Staff Quarter at Sadar Hospital, Jamui | 128 | 2016-11-22 | - | - | - | - | Not Started | - | -
38 | Lakhisarai | Construction of MO & Staff Quarter at CHC Suryagarha | 128 | 2016-11-22 | Kanahaya Contract Pvt Ltd | 101.9719 | - | - | Not Started | - | - |  |  | T.S work in process
39 | Banka | Construction of MO & Staff Quarter at CHC Behlar | 128 | 2016-11-22 | Gurudev Engicon | 197.75 | - | - | Not Started | - | - |  |  | Financial bid opened. Due to Single bid Tender will be decided by board
40 | Banka | Construction of MO & Staff Quarter at CHC Chanan | 128 | 2016-11-22 | Gurudev Engicon |  | - | - | Not Started | - | -
41 | Khagaria | Construction of MO & Staff Quarter at CHC Alauli | 128 | 2016-11-22 | - | - | - | - | Not Started | - | - |  |  | Tender Invited vide NIT no-12/2017 (Two bidder participated in this Tender & One bidder technically disqualify). Hence, Retender to be invited)
42 | Khagaria | Construction of MO & Staff Quarter at Sadar Hospital, Khagaria | 128 | 2016-11-22 | - | - | - | - | Not Started | - | -
43 | Munger | Construction of MO & Staff Quarter at CHC Haveli Kharagpur | 128 | 2016-11-22 | Gurudev Engicon | 211.48 | - | - | Not Started | - | - |  |  | LOA to be issued
44 | Munger | Construction of MO & Staff Quarter at CHC Sangrampur | 128 | 2016-11-22 | Gurudev Engicon | - | - | - | Foundation work is going on | 10% | -
45 | Munger | Construction of MO & Staff Quarter at CHC Dharhara | 128 | 2016-11-22 | Uma Shankar Roy | 211.4896 |  |  | Not Started |  |  |  |  | T.S work in process
46 | Munger | Construction of MO & Staff Quarter at Sadar Hospital Munger | 128 | 2016-11-22 | Uma Shankar Roy |  |  |  | Not Started
47 | Begusarai | Construction of MO & Staff Quarter at Sub-Divisional Hospital Baliya | 128 | 2016-11-22 | Astha & Saumya Construction | 199.1173 |  |  | Not Started |  |  |  |  | T.S work in process
48 | Begusarai | Construction of MO & Staff Quarter at Sadar Hospital Begusarai | 128 | 2016-11-22 | Astha & Saumya Construction |  |  |  | Not Started
49 | Muzaffrapur | Construction of MO & Staff Quarter at CHC Minapur | 128 | 2016-11-22 | Regal Infra Trading Pvt Ltd | 100.7013 |  |  | Not Started |  |  |  |  | Work order to be issued
50 | Vaishali | Construction of MO & Staff Quarter at CHC Patepur | 128 | 2016-11-22 | Life Vision Construction Pvt Ltd | 103.6213 | 2019-02-20 | 2019-11-19 | Pile cap work is going on | 12%
51 | Sheohar | Construction of MO & Staff Quarter at CHC Piprahi | 128 | 2016-11-22 | Mother India Construction Pvt Ltd | 105.722 |  |  | Roof casted (G.F) | 25%
52 | Siwan | Construction of MO & Staff Quarter at Sadar Hospital, Siwan | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Three bidder participated in this Tender & Two bidder technically disqualify). Hence, Retender to be invited)
53 | Sitamarhi | Construction of MO & Staff Quarter at CHC Runni Saidpur | 128 | 2016-11-22 | Dilip Kumar Mishra | 211.4976 | 2019-02-20 | 2019-11-19 | Roof casted (G.F) | 38%
54 | Sitamarhi | Construction of MO & Staff Quarter at CHC Belsand | 128 | 2016-11-22 | Dilip Kumar Mishra |  |  |  | Plinth work is going on | 15%
55 | Sitamarhi | Construction of MO & Staff Quarter at CHC Nanpur | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Two bidder participated in this Tender & both bidder technically disqualify). Hence, Retender to be invited)
56 | Sitamarhi | Construction of MO & Staff Quarter at CHC Riga | 128 | 2016-11-22 | - |  |  |  | Not Started
57 | Kishanganj | Construction of MO & Staff Quarter at CHC Chhatraganch | 128 | 2016-11-22 | Md. Makbul Alam | 105.3427 |  |  | M.O-Ground Roof casting completed. Staff Quarter- Piling started | 25%
58 | East Champaran | Construction of MO & Staff Quarter at CHC Patahi | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender to be invited
59 | East Champaran | Construction of MO & Staff Quarter at CHC Madhuban | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Retender to be invited
60 | East Champaran | Construction of MO & Staff Quarter at CHC Chiraiyan | 128 | 2016-11-22 | Asiana Contract Pvt Ltd | 224.1919 |  |  | Not Started |  |  |  |  | LOA to be issued
61 | East Champaran | Construction of MO & Staff Quarter at CHC Keshariyan | 128 | 2016-11-22 | Asiana Contract Pvt Ltd |  |  |  | Not Started |  |  |  |  | LOA to be issued
62 | West Champaran | Construction of MO & Staff Quarter at CHC Sikta | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Single Bidder) Retender invited vide Nit no-11/2018 (One bidder participated in tender but bidder has been technically disqualified). Hence Retender to be invited
63 | West Champaran | Construction of MO & Staff Quarter at CHC Chanpatiyan | 128 | 2016-11-22 | - |  |  |  | Not Started
64 | West Champaran | Construction of MO & Staff Quarter at CHC Jogpatti | 128 | 2016-11-22 | - |  |  |  | Not Started
65 | West Champaran | Construction of MO & Staff Quarter at CHC Manjhauliya | 128 | 2016-11-22 | Rajnish Kumar Singh | 318.29 |  |  | Not Started |  |  |  |  | Financial bid opened. Due to Single bid Tender will be decided by board
66 | West Champaran | Construction of MO & Staff Quarter at CHC Bairiya | 128 | 2016-11-22 | Rajnish Kumar Singh |  |  |  | Not Started
67 | West Champaran | Construction of MO & Staff Quarter at CHC Ramnagar | 128 | 2016-11-22 | Rajnish Kumar Singh |  |  |  | Not Started
68 | West Champaran | Construction of MO & Staff Quarter at CHC Manatand | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Single Bidder) Retender invited vide Nit no-11/2018 but Tender not received. Hence Retender to be invited
69 | West Champaran | Construction of MO & Staff Quarter at CHC Madhubani | 128 | 2016-11-22 | - |  |  |  | Not Started
70 | West Champaran | Construction of MO & Staff Quarter at CHC Tharkarha | 128 | 2016-11-22 | - |  |  |  | Not Started
71 | West Champaran | Construction of MO & Staff Quarter at CHC Nautan | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender Invited vide NIT no-12/2017 (Single Bidder) Retender invited vide Nit no-11/2018 but Tender not received. Hence Retender to be invited
72 | West Champaran | Construction of MO & Staff Quarter at CHC Bagha-2 | 128 | 2016-11-22 | - |  |  |  | Not Started
73 | West Champaran | Construction of MO & Staff Quarter at Sub-Divisional Bagha | 128 | 2016-11-22 | - |  |  |  | Not Started
74 | West Champaran | Construction of MO & Staff Quarter at CHC Bhitaha | 128 | 2016-11-22 | - |  |  |  | Not Started |  |  |  |  | Tender invited vide Nit no-12/2017 (Two bidder participated in tender & one bidder technically disqualified) Hence Retender to be invited
75 | West Champaran | Construction of MO & Staff Quarter at CHC Piprasi | 128 | 2016-11-22 | - |  |  |  | Not Started
|  | Total | 9600

## Eye Bank
REPORT OF EYE BANK
SL NO | DISTRICT | NAME OF WORK | ADMINISTRATIVE APPROVAL DETAIL |  | NAME OF CONTRACTOR | AGREEMENT AMOUNT | DATE OF START | DATE OF COMPLETION | PHYSICAL |  | UP TO DATE PAYMENT | NAME OF Dy.G.M | NAME OF G.M | REMARKS
|  |  | Amount (in rs lakh) | Date |  | (Rs in lakh) |  |  | STAGE | % | (Rs in lakh)
1 | Patna | RENOVATION OF EYE BANK AT PMCH, PATNA | 118.5988 | 2018-02-21 | M/s Gauri Homes Pvt. Ltd. | 19.06 | 2018-06-29 | 2018-08-28 | Completed | 100% | 7.78 | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Handed over
2 | Bhagalpur | RENOVATION OF EYE BANK AT JLMNCH, BHAGALPUR | 117.32 | 2018-02-21 | Shabnam Sharma | 18.1 | 2018-06-21 | 2018-08-20 | Completed | 100% | 18.1 | Sri Anil Kumar | Sri Sanjeev Ranjan | Handed over
3 | Muzaffarpur | CONSTRUCTION OF EYE BANK AT SKMCH, MUZAFFARPUR | 124.36 | 2018-02-21 | M/s Harendra Construction | 23.98 | 2018-07-09 | 2018-10-08 | Completed | 100% | 4.36 | Sri Arjun Kumar Mishra | Sri Rajendra Prasad
4 | Darbhanga | CONSTRUCTION OF EYE BANK AT DMCH, DARBHANGA | 124.36 | 2018-02-21 | M/s Harendra Construction | 23.83 | 2018-07-05 | 2018-10-04 | Completed | 100% | 9.1617 | Sri Sunil Kumar | Sri Rajendra Prasad | Letter sent for Handed over vide Letter no- 4081 Dated-29.11.2018 & Letter no- 4728, Dated-04.01.2019
5 | Gaya | CONSTRUCTION OF EYE BANK AT ANMMCH, GAYA | 148.63 | 2018-02-21 | M/s Gauri Homes Pvt. Ltd. | 43.14 | 2018-07-25 | 2018-10-24 | Completed | 100% | 20 | Sri Pankaj Kumar | Sri Sanjeev Ranjan | Handed over
6 | Bettiah | CONSTRUCTION OF EYE BANK AT GOVT. MEDICAL COLLEGE & HOSPITAL, BETTIAH | 124.36 | 2018-02-21 | M/s Harendra Construction | 24.41 | 2018-07-18 | 2018-10-17 | Completed | 100% | 20.01 | Md. Nasim Akhtar Ansari | Sri Rajendra Prasad | Letter sent for Handed over vide Letter no- 3766, Dated-15.11.2018
7 | Patna | CONSTRUCTION OF EYE BANK AT NMCH, PATNA | 170.32 | [8 empty] | Sri Arjun Kumar Mishra | Sri Sanjeev Ranjan | Tender Invited vide NIT no- 41/2018, Last date of receipt of Tender-25/01/2019
|  | Total | 927.9488